## PRINTOUT
CP CHEM: 7052 |  | 1295 Spools |  | 936 Workable |  | 1148 Issued
SPOOLS BY SCOPE | [5 empty] | Workable Man Hours (By Material)
SPOOLS | Performance | Client | Other | TOTAL |  |  |  | Carbon | Stainless | TOTAL
Valves | [5 empty] | Workable Man Hours
Flanges
Fittings | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
Pipe | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Supports | [5 empty] | Valves
Issued | [5 empty] | Flanges
Workable (Not Issued) | [5 empty] | Fittings
Issued (Missing Items) | [5 empty] | Supports
On Hold (No Shorts) | [5 empty] | TOTAL
Discrepancies
TOTAL | [5 empty] | Pipe
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Supports | [5 empty] | Supports
TOTAL | [5 empty] | TOTAL
Pipe | [5 empty] | Pipe
Not on Line List | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Purchased
7052 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
Nozzle |  | 153 | 0 | 0 | 153 | 145 | 8 | 0 | 120 | 33 | 0% | 94.8% | 78.4%
J30 | 1 | 9 | 0 | 3 | 6 | 3 | 6 | 3 | 3 | 6 | 33.3% | 33.3% | 33.3%
J14 | 2 | 123 | 0 | 121 | 2 | 121 | 2 | 0 | 121 | 2 | 98.4% | 98.4% | 98.4%
J23 | 3 | 45 | 0 | 45 | 0 | 44 | 1 | 44 | 43 | 2 | 100% | 97.8% | 95.6%
J32 | 4 | 237 | 0 | 217 | 20 | 224 | 13 | 131 | 179 | 58 | 91.6% | 94.5% | 75.5%
J06 | 5 | 151 | 5 | 76 | 75 | 73 | 78 | 65 | 58 | 93 | 50.3% | 48.3% | 38.4%
J07 | 5 | 150 | 5 | 80 | 70 | 68 | 82 | 56 | 62 | 88 | 53.3% | 45.3% | 41.3%
J21 | 6 | 42 | 0 | 41 | 1 | 41 | 1 | 31 | 41 | 1 | 97.6% | 97.6% | 97.6%
J20 | 6 | 21 | 1 | 20 | 1 | 21 | 0 | 21 | 17 | 4 | 95.2% | 100% | 81.0%
J04 | 7 | 158 | 0 | 150 | 8 | 148 | 10 | 14 | 140 | 18 | 94.9% | 93.7% | 88.6%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 40 | 42 | 0 | 100% | 100% | 100%
J25 | 8 | 39 | 2 | 25 | 14 | 22 | 17 | 1 | 18 | 21 | 64.1% | 56.4% | 46.2%
J10 | 8 | 10 | 1 | 7 | 3 | 5 | 5 | 5 | 4 | 6 | 70.0% | 50.0% | 40.0%
J19 | 9 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 1 | 2 | 100% | 100% | 33.3%
J03 | 10 | 9 | 0 | 9 | 0 | 9 | 0 | 9 | 9 | 0 | 100% | 100% | 100%
J13 | 11 | 22 | 0 | 22 | 0 | 22 | 0 | 10 | 21 | 1 | 100% | 100% | 95.5%
J18 | 11 | 25 | 0 | 25 | 0 | 25 | 0 | 12 | 25 | 0 | 100% | 100% | 100%
J01 | 12 | 53 | 0 | 47 | 6 | 46 | 7 | 32 | 45 | 8 | 88.7% | 86.8% | 84.9%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 3 | 0 | 100% | 100% | 100%
TOTALS |  | 1295 | 14 | 936 | 359 | 1065 | 230 | 477 | 952 | 343 | 72% | 82% | 74%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
Nozzle |  | 153 | 0 | 0 | 153 | 145 | 8 | 0 | 120 | 33 | 0% | 94.8% | 78.4%
J30 | 1 | 9 | 0 | 3 | 6 | 3 | 6 | 3 | 3 | 6 | 33.3% | 33.3% | 33.3%
J14 | 2 | 123 | 0 | 121 | 2 | 121 | 2 | 0 | 121 | 2 | 98.4% | 98.4% | 98.4%
J23 | 3 | 45 | 0 | 45 | 0 | 44 | 1 | 44 | 43 | 2 | 100% | 97.8% | 95.6%
J32 | 4 | 237 | 0 | 217 | 20 | 224 | 13 | 131 | 179 | 58 | 91.6% | 94.5% | 75.5%
J06 | 5 | 151 | 5 | 76 | 75 | 73 | 78 | 65 | 58 | 93 | 50.3% | 48.3% | 38.4%
J07 | 5 | 150 | 5 | 80 | 70 | 68 | 82 | 56 | 62 | 88 | 53.3% | 45.3% | 41.3%
J21 | 6 | 42 | 0 | 41 | 1 | 41 | 1 | 31 | 41 | 1 | 97.6% | 97.6% | 97.6%
J20 | 6 | 21 | 1 | 20 | 1 | 21 | 0 | 21 | 17 | 4 | 95.2% | 100% | 81.0%
J04 | 7 | 158 | 0 | 150 | 8 | 148 | 10 | 14 | 140 | 18 | 94.9% | 93.7% | 88.6%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 40 | 42 | 0 | 100% | 100% | 100%
J25 | 8 | 39 | 2 | 25 | 14 | 22 | 17 | 1 | 18 | 21 | 64.1% | 56.4% | 46.2%
J10 | 8 | 10 | 1 | 7 | 3 | 5 | 5 | 5 | 4 | 6 | 70.0% | 50.0% | 40.0%
J19 | 9 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 1 | 2 | 100% | 100% | 33.3%
J03 | 10 | 9 | 0 | 9 | 0 | 9 | 0 | 9 | 9 | 0 | 100% | 100% | 100%
J13 | 11 | 22 | 0 | 22 | 0 | 22 | 0 | 10 | 21 | 1 | 100% | 100% | 95.5%
J18 | 11 | 25 | 0 | 25 | 0 | 25 | 0 | 12 | 25 | 0 | 100% | 100% | 100%
J01 | 12 | 53 | 0 | 47 | 6 | 46 | 7 | 32 | 45 | 8 | 88.7% | 86.8% | 84.9%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 3 | 0 | 100% | 100% | 100%
TOTALS |  | 1295 | 14 | 936 | 359 | 1065 | 230 | 477 | 952 | 343 | 72% | 82% | 74%

## Areas Summary (By Material)
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J04 | 7 | 154 | 0 | 146 | 8 | 144 | 10 | 12 | 140 | 14 | 94.8% | 93.5% | 90.9%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 40 | 42 | 0 | 100% | 100% | 100%
J18 | 11 | 13 | 0 | 13 | 0 | 13 | 0 | 0 | 13 | 0 | 100% | 100% | 100%
J13 | 11 | 12 | 0 | 12 | 0 | 12 | 0 | 0 | 12 | 0 | 100% | 100% | 100%
J32 | 4 | 38 | 0 | 38 | 0 | 38 | 0 | 0 | 37 | 1 | 100% | 100% | 97.4%
Nozzle |  | 31 | 0 | 0 | 31 | 30 | 1 | 0 | 8 | 23 | 0% | 96.8% | 25.8%
TOTALS |  | 290 | 0 | 251 | 39 | 279 | 11 | 52 | 252 | 38 | 87% | 96% | 87%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J13 | 11 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 9 | 1 | 100% | 100% | 90.0%
J18 | 11 | 12 | 0 | 12 | 0 | 12 | 0 | 12 | 12 | 0 | 100% | 100% | 100%
J01 | 12 | 28 | 0 | 28 | 0 | 28 | 0 | 28 | 27 | 1 | 100% | 100% | 96.4%
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 3 | 0 | 100% | 100% | 100%
J03 | 10 | 9 | 0 | 9 | 0 | 9 | 0 | 9 | 9 | 0 | 100% | 100% | 100%
J23 | 3 | 45 | 0 | 45 | 0 | 44 | 1 | 44 | 43 | 2 | 100% | 97.8% | 95.6%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 3 | 0 | 100% | 100% | 100%
J32 | 4 | 199 | 0 | 179 | 20 | 186 | 13 | 131 | 142 | 57 | 89.9% | 93.5% | 71.4%
J07 | 5 | 121 | 5 | 54 | 67 | 42 | 79 | 39 | 36 | 85 | 44.6% | 34.7% | 29.8%
J06 | 5 | 122 | 5 | 51 | 71 | 47 | 75 | 44 | 36 | 86 | 41.8% | 38.5% | 29.5%
J21 | 6 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 20 | 0 | 100% | 100% | 100%
J20 | 6 | 11 | 1 | 10 | 1 | 11 | 0 | 11 | 9 | 2 | 90.9% | 100% | 81.8%
J04 | 7 | 4 | 0 | 4 | 0 | 4 | 0 | 2 | 0 | 4 | 100% | 100% | 0.0%
J10 | 8 | 10 | 1 | 7 | 3 | 5 | 5 | 5 | 4 | 6 | 70.0% | 50.0% | 40.0%
J25 | 8 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 3 | 50.0% | 50.0% | 25.0%
TOTALS |  | 601 | 14 | 437 | 164 | 426 | 175 | 362 | 354 | 247 | 73% | 71% | 59%
A333 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 4 | 0 | 100% | 100% | 100%
J20 | 6 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 8 | 2 | 100% | 100% | 80.0%
J21 | 6 | 12 | 0 | 11 | 1 | 11 | 1 | 11 | 11 | 1 | 91.7% | 91.7% | 91.7%
TOTALS |  | 26 | 0 | 25 | 1 | 25 | 1 | 25 | 23 | 3 | 96% | 96% | 88%
ALUMINUM Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 122 | 0 | 120 | 2 | 120 | 2 | 0 | 120 | 2 | 98.4% | 98.4% | 98.4%
J01 | 12 | 17 | 0 | 11 | 6 | 10 | 7 | 0 | 10 | 7 | 64.7% | 58.8% | 58.8%
J19 | 9 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 1 | 2 | 100% | 100% | 33.3%
J25 | 8 | 35 | 0 | 23 | 12 | 20 | 15 | 0 | 17 | 18 | 65.7% | 57.1% | 48.6%
Nozzle |  | 122 | 0 | 0 | 122 | 115 | 7 | 0 | 112 | 10 | 0% | 94.3% | 91.8%
TOTALS |  | 299 | 0 | 157 | 142 | 268 | 31 | 0 | 260 | 39 | 53% | 90% | 87%
304/304L SS CRYO Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 100% | 100% | 100%
J21 | 6 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0 | 100% | 100% | 100%
TOTALS |  | 14 | 0 | 14 | 0 | 14 | 0 | 0 | 14 | 0 | 100% | 100% | 100%
Galv. Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J06 | 5 | 29 | 0 | 25 | 4 | 26 | 3 | 21 | 22 | 7 | 86.2% | 89.7% | 75.9%
J07 | 5 | 29 | 0 | 26 | 3 | 26 | 3 | 17 | 26 | 3 | 89.7% | 89.7% | 89.7%
TOTALS |  | 58 | 0 | 51 | 7 | 52 | 6 | 38 | 48 | 10 | 88% | 90% | 83%
A105 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 100% | 100% | 100%
TOTALS |  | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 100% | 100% | 100%
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 0% | 0.0% | 0.0%
TOTALS |  | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 0% | 0% | 0%

## Spool Location
Not Workable | 345
Workable | 0
Issued | 7
Pulled | 26
Welded Out | 43
Shipped to Coating | 18
Ready To Deliver | 12
Delivered | 830
On Hold | 14

## Shorts by Scope
| 1295 Spools | 936 Workable | 1148 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 9 | 0 | 9
Flanges | 17 | 0 | 0 | 17
Fittings | 34 | 0 | 0 | 34
Supports | 30 | 0 | 0 | 30
TOTAL | 81 | 9 | 0 | 90
Pipe | 117.7 | 0 | 0 | 117.7
Not on Line List

## Purchased by Scope
| 1295 Spools | 936 Workable | 1148 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 1 | 0 | 1
Flanges | 2 | 0 | 0 | 2
Fittings | 4 | 0 | 0 | 4
Supports | 0 | 0 | 0 | 0
TOTAL | 6 | 1 | 0 | 7
Pipe | 98.7 | 0 | 0 | 98.7

## No Material by Scope
| 1295 Spools | 936 Workable | 1148 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 8 | 0 | 8
Flanges | 15 | 0 | 0 | 15
Fittings | 30 | 0 | 0 | 30
Supports | 30 | 0 | 0 | 30
TOTAL | 75 | 8 | 0 | 83
Pipe | 19 | 0 | 0 | 19

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 7 | 7

## Spools by Scope
| 1295 Spools | 936 Workable | 1148 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 9 | 0 | 9
Flanges | 32 | 0 | 0 | 32
Fittings | 11 | 0 | 0 | 11
Pipe | 7 | 0 | 0 | 7
Supports | 3 | 0 | 0 | 3
Issued |  |  |  | 1148
Workable (Not Issued) |  |  |  | 0
Issued (Missing Items) |  |  |  | 43
On Hold (No Shorts) |  |  |  | 3
Discrepancies |  |  |  | 806
TOTAL | 53 | 9 | 0 | 1295

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)
72-3 |  |  | PK101XA-FW-100430.01-1
72-4 |  |  | PK101XA-FW-102003.01-1
74-2 |  |  | PK101XA-FW-102004.01-1
74-3 |  |  | PK101XA-FW-102331.01-1
76-1 |  |  | PK101XA-FW-102333.01-1
77-1 |  |  | PK101XA-FW-102336.01-1
86-2 |  |  | 7052-CCW-VALVE-564-1
86-3 |  |  | 7052-CCW-VALVE-565-1
92-2 |  |  | 7052-CCW-VALVE-568-1
92-3 |  |  | 7052-CCW-VALVE-573-1
94-1 |  |  | 7052-CCW-VALVE-574-1
94-2 |  |  | 7052-CCW-VALVE-575-1
95-1 |  |  | 7052-CCW-VALVE-576-1
95-2 |  |  | 7052-CS-VALVE-569-1
96-1 |  |  | 7052-CS-VALVE-570-1
96-2 |  |  | 7052-CW-VALVE-566-1
96-3 |  |  | 7052-CW-VALVE-567-1
97-1 |  |  | 7052-GN-VALVE-563-1
97-2 |  |  | 7052-GN-VALVE-571-1
216-1 |  |  | 7052-GN-VALVE-572-1
217-3 |  |  | PM110XA-CS-99999.09-4
218-5
218-7
219-9
219-17
221-1
241-2
296-3
328-2
329-1
330-1
331-1
332-1
340-1
388-1
512-1
512-2
2167-1
2171-1
2172-1
2178-1
2180-1
2183-1