## PRINTOUT
undefined: 7114 |  | 2694 Spools |  | 1911 Workable |  | 523 Issued |  | NaN Workable Man Hours
SPOOLS BY SCOPE | [5 empty] | Workable Man Hours (By Material)
SPOOLS | Performance | Client | Other | TOTAL |  |  |  | Carbon | Stainless | TOTAL
Valves | [5 empty] | Workable Man Hours |  | 0 | 0 | 0
Flanges
Fittings | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
Pipe | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Supports | [5 empty] | Valves
Issued | [5 empty] | Flanges
Workable (Not Issued) | [5 empty] | Fittings
Issued (Missing Items) | [5 empty] | Supports
On Hold (No Shorts) | [5 empty] | TOTAL
Discrepancies
TOTAL | [5 empty] | Pipe
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Supports | [5 empty] | Supports
TOTAL | [5 empty] | TOTAL
Pipe | [5 empty] | Pipe
Not on Line List | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Purchased
7114 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
7 |  | 202 | 0 | 202 | 0 | 0 | 202 | 0 | 0 | 202 | 100% | 0.0% | 0.0%
6 | 1C | 1726 | 42 | 943 | 783 | 181 | 1545 | 0 | 0 | 1726 | 54.6% | 10.5% | 0.0%
0 |  | 507 | 0 | 507 | 0 | 0 | 507 | 0 | 0 | 507 | 100% | 0.0% | 0.0%
3 |  | 67 | 0 | 67 | 0 | 0 | 67 | 0 | 0 | 67 | 100% | 0.0% | 0.0%
4 |  | 73 | 0 | 73 | 0 | 0 | 73 | 0 | 0 | 73 | 100% | 0.0% | 0.0%
2 |  | 95 | 0 | 95 | 0 | 0 | 95 | 0 | 0 | 95 | 100% | 0.0% | 0.0%
8 |  | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 100% | 0.0% | 0.0%
1 |  | 22 | 0 | 22 | 0 | 0 | 22 | 0 | 0 | 22 | 100% | 0.0% | 0.0%
TOTALS |  | 2694 | 42 | 3311 | -617 | 181 | 2513 | 0 | 0 | 2694 | 71% | 7% | 0%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
7 |  | 202 | 0 | 202 | 0 | 0 | 202 | 0 | 0 | 202 | 100% | 0.0% | 0.0%
6 | 1C | 1726 | 42 | 943 | 783 | 181 | 1545 | 0 | 0 | 1726 | 54.6% | 10.5% | 0.0%
0 |  | 507 | 0 | 507 | 0 | 0 | 507 | 0 | 0 | 507 | 100% | 0.0% | 0.0%
3 |  | 67 | 0 | 67 | 0 | 0 | 67 | 0 | 0 | 67 | 100% | 0.0% | 0.0%
4 |  | 73 | 0 | 73 | 0 | 0 | 73 | 0 | 0 | 73 | 100% | 0.0% | 0.0%
2 |  | 95 | 0 | 95 | 0 | 0 | 95 | 0 | 0 | 95 | 100% | 0.0% | 0.0%
8 |  | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 100% | 0.0% | 0.0%
1 |  | 22 | 0 | 22 | 0 | 0 | 22 | 0 | 0 | 22 | 100% | 0.0% | 0.0%
TOTALS |  | 2694 | 42 | 1911 | 783 | 181 | 2513 | 0 | 0 | 2694 | 71% | 7% | 0%

## Areas Summary (By Material)
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
7 |  | 202 | 0 | 202 | 0 | 0 | 202 | 0 | 0 | 202 | 100% | 0.0% | 0.0%
0 |  | 15 | 0 | 15 | 0 | 0 | 15 | 0 | 0 | 15 | 100% | 0.0% | 0.0%
4 |  | 73 | 0 | 73 | 0 | 0 | 73 | 0 | 0 | 73 | 100% | 0.0% | 0.0%
2 |  | 95 | 0 | 95 | 0 | 0 | 95 | 0 | 0 | 95 | 100% | 0.0% | 0.0%
6 |  | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 4 | 100% | 0.0% | 0.0%
1 |  | 22 | 0 | 22 | 0 | 0 | 22 | 0 | 0 | 22 | 100% | 0.0% | 0.0%
TOTALS |  | 411 | 0 | 411 | 0 | 0 | 411 | 0 | 0 | 411 | 100% | 0% | 0%
316/316L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
6 | 1C | 504 | 13 | 331 | 173 | 58 | 446 | 0 | 0 | 504 | 65.7% | 11.5% | 0.0%
0 |  | 111 | 0 | 111 | 0 | 0 | 111 | 0 | 0 | 111 | 100% | 0.0% | 0.0%
3 |  | 37 | 0 | 37 | 0 | 0 | 37 | 0 | 0 | 37 | 100% | 0.0% | 0.0%
TOTALS |  | 652 | 13 | 479 | 173 | 58 | 594 | 0 | 0 | 652 | 73% | 9% | 0%
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
6 | 1C | 548 | 13 | 240 | 308 | 21 | 527 | 0 | 0 | 548 | 43.8% | 3.8% | 0.0%
0 |  | 135 | 0 | 135 | 0 | 0 | 135 | 0 | 0 | 135 | 100% | 0.0% | 0.0%
3 |  | 5 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 5 | 100% | 0.0% | 0.0%
TOTALS |  | 688 | 13 | 380 | 308 | 21 | 667 | 0 | 0 | 688 | 55% | 3% | 0%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
6 | 1C | 365 | 12 | 160 | 205 | 55 | 310 | 0 | 0 | 365 | 43.8% | 15.1% | 0.0%
0 |  | 124 | 0 | 124 | 0 | 0 | 124 | 0 | 0 | 124 | 100% | 0.0% | 0.0%
3 |  | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 100% | 0.0% | 0.0%
TOTALS |  | 491 | 12 | 286 | 205 | 55 | 436 | 0 | 0 | 491 | 58% | 11% | 0%
CS-GALV Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
6 |  | 305 | 4 | 208 | 97 | 47 | 258 | 0 | 0 | 305 | 68.2% | 15.4% | 0.0%
0 |  | 122 | 0 | 122 | 0 | 0 | 122 | 0 | 0 | 122 | 100% | 0.0% | 0.0%
3 |  | 23 | 0 | 23 | 0 | 0 | 23 | 0 | 0 | 23 | 100% | 0.0% | 0.0%
8 |  | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 100% | 0.0% | 0.0%
TOTALS |  | 452 | 4 | 355 | 97 | 47 | 405 | 0 | 0 | 452 | 79% | 10% | 0%

## Spool Location
Not Workable | 741
Workable | 1400
Issued | 100
Pulled | 231
Welded Out | 180
Shipped to Coating | 0
Ready To Deliver | 0
Delivered | 0
On Hold | 42

## Shorts by Scope
| 2694 Spools | 1911 Workable | 523 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 636
Fittings | 0 | 0 | 1240
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 2156.8
Not on Line List

## Purchased by Scope
| 2694 Spools | 1911 Workable | 523 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 460
Fittings | 0 | 0 | 612
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 631.7

## No Material by Scope
| 2694 Spools | 1911 Workable | 523 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 176
Fittings | 0 | 0 | 628
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 1525.1

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 0

## Spools by Scope
| 2694 Spools | 1911 Workable | 523 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 313
Fittings | 0 | 0 | 293
Pipe | 0 | 0 | 148
Supports | 0 | 0 | 0
Issued |  |  |  | 523
Workable (Not Issued) |  |  |  | 1400
Issued (Missing Items) |  |  |  | 4
On Hold (No Shorts) |  |  |  | 9
Discrepancies |  |  |  | 12
TOTAL |  |  |  | 2694

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)
99-1 |  |  | 64339-P1B206AC-1
99-2 |  |  | 64339-P1B206AC-2
395 |  |  | 64339-P1B206AC-3
568-1 |  |  | 64339-P1B206AC-4