## PRINTOUT
CP CHEM: 7052 |  | 1019 Spools |  |  | 412 Workable |  |  | 417 Issued
SPOOLS BY SCOPE | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
SPOOLS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Pipe | [5 empty] | Supports
Supports | [5 empty] | TOTAL
Issued
Issued (Missing Items) | [5 empty] | Pipe
Workable (Not Issued)
On Hold (No Shorts)
Discrepancies | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
TOTAL | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Valves
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | Flanges
ITEMS | Performance | Client | Other | TOTAL |  | Fittings
Valves | [5 empty] | Supports
Flanges | [5 empty] | TOTAL
Fittings
Supports | [5 empty] | Pipe
TOTAL
Pipe | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Not on Line List | [5 empty] | Purchased
7052 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 100% | 100% | 0.0%
J14 | 2 | 123 | 3 | 0 | 123 | 0 | 123 | 0 | 0 | 123 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 5 | 37 | 8 | 33 | 12 | 0 | 0 | 45 | 82.2% | 73.3% | 0.0%
J32 | 4 | 242 | 80 | 123 | 119 | 32 | 210 | 0 | 0 | 242 | 50.8% | 13.2% | 0.0%
J06 | 5 | 83 | 50 | 19 | 64 | 6 | 77 | 0 | 0 | 83 | 22.9% | 7.2% | 0.0%
J07 | 5 | 94 | 61 | 19 | 75 | 6 | 88 | 0 | 0 | 94 | 20.2% | 6.4% | 0.0%
J21 | 6 | 42 | 1 | 24 | 18 | 21 | 21 | 0 | 0 | 42 | 57.1% | 50.0% | 0.0%
J20 | 6 | 21 | 3 | 12 | 9 | 9 | 12 | 0 | 0 | 21 | 57.1% | 42.9% | 0.0%
J04 | 7 | 156 | 40 | 89 | 67 | 17 | 139 | 0 | 0 | 156 | 57.1% | 10.9% | 0.0%
J05 | 7 | 42 | 4 | 20 | 22 | 2 | 40 | 0 | 0 | 42 | 47.6% | 4.8% | 0.0%
J25 | 8 | 39 | 24 | 2 | 37 | 0 | 39 | 0 | 0 | 39 | 5.1% | 0.0% | 0.0%
J10 | 8 | 10 | 6 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 0 | 7 | 2 | 2 | 7 | 0 | 0 | 9 | 77.8% | 22.2% | 0.0%
J13 | 11 | 22 | 6 | 16 | 6 | 6 | 16 | 0 | 0 | 22 | 72.7% | 27.3% | 0.0%
J18 | 11 | 25 | 4 | 21 | 4 | 14 | 11 | 0 | 0 | 25 | 84.0% | 56.0% | 0.0%
J01 | 12 | 53 | 6 | 20 | 33 | 9 | 44 | 0 | 0 | 53 | 37.7% | 17.0% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
TOTALS |  | 1019 | 300 | 413 | 606 | 160 | 859 | 0 | 0 | 1019 | 40% | 16% | 0%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 100% | 100% | 0.0%
J14 | 2 | 123 | 3 | 0 | 123 | 0 | 123 | 0 | 0 | 123 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 5 | 37 | 8 | 33 | 12 | 0 | 0 | 45 | 82.2% | 73.3% | 0.0%
J32 | 4 | 242 | 80 | 123 | 119 | 32 | 210 | 0 | 0 | 242 | 50.8% | 13.2% | 0.0%
J06 | 5 | 83 | 50 | 19 | 64 | 6 | 77 | 0 | 0 | 83 | 22.9% | 7.2% | 0.0%
J07 | 5 | 94 | 61 | 19 | 75 | 6 | 88 | 0 | 0 | 94 | 20.2% | 6.4% | 0.0%
J21 | 6 | 42 | 1 | 24 | 18 | 21 | 21 | 0 | 0 | 42 | 57.1% | 50.0% | 0.0%
J20 | 6 | 21 | 3 | 12 | 9 | 9 | 12 | 0 | 0 | 21 | 57.1% | 42.9% | 0.0%
J04 | 7 | 156 | 40 | 89 | 67 | 17 | 139 | 0 | 0 | 156 | 57.1% | 10.9% | 0.0%
J05 | 7 | 42 | 4 | 20 | 22 | 2 | 40 | 0 | 0 | 42 | 47.6% | 4.8% | 0.0%
J25 | 8 | 39 | 24 | 2 | 37 | 0 | 39 | 0 | 0 | 39 | 5.1% | 0.0% | 0.0%
J10 | 8 | 10 | 6 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 0 | 7 | 2 | 2 | 7 | 0 | 0 | 9 | 77.8% | 22.2% | 0.0%
J13 | 11 | 22 | 6 | 16 | 6 | 6 | 16 | 0 | 0 | 22 | 72.7% | 27.3% | 0.0%
J18 | 11 | 25 | 4 | 21 | 4 | 14 | 11 | 0 | 0 | 25 | 84.0% | 56.0% | 0.0%
J01 | 12 | 53 | 6 | 20 | 33 | 9 | 44 | 0 | 0 | 53 | 37.7% | 17.0% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
TOTALS |  | 1019 | 300 | 412 | 607 | 160 | 859 | 0 | 0 | 1019 | 40% | 16% | 0%

## Areas Summary (By Material)
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J04 | 7 | 152 | 36 | 89 | 63 | 17 | 135 | 0 | 0 | 152 | 58.6% | 11.2% | 0.0%
J05 | 7 | 42 | 4 | 20 | 22 | 2 | 40 | 0 | 0 | 42 | 47.6% | 4.8% | 0.0%
J18 | 11 | 13 | 2 | 11 | 2 | 8 | 5 | 0 | 0 | 13 | 84.6% | 61.5% | 0.0%
J13 | 11 | 12 | 4 | 8 | 4 | 4 | 8 | 0 | 0 | 12 | 66.7% | 33.3% | 0.0%
J32 | 4 | 38 | 6 | 32 | 6 | 4 | 34 | 0 | 0 | 38 | 84.2% | 10.5% | 0.0%
TOTALS |  | 257 | 52 | 160 | 97 | 35 | 222 | 0 | 0 | 257 | 62% | 14% | 0%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J13 | 11 | 10 | 2 | 8 | 2 | 2 | 8 | 0 | 0 | 10 | 80.0% | 20.0% | 0.0%
J18 | 11 | 12 | 2 | 10 | 2 | 6 | 6 | 0 | 0 | 12 | 83.3% | 50.0% | 0.0%
J01 | 12 | 28 | 0 | 18 | 10 | 7 | 21 | 0 | 0 | 28 | 64.3% | 25.0% | 0.0%
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 100% | 100% | 0.0%
J03 | 10 | 9 | 0 | 7 | 2 | 2 | 7 | 0 | 0 | 9 | 77.8% | 22.2% | 0.0%
J23 | 3 | 45 | 5 | 37 | 8 | 33 | 12 | 0 | 0 | 45 | 82.2% | 73.3% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
J32 | 4 | 204 | 74 | 91 | 113 | 28 | 176 | 0 | 0 | 204 | 44.6% | 13.7% | 0.0%
J06 | 5 | 73 | 40 | 19 | 54 | 6 | 67 | 0 | 0 | 73 | 26.0% | 8.2% | 0.0%
J07 | 5 | 66 | 33 | 19 | 47 | 6 | 60 | 0 | 0 | 66 | 28.8% | 9.1% | 0.0%
J21 | 6 | 20 | 0 | 16 | 4 | 13 | 7 | 0 | 0 | 20 | 80.0% | 65.0% | 0.0%
J20 | 6 | 11 | 3 | 4 | 7 | 2 | 9 | 0 | 0 | 11 | 36.4% | 18.2% | 0.0%
J04 | 7 | 4 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
J10 | 8 | 10 | 6 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J25 | 8 | 4 | 2 | 2 | 2 | 0 | 4 | 0 | 0 | 4 | 50.0% | 0.0% | 0.0%
TOTALS |  | 506 | 178 | 234 | 272 | 108 | 398 | 0 | 0 | 506 | 46% | 21% | 0%
A333 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 4 | 50.0% | 50.0% | 0.0%
J20 | 6 | 10 | 0 | 8 | 2 | 7 | 3 | 0 | 0 | 10 | 80.0% | 70.0% | 0.0%
J21 | 6 | 12 | 1 | 8 | 4 | 8 | 4 | 0 | 0 | 12 | 66.7% | 66.7% | 0.0%
TOTALS |  | 26 | 1 | 18 | 8 | 17 | 9 | 0 | 0 | 26 | 69% | 65% | 0%
ALUMINUM Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 122 | 2 | 0 | 122 | 0 | 122 | 0 | 0 | 122 | 0% | 0.0% | 0.0%
J01 | 12 | 17 | 6 | 0 | 17 | 0 | 17 | 0 | 0 | 17 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J25 | 8 | 35 | 22 | 0 | 35 | 0 | 35 | 0 | 0 | 35 | 0% | 0.0% | 0.0%
TOTALS |  | 177 | 30 | 0 | 177 | 0 | 177 | 0 | 0 | 177 | 0% | 0% | 0%
304/304L SS CRYO Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
J21 | 6 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
TOTALS |  | 14 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 14 | 0% | 0% | 0%
Galv. Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J06 | 5 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J07 | 5 | 28 | 28 | 0 | 28 | 0 | 28 | 0 | 0 | 28 | 0% | 0.0% | 0.0%
TOTALS |  | 38 | 38 | 0 | 38 | 0 | 38 | 0 | 0 | 38 | 0% | 0% | 0%
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0% | 0.0% | 0.0%
TOTALS |  | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0% | 0% | 0%

## Spool Location
Not Workable | 307
Workable | 1
Issued | 203
Pulled | 54
Welded Out | 103
Shipped to Coating | 0
Ready To Deliver | 0
Delivered | 0
On Hold | 294

## Shorts by Scope
| 1019 Spools | 412 Workable | 417 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 41 | 0
Flanges | 456 | 0 | 0
Fittings | 111 | 0 | 0
Supports | 17 | 0 | 0
TOTAL
Pipe | 3198.2 | 0 | 0
Not on Line List

## Purchased by Scope
| 1019 Spools | 412 Workable | 417 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 15 | 0
Flanges | 423 | 0 | 0
Fittings | 32 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 1245 | 0 | 0

## No Material by Scope
| 1019 Spools | 412 Workable | 417 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 26 | 0
Flanges | 33 | 0 | 0
Fittings | 79 | 0 | 0
Supports | 17 | 0 | 0
TOTAL
Pipe | 1953.2 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 10

## Spools by Scope
| 1019 Spools | 412 Workable | 417 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 28 | 0
Flanges | 290 | 0 | 0
Fittings | 95 | 0 | 0
Pipe | 5 | 0 | 0
Supports | 8 | 0 | 0
Issued |  |  |  | 417
Issued (Missing Items) |  |  |  | 1
Workable (Not Issued) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 175
Discrepancies |  |  |  | 0
TOTAL |  |  |  | 1019

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)
19-1
20-1
46-1
56-1
98-1
99-6
100-1
201-2
201-3
201-4
201-5
201-6
201-7
201-8
201-9
201-10
202-1
202-2
202-3
202-4
202-5
202-6
202-7
210-2
223-1
223-2
223-3
224-1
224-2
224-3
225-1
225-2
225-3
226-1
226-2
226-3
227-1
227-2
227-3
228-1
228-2
228-3
229-1
229-2
229-3
230-1
230-2
230-3
231-1
231-2
231-3
232-1
232-2
232-3
233-1
233-2
233-3
234-1
234-2
234-3
235-1
236-1
236-2
238-1
238-2
308-2
313-1
313-2
313-3
313-4
313-5
314-1
314-2
314-3
319-1
325-1
325-2
326-1
326-2
333-1
335-1
336-1
336-2
337-1
337-2
338-1
339-1
339-2
343-1
343-2
344-1
344-2
345-1
358-1
399-1
401-5
401-6
402-1
402-2
402-3
403-1
403-2
403-3
403-4
403-5
404-1
404-2
404-3
404-4
404-5
405-1
405-2
405-3
405-4
406-1
406-2
406-3
406-4
407-1
407-2
407-3
407-4
407-5