## PRINTOUT
CP CHEM: 7052 |  | 1188 Spools |  | 1081 Workable |  | 1081 Issued
SPOOLS BY SCOPE | [5 empty] | Workable Man Hours (By Material)
SPOOLS | Performance | Client | Other | TOTAL |  |  |  | Carbon | Stainless | TOTAL
Valves | [5 empty] | Workable Man Hours
Flanges
Fittings | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
Pipe | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Supports | [5 empty] | Valves
Issued | [5 empty] | Flanges
Workable (Not Issued) | [5 empty] | Fittings
Issued (Missing Items) | [5 empty] | Supports
On Hold (No Shorts) | [5 empty] | TOTAL
Discrepancies
TOTAL | [5 empty] | Pipe
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Supports | [5 empty] | Supports
TOTAL | [5 empty] | TOTAL
Pipe | [5 empty] | Pipe
Not on Line List | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Purchased
7052 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
Nozzle |  | 153 | 0 | 153 | 0 | 0 | 153 | 0 | 0 | 153 | 100% | 0.0% | 0.0%
J30 | 1 | 9 | 0 | 3 | 6 | 3 | 6 | 3 | 0 | 9 | 33.3% | 33.3% | 0.0%
J14 | 2 | 123 | 2 | 121 | 2 | 77 | 46 | 0 | 51 | 72 | 98.4% | 62.6% | 41.5%
J23 | 3 | 45 | 0 | 44 | 1 | 43 | 2 | 43 | 0 | 45 | 97.8% | 95.6% | 0.0%
J32 | 4 | 255 | 18 | 230 | 25 | 200 | 55 | 105 | 63 | 192 | 90.2% | 78.4% | 24.7%
J06 | 5 | 86 | 10 | 72 | 14 | 69 | 17 | 41 | 22 | 64 | 83.7% | 80.2% | 25.6%
J07 | 5 | 90 | 19 | 68 | 22 | 66 | 24 | 39 | 19 | 71 | 75.6% | 73.3% | 21.1%
J21 | 6 | 42 | 0 | 41 | 1 | 40 | 2 | 28 | 8 | 34 | 97.6% | 95.2% | 19.0%
J20 | 6 | 21 | 1 | 20 | 1 | 21 | 0 | 11 | 0 | 21 | 95.2% | 100% | 0.0%
J04 | 7 | 158 | 9 | 147 | 11 | 143 | 15 | 0 | 86 | 72 | 93.0% | 90.5% | 54.4%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 0 | 2 | 40 | 100% | 100% | 4.8%
J25 | 8 | 39 | 15 | 24 | 15 | 14 | 25 | 1 | 9 | 30 | 61.5% | 35.9% | 23.1%
J10 | 8 | 10 | 1 | 7 | 3 | 5 | 5 | 1 | 0 | 10 | 70.0% | 50.0% | 0.0%
J19 | 9 | 3 | 0 | 3 | 0 | 1 | 2 | 0 | 1 | 2 | 100% | 33.3% | 33.3%
J03 | 10 | 9 | 0 | 9 | 0 | 9 | 0 | 8 | 0 | 9 | 100% | 100% | 0.0%
J13 | 11 | 22 | 0 | 22 | 0 | 21 | 1 | 8 | 3 | 19 | 100% | 95.5% | 13.6%
J18 | 11 | 25 | 0 | 25 | 0 | 25 | 0 | 11 | 3 | 22 | 100% | 100% | 12.0%
J01 | 12 | 53 | 6 | 47 | 6 | 41 | 12 | 28 | 8 | 45 | 88.7% | 77.4% | 15.1%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
TOTALS |  | 1188 | 81 | 1082 | 106 | 823 | 365 | 330 | 275 | 913 | 91% | 69% | 23%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
Nozzle |  | 153 | 0 | 153 | 0 | 0 | 153 | 0 | 0 | 153 | 100% | 0.0% | 0.0%
J30 | 1 | 9 | 0 | 3 | 6 | 3 | 6 | 3 | 0 | 9 | 33.3% | 33.3% | 0.0%
J14 | 2 | 123 | 2 | 121 | 2 | 77 | 46 | 0 | 51 | 72 | 98.4% | 62.6% | 41.5%
J23 | 3 | 45 | 0 | 44 | 1 | 43 | 2 | 43 | 0 | 45 | 97.8% | 95.6% | 0.0%
J32 | 4 | 255 | 18 | 230 | 25 | 200 | 55 | 105 | 63 | 192 | 90.2% | 78.4% | 24.7%
J06 | 5 | 86 | 10 | 72 | 14 | 69 | 17 | 41 | 22 | 64 | 83.7% | 80.2% | 25.6%
J07 | 5 | 90 | 19 | 68 | 22 | 66 | 24 | 39 | 19 | 71 | 75.6% | 73.3% | 21.1%
J21 | 6 | 42 | 0 | 41 | 1 | 40 | 2 | 28 | 8 | 34 | 97.6% | 95.2% | 19.0%
J20 | 6 | 21 | 1 | 20 | 1 | 21 | 0 | 11 | 0 | 21 | 95.2% | 100% | 0.0%
J04 | 7 | 158 | 9 | 147 | 11 | 143 | 15 | 0 | 86 | 72 | 93.0% | 90.5% | 54.4%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 0 | 2 | 40 | 100% | 100% | 4.8%
J25 | 8 | 39 | 15 | 24 | 15 | 14 | 25 | 1 | 9 | 30 | 61.5% | 35.9% | 23.1%
J10 | 8 | 10 | 1 | 7 | 3 | 5 | 5 | 1 | 0 | 10 | 70.0% | 50.0% | 0.0%
J19 | 9 | 3 | 0 | 3 | 0 | 1 | 2 | 0 | 1 | 2 | 100% | 33.3% | 33.3%
J03 | 10 | 9 | 0 | 9 | 0 | 9 | 0 | 8 | 0 | 9 | 100% | 100% | 0.0%
J13 | 11 | 22 | 0 | 22 | 0 | 21 | 1 | 8 | 3 | 19 | 100% | 95.5% | 13.6%
J18 | 11 | 25 | 0 | 25 | 0 | 25 | 0 | 11 | 3 | 22 | 100% | 100% | 12.0%
J01 | 12 | 53 | 6 | 47 | 6 | 41 | 12 | 28 | 8 | 45 | 88.7% | 77.4% | 15.1%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
TOTALS |  | 1188 | 81 | 1081 | 107 | 823 | 365 | 330 | 275 | 913 | 91% | 69% | 23%

## Areas Summary (By Material)
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J04 | 7 | 154 | 9 | 143 | 11 | 142 | 12 | 0 | 86 | 68 | 92.9% | 92.2% | 55.8%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 0 | 2 | 40 | 100% | 100% | 4.8%
J18 | 11 | 13 | 0 | 13 | 0 | 13 | 0 | 0 | 3 | 10 | 100% | 100% | 23.1%
J13 | 11 | 12 | 0 | 12 | 0 | 11 | 1 | 0 | 2 | 10 | 100% | 91.7% | 16.7%
J32 | 4 | 38 | 0 | 38 | 0 | 33 | 5 | 0 | 27 | 11 | 100% | 86.8% | 71.1%
Nozzle |  | 31 | 0 | 31 | 0 | 0 | 31 | 0 | 0 | 31 | 100% | 0.0% | 0.0%
TOTALS |  | 290 | 9 | 279 | 11 | 241 | 49 | 0 | 120 | 170 | 96% | 83% | 41%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J13 | 11 | 10 | 0 | 10 | 0 | 10 | 0 | 8 | 1 | 9 | 100% | 100% | 10.0%
J18 | 11 | 12 | 0 | 12 | 0 | 12 | 0 | 11 | 0 | 12 | 100% | 100% | 0.0%
J01 | 12 | 28 | 0 | 28 | 0 | 28 | 0 | 26 | 0 | 28 | 100% | 100% | 0.0%
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J03 | 10 | 9 | 0 | 9 | 0 | 9 | 0 | 8 | 0 | 9 | 100% | 100% | 0.0%
J23 | 3 | 45 | 0 | 44 | 1 | 43 | 2 | 43 | 0 | 45 | 97.8% | 95.6% | 0.0%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J32 | 4 | 217 | 18 | 192 | 25 | 167 | 50 | 105 | 36 | 181 | 88.5% | 77.0% | 16.6%
J07 | 5 | 61 | 19 | 42 | 19 | 40 | 21 | 22 | 2 | 59 | 68.9% | 65.6% | 3.3%
J06 | 5 | 57 | 10 | 46 | 11 | 43 | 14 | 20 | 1 | 56 | 80.7% | 75.4% | 1.8%
J21 | 6 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 100% | 100% | 0.0%
J20 | 6 | 11 | 1 | 10 | 1 | 11 | 0 | 4 | 0 | 11 | 90.9% | 100% | 0.0%
J04 | 7 | 4 | 0 | 4 | 0 | 1 | 3 | 0 | 0 | 4 | 100% | 25.0% | 0.0%
J10 | 8 | 10 | 1 | 7 | 3 | 5 | 5 | 1 | 0 | 10 | 70.0% | 50.0% | 0.0%
J25 | 8 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 4 | 50.0% | 50.0% | 0.0%
TOTALS |  | 494 | 51 | 432 | 62 | 397 | 97 | 275 | 40 | 454 | 87% | 80% | 8%
A333 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 4 | 0 | 4 | 0 | 2 | 0 | 4 | 100% | 100% | 0.0%
J20 | 6 | 10 | 0 | 10 | 0 | 10 | 0 | 7 | 0 | 10 | 100% | 100% | 0.0%
J21 | 6 | 12 | 0 | 11 | 1 | 11 | 1 | 8 | 0 | 12 | 91.7% | 91.7% | 0.0%
TOTALS |  | 26 | 0 | 25 | 1 | 25 | 1 | 17 | 0 | 26 | 96% | 96% | 0%
ALUMINUM Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 122 | 2 | 120 | 2 | 77 | 45 | 0 | 51 | 71 | 98.4% | 63.1% | 41.8%
J01 | 12 | 17 | 6 | 11 | 6 | 6 | 11 | 0 | 6 | 11 | 64.7% | 35.3% | 35.3%
J19 | 9 | 3 | 0 | 3 | 0 | 1 | 2 | 0 | 1 | 2 | 100% | 33.3% | 33.3%
J25 | 8 | 35 | 13 | 22 | 13 | 12 | 23 | 0 | 9 | 26 | 62.9% | 34.3% | 25.7%
Nozzle |  | 122 | 0 | 122 | 0 | 0 | 122 | 0 | 0 | 122 | 100% | 0.0% | 0.0%
TOTALS |  | 299 | 21 | 278 | 21 | 96 | 203 | 0 | 67 | 232 | 93% | 32% | 22%
304/304L SS CRYO Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 4 | 0 | 3 | 1 | 0 | 2 | 2 | 100% | 75.0% | 50.0%
J21 | 6 | 10 | 0 | 10 | 0 | 9 | 1 | 0 | 8 | 2 | 100% | 90.0% | 80.0%
TOTALS |  | 14 | 0 | 14 | 0 | 12 | 2 | 0 | 10 | 4 | 100% | 86% | 71%
Galv. Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J06 | 5 | 29 | 0 | 26 | 3 | 26 | 3 | 21 | 21 | 8 | 89.7% | 89.7% | 72.4%
J07 | 5 | 29 | 0 | 26 | 3 | 26 | 3 | 17 | 17 | 12 | 89.7% | 89.7% | 58.6%
TOTALS |  | 58 | 0 | 52 | 6 | 52 | 6 | 38 | 38 | 20 | 90% | 90% | 66%
A105 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 100% | 0.0% | 0.0%
TOTALS |  | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 100% | 0% | 0%
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 0% | 0.0% | 0.0%
TOTALS |  | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 0% | 0% | 0%

## Spool Location
Not Workable | 26
Workable | 1
Issued | 143
Pulled | 115
Welded Out | 198
Shipped to Coating | 274
Ready To Deliver | 20
Delivered | 275
On Hold | 81

## Shorts by Scope
| 1188 Spools | 1081 Workable | 1081 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 9 | 0
Flanges | 4 | 0 | 0
Fittings | 46 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 112.3 | 0 | 0
Not on Line List

## Purchased by Scope
| 1188 Spools | 1081 Workable | 1081 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 31 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 57.1 | 0 | 0

## No Material by Scope
| 1188 Spools | 1081 Workable | 1081 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 9 | 0
Flanges | 4 | 0 | 0
Fittings | 15 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 55.2 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 8

## Spools by Scope
| 1188 Spools | 1081 Workable | 1081 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 9 | 0
Flanges | 31 | 0 | 0
Fittings | 2 | 0 | 0
Pipe | 10 | 0 | 0
Supports | 0 | 0 | 0
Issued |  |  |  | 1081
Workable (Not Issued) |  |  |  | 1
Issued (Missing Items) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 54
Discrepancies |  |  |  | 0
TOTAL |  |  |  | 1188

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)