## PRINTOUT
CP CHEM: 7052 |  | 1498 Spools |  | 0 Workable |  | 1162 Issued
SPOOLS BY SCOPE | [5 empty] | Workable Man Hours (By Material)
SPOOLS | Performance | Client | Other | TOTAL |  |  |  | Carbon | Stainless | TOTAL
Valves | [5 empty] | Workable Man Hours
Flanges
Fittings | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
Pipe | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Supports | [5 empty] | Valves
Issued | [5 empty] | Flanges
Workable (Not Issued) | [5 empty] | Fittings
Issued (Missing Items) | [5 empty] | Supports
On Hold (No Shorts) | [5 empty] | TOTAL
Discrepancies
TOTAL | [5 empty] | Pipe
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Supports | [5 empty] | Supports
TOTAL | [5 empty] | TOTAL
Pipe | [5 empty] | Pipe
Not on Line List | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Purchased
7052 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
Nozzle |  | 153 | 0 | 0 | 153 | 152 | 1 | 0 | 120 | 33 | 0% | 99.3% | 78.4%
VALVES |  | 14 | 0 | 0 | 14 | 14 | 0 | 14 | 0 | 14 | 0% | 100% | 0.0%
J08 |  | 19 | 0 | 0 | 19 | 0 | 19 | 0 | 0 | 19 | 0% | 0.0% | 0.0%
J16 |  | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J17 |  | 71 | 0 | 0 | 71 | 0 | 71 | 0 | 0 | 71 | 0% | 0.0% | 0.0%
J12 |  | 76 | 0 | 0 | 76 | 0 | 76 | 0 | 0 | 76 | 0% | 0.0% | 0.0%
J30 | 1 | 9 | 0 | 0 | 9 | 3 | 6 | 3 | 3 | 6 | 0% | 33.3% | 33.3%
J14 | 2 | 123 | 0 | 0 | 123 | 121 | 2 | 0 | 121 | 2 | 0% | 98.4% | 98.4%
J23 | 3 | 45 | 0 | 0 | 45 | 45 | 0 | 44 | 43 | 2 | 0% | 100% | 95.6%
J07 | 5 | 150 | 5 | 0 | 150 | 83 | 67 | 56 | 64 | 86 | 0% | 55.3% | 42.7%
J04 | 7 | 158 | 0 | 0 | 158 | 151 | 7 | 14 | 140 | 18 | 0% | 95.6% | 88.6%
- | #N/A | 3 | 0 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 0% | 100% | 100%
J09 |  | 13 | 0 | 0 | 13 | 0 | 13 | 0 | 0 | 13 | 0% | 0.0% | 0.0%
J32 | 4 | 237 | 0 | 0 | 237 | 226 | 11 | 131 | 180 | 57 | 0% | 95.4% | 75.9%
J06 | 5 | 151 | 5 | 0 | 151 | 80 | 71 | 65 | 62 | 89 | 0% | 53.0% | 41.1%
J21 | 6 | 42 | 0 | 0 | 42 | 41 | 1 | 31 | 41 | 1 | 0% | 97.6% | 97.6%
J20 | 6 | 21 | 1 | 0 | 21 | 21 | 0 | 21 | 21 | 0 | 0% | 100% | 100%
J05 | 7 | 42 | 0 | 0 | 42 | 42 | 0 | 40 | 42 | 0 | 0% | 100% | 100%
J25 | 8 | 39 | 2 | 0 | 39 | 26 | 13 | 1 | 18 | 21 | 0% | 66.7% | 46.2%
J10 | 8 | 10 | 1 | 0 | 10 | 6 | 4 | 5 | 5 | 5 | 0% | 60.0% | 50.0%
J19 | 9 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 2 | 0% | 100% | 33.3%
J03 | 10 | 9 | 0 | 0 | 9 | 9 | 0 | 9 | 9 | 0 | 0% | 100% | 100%
J18 | 11 | 25 | 0 | 0 | 25 | 25 | 0 | 12 | 25 | 0 | 0% | 100% | 100%
J13 | 11 | 22 | 0 | 0 | 22 | 22 | 0 | 10 | 22 | 0 | 0% | 100% | 100%
J01 | 12 | 53 | 0 | 0 | 53 | 47 | 6 | 32 | 45 | 8 | 0% | 88.7% | 84.9%
TOTALS |  | 1498 | 14 | 0 | 1498 | 1120 | 378 | 491 | 965 | 533 | 0% | 75% | 64%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
Nozzle |  | 153 | 0 | 0 | 153 | 152 | 1 | 0 | 120 | 33 | 0% | 99.3% | 78.4%
VALVES |  | 14 | 0 | 0 | 14 | 14 | 0 | 14 | 0 | 14 | 0% | 100% | 0.0%
J08 |  | 19 | 0 | 0 | 19 | 0 | 19 | 0 | 0 | 19 | 0% | 0.0% | 0.0%
J16 |  | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J17 |  | 71 | 0 | 0 | 71 | 0 | 71 | 0 | 0 | 71 | 0% | 0.0% | 0.0%
J12 |  | 76 | 0 | 0 | 76 | 0 | 76 | 0 | 0 | 76 | 0% | 0.0% | 0.0%
J30 | 1 | 9 | 0 | 0 | 9 | 3 | 6 | 3 | 3 | 6 | 0% | 33.3% | 33.3%
J14 | 2 | 123 | 0 | 0 | 123 | 121 | 2 | 0 | 121 | 2 | 0% | 98.4% | 98.4%
J23 | 3 | 45 | 0 | 0 | 45 | 45 | 0 | 44 | 43 | 2 | 0% | 100% | 95.6%
J07 | 5 | 150 | 5 | 0 | 150 | 83 | 67 | 56 | 64 | 86 | 0% | 55.3% | 42.7%
J04 | 7 | 158 | 0 | 0 | 158 | 151 | 7 | 14 | 140 | 18 | 0% | 95.6% | 88.6%
- | #N/A | 3 | 0 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 0% | 100% | 100%
J09 |  | 13 | 0 | 0 | 13 | 0 | 13 | 0 | 0 | 13 | 0% | 0.0% | 0.0%
J32 | 4 | 237 | 0 | 0 | 237 | 226 | 11 | 131 | 180 | 57 | 0% | 95.4% | 75.9%
J06 | 5 | 151 | 5 | 0 | 151 | 80 | 71 | 65 | 62 | 89 | 0% | 53.0% | 41.1%
J21 | 6 | 42 | 0 | 0 | 42 | 41 | 1 | 31 | 41 | 1 | 0% | 97.6% | 97.6%
J20 | 6 | 21 | 1 | 0 | 21 | 21 | 0 | 21 | 21 | 0 | 0% | 100% | 100%
J05 | 7 | 42 | 0 | 0 | 42 | 42 | 0 | 40 | 42 | 0 | 0% | 100% | 100%
J25 | 8 | 39 | 2 | 0 | 39 | 26 | 13 | 1 | 18 | 21 | 0% | 66.7% | 46.2%
J10 | 8 | 10 | 1 | 0 | 10 | 6 | 4 | 5 | 5 | 5 | 0% | 60.0% | 50.0%
J19 | 9 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 2 | 0% | 100% | 33.3%
J03 | 10 | 9 | 0 | 0 | 9 | 9 | 0 | 9 | 9 | 0 | 0% | 100% | 100%
J18 | 11 | 25 | 0 | 0 | 25 | 25 | 0 | 12 | 25 | 0 | 0% | 100% | 100%
J13 | 11 | 22 | 0 | 0 | 22 | 22 | 0 | 10 | 22 | 0 | 0% | 100% | 100%
J01 | 12 | 53 | 0 | 0 | 53 | 47 | 6 | 32 | 45 | 8 | 0% | 88.7% | 84.9%
TOTALS |  | 1498 | 14 | 0 | 1498 | 1120 | 378 | 491 | 965 | 533 | 0% | 75% | 64%

## Areas Summary (By Material)
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J04 | 7 | 154 | 0 | 0 | 154 | 147 | 7 | 12 | 140 | 14 | 0% | 95.5% | 90.9%
J05 | 7 | 42 | 0 | 0 | 42 | 42 | 0 | 40 | 42 | 0 | 0% | 100% | 100%
J32 | 4 | 38 | 0 | 0 | 38 | 38 | 0 | 0 | 37 | 1 | 0% | 100% | 97.4%
J18 | 11 | 13 | 0 | 0 | 13 | 13 | 0 | 0 | 13 | 0 | 0% | 100% | 100%
Nozzle |  | 31 | 0 | 0 | 31 | 31 | 0 | 0 | 8 | 23 | 0% | 100% | 25.8%
J13 | 11 | 12 | 0 | 0 | 12 | 12 | 0 | 0 | 12 | 0 | 0% | 100% | 100%
J17 |  | 7 | 0 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
J12 |  | 7 | 0 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
TOTALS |  | 304 | 0 | 0 | 304 | 283 | 21 | 52 | 252 | 52 | 0% | 93% | 83%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J23 | 3 | 45 | 0 | 0 | 45 | 45 | 0 | 44 | 43 | 2 | 0% | 100% | 95.6%
J30 | 1 | 3 | 0 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 0% | 100% | 100%
- | #N/A | 3 | 0 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 0% | 100% | 100%
J18 | 11 | 12 | 0 | 0 | 12 | 12 | 0 | 12 | 12 | 0 | 0% | 100% | 100%
J13 | 11 | 10 | 0 | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 0% | 100% | 100%
J01 | 12 | 28 | 0 | 0 | 28 | 28 | 0 | 28 | 27 | 1 | 0% | 100% | 96.4%
J32 | 4 | 199 | 0 | 0 | 199 | 188 | 11 | 131 | 143 | 56 | 0% | 94.5% | 71.9%
J07 | 5 | 121 | 5 | 0 | 121 | 54 | 67 | 39 | 38 | 83 | 0% | 44.6% | 31.4%
J06 | 5 | 122 | 5 | 0 | 122 | 51 | 71 | 44 | 40 | 82 | 0% | 41.8% | 32.8%
J21 | 6 | 20 | 0 | 0 | 20 | 20 | 0 | 20 | 20 | 0 | 0% | 100% | 100%
J20 | 6 | 11 | 1 | 0 | 11 | 11 | 0 | 11 | 11 | 0 | 0% | 100% | 100%
J04 | 7 | 4 | 0 | 0 | 4 | 4 | 0 | 2 | 0 | 4 | 0% | 100% | 0.0%
J10 | 8 | 10 | 1 | 0 | 10 | 6 | 4 | 5 | 5 | 5 | 0% | 60.0% | 50.0%
J25 | 8 | 4 | 2 | 0 | 4 | 2 | 2 | 1 | 1 | 3 | 0% | 50.0% | 25.0%
J17 |  | 64 | 0 | 0 | 64 | 0 | 64 | 0 | 0 | 64 | 0% | 0.0% | 0.0%
J12 |  | 69 | 0 | 0 | 69 | 0 | 69 | 0 | 0 | 69 | 0% | 0.0% | 0.0%
J09 |  | 13 | 0 | 0 | 13 | 0 | 13 | 0 | 0 | 13 | 0% | 0.0% | 0.0%
J08 |  | 15 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 15 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 0 | 0 | 9 | 9 | 0 | 9 | 9 | 0 | 0% | 100% | 100%
TOTALS |  | 762 | 14 | 0 | 762 | 446 | 316 | 362 | 365 | 397 | 0% | 59% | 48%
ALUMINUM Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J19 | 9 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 2 | 0% | 100% | 33.3%
J14 | 2 | 122 | 0 | 0 | 122 | 120 | 2 | 0 | 120 | 2 | 0% | 98.4% | 98.4%
J01 | 12 | 17 | 0 | 0 | 17 | 11 | 6 | 0 | 10 | 7 | 0% | 64.7% | 58.8%
J25 | 8 | 35 | 0 | 0 | 35 | 24 | 11 | 0 | 17 | 18 | 0% | 68.6% | 48.6%
Nozzle |  | 122 | 0 | 0 | 122 | 121 | 1 | 0 | 112 | 10 | 0% | 99.2% | 91.8%
TOTALS |  | 299 | 0 | 0 | 299 | 279 | 20 | 0 | 260 | 39 | 0% | 93% | 87%
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0% | 100% | 100%
J30 | 1 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 0% | 0.0% | 0.0%
VALVES |  | 14 | 0 | 0 | 14 | 14 | 0 | 14 | 0 | 14 | 0% | 100% | 0.0%
TOTALS |  | 21 | 0 | 0 | 21 | 15 | 6 | 14 | 1 | 20 | 0% | 71% | 5%
304/304L SS CRYO Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 0 | 0% | 100% | 100%
J21 | 6 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 0 | 0% | 100% | 100%
TOTALS |  | 14 | 0 | 0 | 14 | 14 | 0 | 0 | 14 | 0 | 0% | 100% | 100%
Galv. Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J06 | 5 | 29 | 0 | 0 | 29 | 29 | 0 | 21 | 22 | 7 | 0% | 100% | 75.9%
J07 | 5 | 29 | 0 | 0 | 29 | 29 | 0 | 17 | 26 | 3 | 0% | 100% | 89.7%
TOTALS |  | 58 | 0 | 0 | 58 | 58 | 0 | 38 | 48 | 10 | 0% | 100% | 83%
A333 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J20 | 6 | 10 | 0 | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 0% | 100% | 100%
J21 | 6 | 12 | 0 | 0 | 12 | 11 | 1 | 11 | 11 | 1 | 0% | 91.7% | 91.7%
J08 |  | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
J16 |  | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J01 | 12 | 4 | 0 | 0 | 4 | 4 | 0 | 4 | 4 | 0 | 0% | 100% | 100%
TOTALS |  | 40 | 0 | 0 | 40 | 25 | 15 | 25 | 25 | 15 | 0% | 62% | 62%

## Spool Location
Not Workable | 1484
Workable | 0
Issued | 0
Pulled | 0
Welded Out | 0
Shipped to Coating | 0
Ready To Deliver | 0
Delivered | 0
On Hold | 14

## Shorts by Scope
| 1498 Spools | 0 Workable | 1162 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0
Not on Line List

## Purchased by Scope
| 1498 Spools | 0 Workable | 1162 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0

## No Material by Scope
| 1498 Spools | 0 Workable | 1162 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 0

## Spools by Scope
| 1498 Spools | 0 Workable | 1162 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Pipe | 0 | 0 | 0
Supports | 0 | 0 | 0
Issued |  |  |  | 1162
Workable (Not Issued) |  |  |  | 0
Issued (Missing Items) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 13
Discrepancies |  |  |  | 21
TOTAL |  |  |  | 1498

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)
PK101XA-FW-100430.01-1
PK101XA-FW-102003.01-1
PK101XA-FW-102004.01-1
PK101XA-FW-102331.01-1
PK101XA-FW-102333.01-1
PK101XA-FW-102336.01-1
7052-CCW-VALVE-564-1
7052-CCW-VALVE-565-1
7052-CCW-VALVE-568-1
7052-CCW-VALVE-573-1
7052-CCW-VALVE-574-1
7052-CCW-VALVE-575-1
7052-CCW-VALVE-576-1
7052-CS-VALVE-569-1
7052-CS-VALVE-570-1
7052-CW-VALVE-566-1
7052-CW-VALVE-567-1
7052-GN-VALVE-563-1
7052-GN-VALVE-571-1
7052-GN-VALVE-572-1
PM110XA-CS-99999.09-4