## PRINTOUT
CP CHEM: 7052 |  | 1019 Spools |  |  | 437 Workable |  |  | 417 Issued
SPOOLS BY SCOPE | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
SPOOLS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Pipe | [5 empty] | Supports
Supports | [5 empty] | TOTAL
Issued
Issued (Missing Items) | [5 empty] | Pipe
Workable (Not Issued)
On Hold (No Shorts)
Discrepancies | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
TOTAL | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Valves
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | Flanges
ITEMS | Performance | Client | Other | TOTAL |  | Fittings
Valves | [5 empty] | Supports
Flanges | [5 empty] | TOTAL
Fittings
Supports | [5 empty] | Pipe
TOTAL
Pipe | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Not on Line List | [5 empty] | Purchased
7052 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J14 | 2 | 123 | 3 | 0 | 123 | 0 | 123 | 0 | 0 | 123 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 11 | 33 | 12 | 33 | 12 | 27 | 0 | 45 | 73.3% | 73.3% | 0.0%
J32 | 4 | 242 | 121 | 121 | 121 | 35 | 207 | 2 | 0 | 242 | 50.0% | 14.5% | 0.0%
J06 | 5 | 83 | 64 | 19 | 64 | 11 | 72 | 3 | 0 | 83 | 22.9% | 13.3% | 0.0%
J07 | 5 | 94 | 75 | 19 | 75 | 13 | 81 | 3 | 0 | 94 | 20.2% | 13.8% | 0.0%
J21 | 6 | 42 | 1 | 33 | 9 | 24 | 18 | 7 | 0 | 42 | 78.6% | 57.1% | 0.0%
J20 | 6 | 21 | 4 | 11 | 10 | 10 | 11 | 2 | 0 | 21 | 52.4% | 47.6% | 0.0%
J04 | 7 | 156 | 40 | 104 | 52 | 17 | 139 | 0 | 0 | 156 | 66.7% | 10.9% | 0.0%
J05 | 7 | 42 | 4 | 25 | 17 | 2 | 40 | 0 | 0 | 42 | 59.5% | 4.8% | 0.0%
J25 | 8 | 39 | 24 | 2 | 37 | 0 | 39 | 0 | 0 | 39 | 5.1% | 0.0% | 0.0%
J10 | 8 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 2 | 7 | 2 | 2 | 7 | 1 | 0 | 9 | 77.8% | 22.2% | 0.0%
J13 | 11 | 22 | 6 | 16 | 6 | 12 | 10 | 0 | 0 | 22 | 72.7% | 54.5% | 0.0%
J18 | 11 | 25 | 4 | 21 | 4 | 16 | 9 | 3 | 0 | 25 | 84.0% | 64.0% | 0.0%
J01 | 12 | 53 | 9 | 23 | 30 | 11 | 42 | 6 | 0 | 53 | 43.4% | 20.8% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
TOTALS |  | 1019 | 385 | 470 | 549 | 189 | 830 | 57 | 0 | 1019 | 43% | 19% | 0%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J14 | 2 | 123 | 3 | 0 | 123 | 0 | 123 | 0 | 0 | 123 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 11 | 33 | 12 | 33 | 12 | 27 | 0 | 45 | 73.3% | 73.3% | 0.0%
J32 | 4 | 242 | 121 | 121 | 121 | 35 | 207 | 2 | 0 | 242 | 50.0% | 14.5% | 0.0%
J06 | 5 | 83 | 64 | 19 | 64 | 11 | 72 | 3 | 0 | 83 | 22.9% | 13.3% | 0.0%
J07 | 5 | 94 | 75 | 19 | 75 | 13 | 81 | 3 | 0 | 94 | 20.2% | 13.8% | 0.0%
J21 | 6 | 42 | 1 | 33 | 9 | 24 | 18 | 7 | 0 | 42 | 78.6% | 57.1% | 0.0%
J20 | 6 | 21 | 4 | 11 | 10 | 10 | 11 | 2 | 0 | 21 | 52.4% | 47.6% | 0.0%
J04 | 7 | 156 | 40 | 104 | 52 | 17 | 139 | 0 | 0 | 156 | 66.7% | 10.9% | 0.0%
J05 | 7 | 42 | 4 | 25 | 17 | 2 | 40 | 0 | 0 | 42 | 59.5% | 4.8% | 0.0%
J25 | 8 | 39 | 24 | 2 | 37 | 0 | 39 | 0 | 0 | 39 | 5.1% | 0.0% | 0.0%
J10 | 8 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 2 | 7 | 2 | 2 | 7 | 1 | 0 | 9 | 77.8% | 22.2% | 0.0%
J13 | 11 | 22 | 6 | 16 | 6 | 12 | 10 | 0 | 0 | 22 | 72.7% | 54.5% | 0.0%
J18 | 11 | 25 | 4 | 21 | 4 | 16 | 9 | 3 | 0 | 25 | 84.0% | 64.0% | 0.0%
J01 | 12 | 53 | 9 | 23 | 30 | 11 | 42 | 6 | 0 | 53 | 43.4% | 20.8% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
TOTALS |  | 1019 | 385 | 437 | 582 | 189 | 830 | 57 | 0 | 1019 | 43% | 19% | 0%

## Areas Summary (By Material)
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J04 | 7 | 152 | 36 | 104 | 48 | 17 | 135 | 0 | 0 | 152 | 68.4% | 11.2% | 0.0%
J05 | 7 | 42 | 4 | 25 | 17 | 2 | 40 | 0 | 0 | 42 | 59.5% | 4.8% | 0.0%
J18 | 11 | 13 | 2 | 11 | 2 | 9 | 4 | 0 | 0 | 13 | 84.6% | 69.2% | 0.0%
J13 | 11 | 12 | 4 | 8 | 4 | 6 | 6 | 0 | 0 | 12 | 66.7% | 50.0% | 0.0%
J32 | 4 | 38 | 6 | 32 | 6 | 4 | 34 | 0 | 0 | 38 | 84.2% | 10.5% | 0.0%
TOTALS |  | 257 | 52 | 180 | 77 | 38 | 219 | 0 | 0 | 257 | 70% | 15% | 0%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J13 | 11 | 10 | 2 | 8 | 2 | 6 | 4 | 0 | 0 | 10 | 80.0% | 60.0% | 0.0%
J18 | 11 | 12 | 2 | 10 | 2 | 7 | 5 | 3 | 0 | 12 | 83.3% | 58.3% | 0.0%
J01 | 12 | 28 | 3 | 19 | 9 | 9 | 19 | 4 | 0 | 28 | 67.9% | 32.1% | 0.0%
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J03 | 10 | 9 | 2 | 7 | 2 | 2 | 7 | 1 | 0 | 9 | 77.8% | 22.2% | 0.0%
J23 | 3 | 45 | 11 | 33 | 12 | 33 | 12 | 27 | 0 | 45 | 73.3% | 73.3% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
J32 | 4 | 204 | 115 | 89 | 115 | 31 | 173 | 2 | 0 | 204 | 43.6% | 15.2% | 0.0%
J06 | 5 | 73 | 54 | 19 | 54 | 11 | 62 | 3 | 0 | 73 | 26.0% | 15.1% | 0.0%
J07 | 5 | 66 | 47 | 19 | 47 | 13 | 53 | 3 | 0 | 66 | 28.8% | 19.7% | 0.0%
J21 | 6 | 20 | 0 | 16 | 4 | 16 | 4 | 7 | 0 | 20 | 80.0% | 80.0% | 0.0%
J20 | 6 | 11 | 4 | 3 | 8 | 2 | 9 | 1 | 0 | 11 | 27.3% | 18.2% | 0.0%
J04 | 7 | 4 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
J10 | 8 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J25 | 8 | 4 | 2 | 2 | 2 | 0 | 4 | 0 | 0 | 4 | 50.0% | 0.0% | 0.0%
TOTALS |  | 506 | 263 | 228 | 278 | 133 | 373 | 54 | 0 | 506 | 45% | 26% | 0%
A333 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 4 | 50.0% | 50.0% | 0.0%
J20 | 6 | 10 | 0 | 8 | 2 | 8 | 2 | 1 | 0 | 10 | 80.0% | 80.0% | 0.0%
J21 | 6 | 12 | 1 | 8 | 4 | 8 | 4 | 0 | 0 | 12 | 66.7% | 66.7% | 0.0%
TOTALS |  | 26 | 1 | 18 | 8 | 18 | 8 | 3 | 0 | 26 | 69% | 69% | 0%
ALUMINUM Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 122 | 2 | 0 | 122 | 0 | 122 | 0 | 0 | 122 | 0% | 0.0% | 0.0%
J01 | 12 | 17 | 6 | 0 | 17 | 0 | 17 | 0 | 0 | 17 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J25 | 8 | 35 | 22 | 0 | 35 | 0 | 35 | 0 | 0 | 35 | 0% | 0.0% | 0.0%
TOTALS |  | 177 | 30 | 0 | 177 | 0 | 177 | 0 | 0 | 177 | 0% | 0% | 0%
304/304L SS CRYO Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 2 | 2 | 0 | 4 | 0 | 0 | 4 | 50.0% | 0.0% | 0.0%
J21 | 6 | 10 | 0 | 9 | 1 | 0 | 10 | 0 | 0 | 10 | 90.0% | 0.0% | 0.0%
TOTALS |  | 14 | 0 | 11 | 3 | 0 | 14 | 0 | 0 | 14 | 79% | 0% | 0%
Galv. Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J06 | 5 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J07 | 5 | 28 | 28 | 0 | 28 | 0 | 28 | 0 | 0 | 28 | 0% | 0.0% | 0.0%
TOTALS |  | 38 | 38 | 0 | 38 | 0 | 38 | 0 | 0 | 38 | 0% | 0% | 0%
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0% | 0.0% | 0.0%
TOTALS |  | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0% | 0% | 0%

## Spool Location
Not Workable | 197
Workable | 33
Issued | 109
Pulled | 119
Welded Out | 132
Shipped to Coating | 57
Ready To Deliver | 0
Delivered | 0
On Hold | 372

## Shorts by Scope
| 1019 Spools | 437 Workable | 417 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 41 | 0
Flanges | 347 | 0 | 0
Fittings | 46 | 0 | 0
Supports | 17 | 0 | 0
TOTAL
Pipe | 3310.2 | 0 | 0
Not on Line List

## Purchased by Scope
| 1019 Spools | 437 Workable | 417 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 15 | 0
Flanges | 337 | 0 | 0
Fittings | 28 | 0 | 0
Supports | 17 | 0 | 0
TOTAL
Pipe | 1357 | 0 | 0

## No Material by Scope
| 1019 Spools | 437 Workable | 417 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 26 | 0
Flanges | 10 | 0 | 0
Fittings | 18 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 1953.2 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 11

## Spools by Scope
| 1019 Spools | 437 Workable | 417 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 28 | 0
Flanges | 290 | 0 | 0
Fittings | 40 | 0 | 0
Pipe | 21 | 0 | 0
Supports | 12 | 0 | 0
Issued |  |  |  | 417
Issued (Missing Items) |  |  |  | 33
Workable (Not Issued) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 178
Discrepancies |  |  |  | 0
TOTAL |  |  |  | 1019

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)