## PRINTOUT
CP CHEM: 7052 |  | 1019 Spools |  |  | 185 Workable |  |  | 187 Issued
SPOOLS BY SCOPE | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
SPOOLS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Pipe | [5 empty] | Supports
Supports | [5 empty] | TOTAL
Issued
Issued (Missing Items) | [5 empty] | Pipe
Workable (Not Issued)
On Hold (No Shorts)
Discrepancies | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
TOTAL | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Valves
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | Flanges
ITEMS | Performance | Client | Other | TOTAL |  | Fittings
Valves | [5 empty] | Supports
Flanges | [5 empty] | TOTAL
Fittings
Supports | [5 empty] | Pipe
TOTAL
Pipe | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Not on Line List | [5 empty] | Purchased
7052 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 100% | 0.0% | 0.0%
J14 | 2 | 123 | 0 | 0 | 123 | 0 | 123 | 0 | 0 | 123 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 5 | 32 | 13 | 0 | 45 | 0 | 0 | 45 | 71.1% | 0.0% | 0.0%
J32 | 4 | 242 | 97 | 57 | 185 | 3 | 239 | 0 | 0 | 242 | 23.6% | 1.2% | 0.0%
J06 | 5 | 83 | 45 | 20 | 63 | 0 | 83 | 0 | 0 | 83 | 24.1% | 0.0% | 0.0%
J07 | 5 | 94 | 61 | 15 | 79 | 0 | 94 | 0 | 0 | 94 | 16.0% | 0.0% | 0.0%
J21 | 6 | 42 | 7 | 15 | 27 | 2 | 40 | 0 | 0 | 42 | 35.7% | 4.8% | 0.0%
J20 | 6 | 21 | 3 | 2 | 19 | 0 | 21 | 0 | 0 | 21 | 9.5% | 0.0% | 0.0%
J04 | 7 | 156 | 40 | 13 | 143 | 10 | 146 | 0 | 0 | 156 | 8.3% | 6.4% | 0.0%
J05 | 7 | 42 | 4 | 1 | 41 | 1 | 41 | 0 | 0 | 42 | 2.4% | 2.4% | 0.0%
J25 | 8 | 39 | 13 | 0 | 39 | 0 | 39 | 0 | 0 | 39 | 0% | 0.0% | 0.0%
J10 | 8 | 10 | 4 | 1 | 9 | 0 | 10 | 0 | 0 | 10 | 10.0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 0 | 1 | 8 | 0 | 9 | 0 | 0 | 9 | 11.1% | 0.0% | 0.0%
J13 | 11 | 22 | 4 | 5 | 17 | 2 | 20 | 0 | 0 | 22 | 22.7% | 9.1% | 0.0%
J18 | 11 | 25 | 2 | 11 | 14 | 2 | 23 | 0 | 0 | 25 | 44.0% | 8.0% | 0.0%
J01 | 12 | 53 | 0 | 9 | 44 | 4 | 49 | 0 | 0 | 53 | 17.0% | 7.5% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
TOTALS |  | 1019 | 292 | 185 | 834 | 24 | 995 | 0 | 0 | 1019 | 18% | 2% | 0%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 100% | 0.0% | 0.0%
J14 | 2 | 123 | 0 | 0 | 123 | 0 | 123 | 0 | 0 | 123 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 5 | 32 | 13 | 0 | 45 | 0 | 0 | 45 | 71.1% | 0.0% | 0.0%
J32 | 4 | 242 | 97 | 57 | 185 | 3 | 239 | 0 | 0 | 242 | 23.6% | 1.2% | 0.0%
J06 | 5 | 83 | 45 | 20 | 63 | 0 | 83 | 0 | 0 | 83 | 24.1% | 0.0% | 0.0%
J07 | 5 | 94 | 61 | 15 | 79 | 0 | 94 | 0 | 0 | 94 | 16.0% | 0.0% | 0.0%
J21 | 6 | 42 | 7 | 15 | 27 | 2 | 40 | 0 | 0 | 42 | 35.7% | 4.8% | 0.0%
J20 | 6 | 21 | 3 | 2 | 19 | 0 | 21 | 0 | 0 | 21 | 9.5% | 0.0% | 0.0%
J04 | 7 | 156 | 40 | 13 | 143 | 10 | 146 | 0 | 0 | 156 | 8.3% | 6.4% | 0.0%
J05 | 7 | 42 | 4 | 1 | 41 | 1 | 41 | 0 | 0 | 42 | 2.4% | 2.4% | 0.0%
J25 | 8 | 39 | 13 | 0 | 39 | 0 | 39 | 0 | 0 | 39 | 0% | 0.0% | 0.0%
J10 | 8 | 10 | 4 | 1 | 9 | 0 | 10 | 0 | 0 | 10 | 10.0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 0 | 1 | 8 | 0 | 9 | 0 | 0 | 9 | 11.1% | 0.0% | 0.0%
J13 | 11 | 22 | 4 | 5 | 17 | 2 | 20 | 0 | 0 | 22 | 22.7% | 9.1% | 0.0%
J18 | 11 | 25 | 2 | 11 | 14 | 2 | 23 | 0 | 0 | 25 | 44.0% | 8.0% | 0.0%
J01 | 12 | 53 | 0 | 9 | 44 | 4 | 49 | 0 | 0 | 53 | 17.0% | 7.5% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
TOTALS |  | 1019 | 292 | 185 | 834 | 24 | 995 | 0 | 0 | 1019 | 18% | 2% | 0%

## Areas Summary (By Material)
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J04 | 7 | 152 | 36 | 13 | 139 | 10 | 142 | 0 | 0 | 152 | 8.6% | 6.6% | 0.0%
J05 | 7 | 42 | 4 | 1 | 41 | 1 | 41 | 0 | 0 | 42 | 2.4% | 2.4% | 0.0%
J18 | 11 | 13 | 2 | 4 | 9 | 2 | 11 | 0 | 0 | 13 | 30.8% | 15.4% | 0.0%
J13 | 11 | 12 | 4 | 3 | 9 | 2 | 10 | 0 | 0 | 12 | 25.0% | 16.7% | 0.0%
J32 | 4 | 38 | 6 | 4 | 34 | 0 | 38 | 0 | 0 | 38 | 10.5% | 0.0% | 0.0%
TOTALS |  | 257 | 52 | 25 | 232 | 15 | 242 | 0 | 0 | 257 | 10% | 6% | 0%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J13 | 11 | 10 | 0 | 2 | 8 | 0 | 10 | 0 | 0 | 10 | 20.0% | 0.0% | 0.0%
J18 | 11 | 12 | 0 | 7 | 5 | 0 | 12 | 0 | 0 | 12 | 58.3% | 0.0% | 0.0%
J01 | 12 | 28 | 0 | 7 | 21 | 2 | 26 | 0 | 0 | 28 | 25.0% | 7.1% | 0.0%
J30 | 1 | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 100% | 0.0% | 0.0%
J03 | 10 | 9 | 0 | 1 | 8 | 0 | 9 | 0 | 0 | 9 | 11.1% | 0.0% | 0.0%
J23 | 3 | 45 | 5 | 32 | 13 | 0 | 45 | 0 | 0 | 45 | 71.1% | 0.0% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
J32 | 4 | 204 | 91 | 53 | 151 | 3 | 201 | 0 | 0 | 204 | 26.0% | 1.5% | 0.0%
J06 | 5 | 73 | 35 | 20 | 53 | 0 | 73 | 0 | 0 | 73 | 27.4% | 0.0% | 0.0%
J07 | 5 | 66 | 33 | 15 | 51 | 0 | 66 | 0 | 0 | 66 | 22.7% | 0.0% | 0.0%
J21 | 6 | 20 | 0 | 14 | 6 | 2 | 18 | 0 | 0 | 20 | 70.0% | 10.0% | 0.0%
J20 | 6 | 11 | 3 | 1 | 10 | 0 | 11 | 0 | 0 | 11 | 9.1% | 0.0% | 0.0%
J04 | 7 | 4 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
J10 | 8 | 10 | 4 | 1 | 9 | 0 | 10 | 0 | 0 | 10 | 10.0% | 0.0% | 0.0%
J25 | 8 | 4 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
TOTALS |  | 506 | 184 | 156 | 350 | 7 | 499 | 0 | 0 | 506 | 31% | 1% | 0%
A333 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 4 | 50.0% | 50.0% | 0.0%
J20 | 6 | 10 | 0 | 1 | 9 | 0 | 10 | 0 | 0 | 10 | 10.0% | 0.0% | 0.0%
J21 | 6 | 12 | 7 | 1 | 11 | 0 | 12 | 0 | 0 | 12 | 8.3% | 0.0% | 0.0%
TOTALS |  | 26 | 7 | 4 | 22 | 2 | 24 | 0 | 0 | 26 | 15% | 8% | 0%
ALUMINUM Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 122 | 0 | 0 | 122 | 0 | 122 | 0 | 0 | 122 | 0% | 0.0% | 0.0%
J01 | 12 | 17 | 0 | 0 | 17 | 0 | 17 | 0 | 0 | 17 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J25 | 8 | 35 | 11 | 0 | 35 | 0 | 35 | 0 | 0 | 35 | 0% | 0.0% | 0.0%
TOTALS |  | 177 | 11 | 0 | 177 | 0 | 177 | 0 | 0 | 177 | 0% | 0% | 0%
304/304L SS CRYO Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
J21 | 6 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
TOTALS |  | 14 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 14 | 0% | 0% | 0%
#N/A Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J06 | 5 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J07 | 5 | 28 | 28 | 0 | 28 | 0 | 28 | 0 | 0 | 28 | 0% | 0.0% | 0.0%
TOTALS |  | 38 | 38 | 0 | 38 | 0 | 38 | 0 | 0 | 38 | 0% | 0% | 0%
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0% | 0.0% | 0.0%
TOTALS |  | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0% | 0% | 0%

## Spool Location
Not Workable | 540
Workable | 0
Issued | 124
Pulled | 39
Welded Out | 24
Shipped to Coating | 0
Ready To Deliver | 0
Delivered | 0
On Hold | 292

## Shorts by Scope
| 1019 Spools | 185 Workable | 187 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 163 | 0
Flanges | 875 | 0 | 0
Fittings | 450 | 0 | 0
Supports | 3 | 0 | 0
TOTAL
Pipe | 5262.4 | 0 | 0
Not on Line List

## Purchased by Scope
| 1019 Spools | 185 Workable | 187 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 137 | 0
Flanges | 507 | 0 | 0
Fittings | 358 | 0 | 0
Supports | 1 | 0 | 0
TOTAL
Pipe | 694 | 0 | 0

## No Material by Scope
| 1019 Spools | 185 Workable | 187 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 26 | 0
Flanges | 368 | 0 | 0
Fittings | 92 | 0 | 0
Supports | 2 | 0 | 0
TOTAL
Pipe | 4568.4 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 36

## Spools by Scope
| 1019 Spools | 185 Workable | 187 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 124 | 0
Flanges | 329 | 0 | 0
Fittings | 200 | 0 | 0
Pipe | 34 | 0 | 0
Supports | 1 | 0 | 0
Issued |  |  |  | 187
Issued (Missing Items) |  |  |  | 0
Workable (Not Issued) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 126
Discrepancies |  |  |  | 18
TOTAL |  |  |  | 1019

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)
44-2
48-1
52-2
341-1
401-1
401-2
401-3
401-4
463-4