## PRINTOUT
EXXON: 6951 |  | 1701 Spools |  |  | 1386 Workable |  |  | 1384 Issued
SPOOLS BY SCOPE | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
SPOOLS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Pipe | [5 empty] | Supports
Supports | [5 empty] | TOTAL
Issued
Issued (Missing Items) | [5 empty] | Pipe
Workable (Not Issued)
On Hold (No Shorts)
Discrepancies | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
TOTAL | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Valves
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | Flanges
ITEMS | Performance | Client | Other | TOTAL |  | Fittings
Valves | [5 empty] | Supports
Flanges | [5 empty] | TOTAL
Fittings
Supports | [5 empty] | Pipe
TOTAL
Pipe | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Not on Line List | [5 empty] | Purchased
6951 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
16B | 1 | 35 | 0 | 32 | 3 | 31 | 4 | 17 | 2 | 33 | 91.43% | 88.57% | 5.71%
14A | 2 | 27 | 0 | 22 | 5 | 22 | 5 | 21 | 2 | 25 | 81.48% | 81.48% | 7.41%
20B | 3 | 58 | 0 | 47 | 11 | 46 | 12 | 46 | 14 | 44 | 81.03% | 79.31% | 24.14%
15C | 4 | 14 | 0 | 13 | 1 | 13 | 1 | 3 | 10 | 4 | 92.86% | 92.86% | 71.43%
15B | 5 | 31 | 0 | 28 | 3 | 28 | 3 | 7 | 22 | 9 | 90.32% | 90.32% | 70.97%
15A | 6 | 53 | 0 | 47 | 6 | 46 | 7 | 11 | 34 | 19 | 88.68% | 86.79% | 64.15%
31A | 7 | 151 | 9 | 135 | 16 | 107 | 44 | 88 | 16 | 135 | 89.40% | 70.86% | 10.60%
14B | 8 | 388 | 0 | 378 | 10 | 361 | 27 | 322 | 114 | 274 | 97.42% | 93.04% | 29.38%
13F | 9 | 259 | 10 | 153 | 106 | 135 | 124 | 117 | 2 | 257 | 59.07% | 52.12% | 0.77%
13E | 10 | 64 | 0 | 52 | 12 | 43 | 21 | 38 | 2 | 62 | 81.25% | 67.19% | 3.13%
30B | 11 | 59 | 2 | 52 | 7 | 50 | 9 | 24 | 3 | 56 | 88.14% | 84.75% | 5.08%
13H | 12 | 46 | 0 | 39 | 7 | 39 | 7 | 38 | 0 | 46 | 84.78% | 84.78% | 0.00%
13G | 13 | 20 | 2 | 14 | 6 | 14 | 6 | 10 | 0 | 20 | 70.00% | 70.00% | 0.00%
13A | 14 | 82 | 0 | 68 | 14 | 65 | 17 | 53 | 5 | 77 | 82.93% | 79.27% | 6.10%
13C | 15 | 242 | 18 | 166 | 76 | 140 | 102 | 121 | 8 | 234 | 68.60% | 57.85% | 3.31%
13D | 16 | 71 | 11 | 49 | 22 | 39 | 32 | 33 | 0 | 71 | 69.01% | 54.93% | 0.00%
13B | 17 | 66 | 0 | 62 | 4 | 42 | 24 | 29 | 6 | 60 | 93.94% | 63.64% | 9.09%
16A | 18 | 35 | 0 | 29 | 6 | 25 | 10 | 15 | 0 | 35 | 82.86% | 71.43% | 0.00%
TOTALS |  | 1701 | 52 | 1386 | 315 | 1246 | 455 | 993 | 240 | 1461 | 81% | 73% | 14%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
16B | 1 | 35 | 0 | 32 | 3 | 31 | 4 | 17 | 2 | 33 | 91.43% | 88.57% | 5.71%
14A | 2 | 27 | 0 | 22 | 5 | 22 | 5 | 21 | 2 | 25 | 81.48% | 81.48% | 7.41%
20B | 3 | 58 | 0 | 47 | 11 | 46 | 12 | 46 | 14 | 44 | 81.03% | 79.31% | 24.14%
15C | 4 | 14 | 0 | 13 | 1 | 13 | 1 | 3 | 10 | 4 | 92.86% | 92.86% | 71.43%
15B | 5 | 31 | 0 | 28 | 3 | 28 | 3 | 7 | 22 | 9 | 90.32% | 90.32% | 70.97%
15A | 6 | 53 | 0 | 47 | 6 | 46 | 7 | 11 | 34 | 19 | 88.68% | 86.79% | 64.15%
31A | 7 | 151 | 9 | 135 | 16 | 107 | 44 | 88 | 16 | 135 | 89.40% | 70.86% | 10.60%
14B | 8 | 388 | 0 | 378 | 10 | 361 | 27 | 322 | 114 | 274 | 97.42% | 93.04% | 29.38%
13F | 9 | 259 | 10 | 153 | 106 | 135 | 124 | 117 | 2 | 257 | 59.07% | 52.12% | 0.77%
13E | 10 | 64 | 0 | 52 | 12 | 43 | 21 | 38 | 2 | 62 | 81.25% | 67.19% | 3.13%
30B | 11 | 59 | 2 | 52 | 7 | 50 | 9 | 24 | 3 | 56 | 88.14% | 84.75% | 5.08%
13H | 12 | 46 | 0 | 39 | 7 | 39 | 7 | 38 | 0 | 46 | 84.78% | 84.78% | 0.00%
13G | 13 | 20 | 2 | 14 | 6 | 14 | 6 | 10 | 0 | 20 | 70.00% | 70.00% | 0.00%
13A | 14 | 82 | 0 | 68 | 14 | 65 | 17 | 53 | 5 | 77 | 82.93% | 79.27% | 6.10%
13C | 15 | 242 | 18 | 166 | 76 | 140 | 102 | 121 | 8 | 234 | 68.60% | 57.85% | 3.31%
13D | 16 | 71 | 11 | 49 | 22 | 39 | 32 | 33 | 0 | 71 | 69.01% | 54.93% | 0.00%
13B | 17 | 66 | 0 | 62 | 4 | 42 | 24 | 29 | 6 | 60 | 93.94% | 63.64% | 9.09%
16A | 18 | 35 | 0 | 29 | 6 | 25 | 10 | 15 | 0 | 35 | 82.86% | 71.43% | 0.00%
TOTALS |  | 1701 | 52 | 1386 | 315 | 1246 | 455 | 993 | 240 | 1461 | 81% | 73% | 14%

## Areas Summary (By Material)
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
13G | 13 | 16 | 0 | 12 | 4 | 12 | 4 | 10 | 0 | 16 | 75.00% | 75.00% | 0.00%
20B | 3 | 58 | 0 | 47 | 11 | 46 | 12 | 46 | 14 | 44 | 81.03% | 79.31% | 24.14%
13A | 14 | 80 | 0 | 66 | 14 | 63 | 17 | 53 | 3 | 77 | 82.50% | 78.75% | 3.75%
15A | 6 | 20 | 0 | 14 | 6 | 13 | 7 | 11 | 1 | 19 | 70.00% | 65.00% | 5.00%
15B | 5 | 11 | 0 | 8 | 3 | 8 | 3 | 7 | 2 | 9 | 72.73% | 72.73% | 18.18%
15C | 4 | 4 | 0 | 3 | 1 | 3 | 1 | 3 | 0 | 4 | 75.00% | 75.00% | 0.00%
16A | 18 | 27 | 0 | 21 | 6 | 17 | 10 | 15 | 0 | 27 | 77.78% | 62.96% | 0.00%
16B | 1 | 23 | 0 | 20 | 3 | 19 | 4 | 17 | 0 | 23 | 86.96% | 82.61% | 0.00%
13B | 17 | 66 | 0 | 62 | 4 | 42 | 24 | 29 | 6 | 60 | 93.94% | 63.64% | 9.09%
13E | 10 | 64 | 0 | 52 | 12 | 43 | 21 | 38 | 2 | 62 | 81.25% | 67.19% | 3.13%
14A | 2 | 27 | 0 | 22 | 5 | 22 | 5 | 21 | 2 | 25 | 81.48% | 81.48% | 7.41%
13D | 16 | 57 | 0 | 48 | 9 | 38 | 19 | 32 | 0 | 57 | 84.21% | 66.67% | 0.00%
13F | 9 | 194 | 0 | 108 | 86 | 92 | 102 | 81 | 2 | 192 | 55.67% | 47.42% | 1.03%
13H | 12 | 43 | 0 | 39 | 4 | 39 | 4 | 38 | 0 | 43 | 90.70% | 90.70% | 0.00%
30B | 11 | 51 | 2 | 44 | 7 | 42 | 9 | 24 | 3 | 48 | 86.27% | 82.35% | 5.88%
31A | 7 | 148 | 9 | 132 | 16 | 104 | 44 | 88 | 13 | 135 | 89.19% | 70.27% | 8.78%
13C | 15 | 151 | 0 | 129 | 22 | 103 | 48 | 93 | 7 | 144 | 85.43% | 68.21% | 4.64%
14B | 8 | 360 | 0 | 350 | 10 | 334 | 26 | 322 | 89 | 271 | 97.22% | 92.78% | 24.72%
TOTALS |  | 1400 | 11 | 1177 | 223 | 1040 | 360 | 928 | 144 | 1256 | 84% | 74% | 10%
SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
13G | 13 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 100% | 100% | 0.00%
13A | 14 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 100% | 100% | 100%
16A | 18 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 100% | 100% | 0.00%
16B | 1 | 12 | 0 | 12 | 0 | 12 | 0 | 0 | 2 | 10 | 100% | 100% | 16.67%
15A | 6 | 33 | 0 | 33 | 0 | 33 | 0 | 0 | 33 | 0 | 100% | 100% | 100%
15B | 5 | 20 | 0 | 20 | 0 | 20 | 0 | 0 | 20 | 0 | 100% | 100% | 100%
15C | 4 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0 | 100% | 100% | 100%
31A | 7 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 100% | 100% | 100%
13F | 9 | 35 | 0 | 31 | 4 | 31 | 4 | 24 | 0 | 35 | 88.57% | 88.57% | 0.00%
13C | 15 | 48 | 4 | 30 | 18 | 30 | 18 | 23 | 1 | 47 | 62.50% | 62.50% | 2.08%
14B | 8 | 28 | 0 | 28 | 0 | 27 | 1 | 0 | 25 | 3 | 100% | 96.43% | 89.29%
30B | 11 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 100% | 100% | 0.00%
TOTALS |  | 209 | 4 | 187 | 22 | 186 | 23 | 47 | 96 | 113 | 89% | 89% | 46%
P5 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
13G | 13 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0.00% | 0.00% | 0.00%
13D | 16 | 14 | 11 | 1 | 13 | 1 | 13 | 1 | 0 | 14 | 7.14% | 7.14% | 0.00%
13F | 9 | 30 | 10 | 14 | 16 | 12 | 18 | 12 | 0 | 30 | 46.67% | 40.00% | 0.00%
13C | 15 | 43 | 14 | 7 | 36 | 7 | 36 | 5 | 0 | 43 | 16.28% | 16.28% | 0.00%
TOTALS |  | 89 | 37 | 22 | 67 | 20 | 69 | 18 | 0 | 89 | 25% | 22% | 0%
C-276 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
13H | 12 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0.00% | 0.00% | 0.00%
TOTALS |  | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0% | 0%

## Spool Location
Not Workable
Workable
Issued
Pulled
Welded Out
Shipped to Coating
Delivered

## Shorts by Scope
| 1701 Spools | 1386 Workable | 1384 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 244 | 0 | 0
Flanges | 75 | 0 | 0
Fittings | 119 | 0 | 0
Supports | 22 | 0 | 0
TOTAL
Pipe | 1052.9 | 0 | 0
Not on Line List

## Purchased by Scope
| 1701 Spools | 1386 Workable | 1384 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 243 | 0 | 0
Flanges | 34 | 0 | 0
Fittings | 104 | 0 | 0
Supports | 14 | 0 | 0
TOTAL
Pipe | 795 | 0 | 0

## No Material by Scope
| 1701 Spools | 1386 Workable | 1384 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 1 | 0 | 0
Flanges | 41 | 0 | 0
Fittings | 15 | 0 | 0
Supports | 8 | 0 | 0
TOTAL
Pipe | 257.9 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 27 | 0 | 0

## Spools by Scope
| 1701 Spools | 1386 Workable | 1384 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 147 | 0 | 0
Flanges | 38 | 0 | 0
Fittings | 54 | 0 | 0
Pipe | 52 | 0 | 0
Supports | 7 | 0 | 0
Issued |  |  |  | 1384
Issued (Missing Items) |  |  |  | 3
Workable (Not Issued) |  |  |  | 9
On Hold (No Shorts) |  |  |  | 22
Discrepancies |  |  |  | 3
TOTAL |  |  |  | 1701

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)