## PRINTOUT
CP CHEM: 7052 |  | 981 Spools |  |  | 30 Workable |  |  | 30 Issued
SPOOLS BY SCOPE | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
SPOOLS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Pipe | [5 empty] | Supports
Supports | [5 empty] | TOTAL
Issued
Issued (Missing Items) | [5 empty] | Pipe
Workable (Not Issued)
On Hold (No Shorts)
Discrepancies | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
TOTAL | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Valves
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | Flanges
ITEMS | Performance | Client | Other | TOTAL |  | Fittings
Valves | [5 empty] | Supports
Flanges | [5 empty] | TOTAL
Fittings
Supports | [5 empty] | Pipe
TOTAL
Pipe | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Not on Line List | [5 empty] | Purchased
7052 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J14 | 2 | 101 | 54 | 0 | 101 | 0 | 101 | 0 | 0 | 101 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 5 | 0 | 45 | 0 | 45 | 0 | 0 | 45 | 0% | 0.0% | 0.0%
J32 | 4 | 242 | 114 | 6 | 236 | 0 | 242 | 0 | 0 | 242 | 2.5% | 0.0% | 0.0%
J06 | 5 | 81 | 46 | 5 | 76 | 0 | 81 | 0 | 0 | 81 | 6.2% | 0.0% | 0.0%
J07 | 5 | 92 | 63 | 0 | 92 | 0 | 92 | 0 | 0 | 92 | 0% | 0.0% | 0.0%
J21 | 6 | 42 | 17 | 2 | 40 | 0 | 42 | 0 | 0 | 42 | 4.8% | 0.0% | 0.0%
J20 | 6 | 21 | 2 | 0 | 21 | 0 | 21 | 0 | 0 | 21 | 0% | 0.0% | 0.0%
J04 | 7 | 154 | 37 | 10 | 144 | 0 | 154 | 0 | 0 | 154 | 6.5% | 0.0% | 0.0%
J05 | 7 | 42 | 4 | 1 | 41 | 0 | 42 | 0 | 0 | 42 | 2.4% | 0.0% | 0.0%
J25 | 8 | 39 | 13 | 0 | 39 | 0 | 39 | 0 | 0 | 39 | 0% | 0.0% | 0.0%
J10 | 8 | 10 | 5 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 9 | 0% | 0.0% | 0.0%
J13 | 11 | 18 | 1 | 2 | 16 | 0 | 18 | 0 | 0 | 18 | 11.1% | 0.0% | 0.0%
J18 | 11 | 23 | 2 | 2 | 21 | 0 | 23 | 0 | 0 | 23 | 8.7% | 0.0% | 0.0%
J01 | 12 | 49 | 0 | 2 | 47 | 0 | 49 | 0 | 0 | 49 | 4.1% | 0.0% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
TOTALS |  | 981 | 370 | 30 | 951 | 0 | 981 | 0 | 0 | 981 | 3% | 0% | 0%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J14 | 2 | 101 | 54 | 0 | 101 | 0 | 101 | 0 | 0 | 101 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 5 | 0 | 45 | 0 | 45 | 0 | 0 | 45 | 0% | 0.0% | 0.0%
J32 | 4 | 242 | 114 | 6 | 236 | 0 | 242 | 0 | 0 | 242 | 2.5% | 0.0% | 0.0%
J06 | 5 | 81 | 46 | 5 | 76 | 0 | 81 | 0 | 0 | 81 | 6.2% | 0.0% | 0.0%
J07 | 5 | 92 | 63 | 0 | 92 | 0 | 92 | 0 | 0 | 92 | 0% | 0.0% | 0.0%
J21 | 6 | 42 | 17 | 2 | 40 | 0 | 42 | 0 | 0 | 42 | 4.8% | 0.0% | 0.0%
J20 | 6 | 21 | 2 | 0 | 21 | 0 | 21 | 0 | 0 | 21 | 0% | 0.0% | 0.0%
J04 | 7 | 154 | 37 | 10 | 144 | 0 | 154 | 0 | 0 | 154 | 6.5% | 0.0% | 0.0%
J05 | 7 | 42 | 4 | 1 | 41 | 0 | 42 | 0 | 0 | 42 | 2.4% | 0.0% | 0.0%
J25 | 8 | 39 | 13 | 0 | 39 | 0 | 39 | 0 | 0 | 39 | 0% | 0.0% | 0.0%
J10 | 8 | 10 | 5 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 9 | 0% | 0.0% | 0.0%
J13 | 11 | 18 | 1 | 2 | 16 | 0 | 18 | 0 | 0 | 18 | 11.1% | 0.0% | 0.0%
J18 | 11 | 23 | 2 | 2 | 21 | 0 | 23 | 0 | 0 | 23 | 8.7% | 0.0% | 0.0%
J01 | 12 | 49 | 0 | 2 | 47 | 0 | 49 | 0 | 0 | 49 | 4.1% | 0.0% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
TOTALS |  | 981 | 370 | 30 | 951 | 0 | 981 | 0 | 0 | 981 | 3% | 0% | 0%

## Areas Summary (By Material)
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J04 | 7 | 150 | 33 | 10 | 140 | 0 | 150 | 0 | 0 | 150 | 6.7% | 0.0% | 0.0%
J05 | 7 | 42 | 4 | 1 | 41 | 0 | 42 | 0 | 0 | 42 | 2.4% | 0.0% | 0.0%
J18 | 11 | 13 | 2 | 2 | 11 | 0 | 13 | 0 | 0 | 13 | 15.4% | 0.0% | 0.0%
J13 | 11 | 12 | 1 | 2 | 10 | 0 | 12 | 0 | 0 | 12 | 16.7% | 0.0% | 0.0%
J32 | 4 | 38 | 5 | 0 | 38 | 0 | 38 | 0 | 0 | 38 | 0% | 0.0% | 0.0%
TOTALS |  | 255 | 45 | 15 | 240 | 0 | 255 | 0 | 0 | 255 | 6% | 0% | 0%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J13 | 11 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 0% | 0.0% | 0.0%
J18 | 11 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J01 | 12 | 28 | 0 | 0 | 28 | 0 | 28 | 0 | 0 | 28 | 0% | 0.0% | 0.0%
J30 | 1 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 9 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 5 | 0 | 45 | 0 | 45 | 0 | 0 | 45 | 0% | 0.0% | 0.0%
- | #N/A | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 0 | 7 | 0% | 0.0% | 0.0%
J32 | 4 | 204 | 109 | 6 | 198 | 0 | 204 | 0 | 0 | 204 | 2.9% | 0.0% | 0.0%
J06 | 5 | 71 | 36 | 5 | 66 | 0 | 71 | 0 | 0 | 71 | 7.0% | 0.0% | 0.0%
J07 | 5 | 64 | 35 | 0 | 64 | 0 | 64 | 0 | 0 | 64 | 0% | 0.0% | 0.0%
J21 | 6 | 20 | 0 | 2 | 18 | 0 | 20 | 0 | 0 | 20 | 10.0% | 0.0% | 0.0%
J20 | 6 | 11 | 2 | 0 | 11 | 0 | 11 | 0 | 0 | 11 | 0% | 0.0% | 0.0%
J04 | 7 | 4 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
J10 | 8 | 10 | 5 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J25 | 8 | 4 | 2 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
TOTALS |  | 496 | 205 | 13 | 483 | 0 | 496 | 0 | 0 | 496 | 3% | 0% | 0%
A333 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 2 | 2 | 0 | 4 | 0 | 0 | 4 | 50.0% | 0.0% | 0.0%
J20 | 6 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J21 | 6 | 12 | 7 | 0 | 12 | 0 | 12 | 0 | 0 | 12 | 0% | 0.0% | 0.0%
TOTALS |  | 26 | 7 | 2 | 24 | 0 | 26 | 0 | 0 | 26 | 8% | 0% | 0%
ALUMINUM Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 101 | 54 | 0 | 101 | 0 | 101 | 0 | 0 | 101 | 0% | 0.0% | 0.0%
J01 | 12 | 13 | 0 | 0 | 13 | 0 | 13 | 0 | 0 | 13 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J25 | 8 | 35 | 11 | 0 | 35 | 0 | 35 | 0 | 0 | 35 | 0% | 0.0% | 0.0%
TOTALS |  | 152 | 65 | 0 | 152 | 0 | 152 | 0 | 0 | 152 | 0% | 0% | 0%
304/304L SS CRYO Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
J21 | 6 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
TOTALS |  | 14 | 10 | 0 | 14 | 0 | 14 | 0 | 0 | 14 | 0% | 0% | 0%
#N/A Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J06 | 5 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J07 | 5 | 28 | 28 | 0 | 28 | 0 | 28 | 0 | 0 | 28 | 0% | 0.0% | 0.0%
TOTALS |  | 38 | 38 | 0 | 38 | 0 | 38 | 0 | 0 | 38 | 0% | 0% | 0%

## Spool Location
Not Workable | 581
Workable | 0
Issued | 26
Pulled | 4
Welded Out | 0
Shipped to Coating | 0
Ready To Deliver | 0
Delivered | 0
On Hold | 370

## Shorts by Scope
| 981 Spools | 30 Workable | 30 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0
Not on Line List

## Purchased by Scope
| 981 Spools | 30 Workable | 30 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0

## No Material by Scope
| 981 Spools | 30 Workable | 30 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 0

## Spools by Scope
| 981 Spools | 30 Workable | 30 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Pipe | 0 | 0 | 0
Supports | 0 | 0 | 0
Issued |  |  |  | 30
Issued (Missing Items) |  |  |  | 0
Workable (Not Issued) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 370
Discrepancies |  |  |  | 581
TOTAL |  |  |  | 981

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)