## PRINTOUT
CP CHEM: 7052 |  | 1194 Spools |  | 1045 Workable |  | 965 Issued
SPOOLS BY SCOPE | [5 empty] | Workable Man Hours (By Material)
SPOOLS | Performance | Client | Other | TOTAL |  |  |  | Carbon | Stainless | TOTAL
Valves | [5 empty] | Workable Man Hours
Flanges
Fittings | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
Pipe | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Supports | [5 empty] | Valves
Issued | [5 empty] | Flanges
Workable (Not Issued) | [5 empty] | Fittings
Issued (Missing Items) | [5 empty] | Supports
On Hold (No Shorts) | [5 empty] | TOTAL
Discrepancies
TOTAL | [5 empty] | Pipe
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Supports | [5 empty] | Supports
TOTAL | [5 empty] | TOTAL
Pipe | [5 empty] | Pipe
Not on Line List | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Purchased
7052 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
Nozzle |  | 153 | 0 | 153 | 0 | 0 | 153 | 0 | 0 | 153 | 100% | 0.0% | 0.0%
J30 | 1 | 9 | 0 | 9 | 0 | 3 | 6 | 3 | 0 | 9 | 100% | 33.3% | 0.0%
J14 | 2 | 123 | 2 | 116 | 7 | 65 | 58 | 0 | 0 | 123 | 94.3% | 52.8% | 0.0%
J23 | 3 | 45 | 0 | 43 | 2 | 43 | 2 | 38 | 0 | 45 | 95.6% | 95.6% | 0.0%
J32 | 4 | 255 | 48 | 206 | 49 | 180 | 75 | 79 | 36 | 219 | 80.8% | 70.6% | 14.1%
J06 | 5 | 89 | 14 | 71 | 18 | 66 | 23 | 19 | 22 | 67 | 79.8% | 74.2% | 24.7%
J07 | 5 | 93 | 19 | 70 | 23 | 66 | 27 | 20 | 19 | 74 | 75.3% | 71.0% | 20.4%
J21 | 6 | 42 | 0 | 40 | 2 | 40 | 2 | 28 | 0 | 42 | 95.2% | 95.2% | 0.0%
J20 | 6 | 21 | 1 | 20 | 1 | 20 | 1 | 11 | 0 | 21 | 95.2% | 95.2% | 0.0%
J04 | 7 | 158 | 13 | 143 | 15 | 136 | 22 | 0 | 0 | 158 | 90.5% | 86.1% | 0.0%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 0 | 0 | 42 | 100% | 100% | 0.0%
J25 | 8 | 39 | 15 | 24 | 15 | 14 | 25 | 1 | 0 | 39 | 61.5% | 35.9% | 0.0%
J10 | 8 | 10 | 3 | 5 | 5 | 4 | 6 | 1 | 0 | 10 | 50.0% | 40.0% | 0.0%
J19 | 9 | 3 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 3 | 100% | 33.3% | 0.0%
J03 | 10 | 9 | 0 | 9 | 0 | 8 | 1 | 8 | 0 | 9 | 100% | 88.9% | 0.0%
J13 | 11 | 22 | 0 | 22 | 0 | 20 | 2 | 6 | 1 | 21 | 100% | 90.9% | 4.5%
J18 | 11 | 25 | 0 | 25 | 0 | 25 | 0 | 10 | 0 | 25 | 100% | 100% | 0.0%
J01 | 12 | 53 | 6 | 41 | 12 | 41 | 12 | 27 | 0 | 53 | 77.4% | 77.4% | 0.0%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
TOTALS |  | 1194 | 121 | 1126 | 68 | 777 | 417 | 254 | 78 | 1116 | 88% | 65% | 7%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
Nozzle |  | 153 | 0 | 153 | 0 | 0 | 153 | 0 | 0 | 153 | 100% | 0.0% | 0.0%
J30 | 1 | 9 | 0 | 9 | 0 | 3 | 6 | 3 | 0 | 9 | 100% | 33.3% | 0.0%
J14 | 2 | 123 | 2 | 116 | 7 | 65 | 58 | 0 | 0 | 123 | 94.3% | 52.8% | 0.0%
J23 | 3 | 45 | 0 | 43 | 2 | 43 | 2 | 38 | 0 | 45 | 95.6% | 95.6% | 0.0%
J32 | 4 | 255 | 48 | 206 | 49 | 180 | 75 | 79 | 36 | 219 | 80.8% | 70.6% | 14.1%
J06 | 5 | 89 | 14 | 71 | 18 | 66 | 23 | 19 | 22 | 67 | 79.8% | 74.2% | 24.7%
J07 | 5 | 93 | 19 | 70 | 23 | 66 | 27 | 20 | 19 | 74 | 75.3% | 71.0% | 20.4%
J21 | 6 | 42 | 0 | 40 | 2 | 40 | 2 | 28 | 0 | 42 | 95.2% | 95.2% | 0.0%
J20 | 6 | 21 | 1 | 20 | 1 | 20 | 1 | 11 | 0 | 21 | 95.2% | 95.2% | 0.0%
J04 | 7 | 158 | 13 | 143 | 15 | 136 | 22 | 0 | 0 | 158 | 90.5% | 86.1% | 0.0%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 0 | 0 | 42 | 100% | 100% | 0.0%
J25 | 8 | 39 | 15 | 24 | 15 | 14 | 25 | 1 | 0 | 39 | 61.5% | 35.9% | 0.0%
J10 | 8 | 10 | 3 | 5 | 5 | 4 | 6 | 1 | 0 | 10 | 50.0% | 40.0% | 0.0%
J19 | 9 | 3 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 3 | 100% | 33.3% | 0.0%
J03 | 10 | 9 | 0 | 9 | 0 | 8 | 1 | 8 | 0 | 9 | 100% | 88.9% | 0.0%
J13 | 11 | 22 | 0 | 22 | 0 | 20 | 2 | 6 | 1 | 21 | 100% | 90.9% | 4.5%
J18 | 11 | 25 | 0 | 25 | 0 | 25 | 0 | 10 | 0 | 25 | 100% | 100% | 0.0%
J01 | 12 | 53 | 6 | 41 | 12 | 41 | 12 | 27 | 0 | 53 | 77.4% | 77.4% | 0.0%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
TOTALS |  | 1194 | 121 | 1045 | 149 | 777 | 417 | 254 | 78 | 1116 | 88% | 65% | 7%

## Areas Summary (By Material)
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J04 | 7 | 154 | 9 | 143 | 11 | 136 | 18 | 0 | 0 | 154 | 92.9% | 88.3% | 0.0%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 0 | 0 | 42 | 100% | 100% | 0.0%
J18 | 11 | 13 | 0 | 13 | 0 | 13 | 0 | 0 | 0 | 13 | 100% | 100% | 0.0%
J13 | 11 | 12 | 0 | 12 | 0 | 10 | 2 | 0 | 0 | 12 | 100% | 83.3% | 0.0%
J32 | 4 | 38 | 5 | 33 | 5 | 33 | 5 | 0 | 0 | 38 | 86.8% | 86.8% | 0.0%
Nozzle |  | 31 | 0 | 31 | 0 | 0 | 31 | 0 | 0 | 31 | 100% | 0.0% | 0.0%
TOTALS |  | 290 | 14 | 274 | 16 | 234 | 56 | 0 | 0 | 290 | 94% | 81% | 0%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J13 | 11 | 10 | 0 | 10 | 0 | 10 | 0 | 6 | 1 | 9 | 100% | 100% | 10.0%
J18 | 11 | 12 | 0 | 12 | 0 | 12 | 0 | 10 | 0 | 12 | 100% | 100% | 0.0%
J01 | 12 | 28 | 0 | 28 | 0 | 28 | 0 | 25 | 0 | 28 | 100% | 100% | 0.0%
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J03 | 10 | 9 | 0 | 9 | 0 | 8 | 1 | 8 | 0 | 9 | 100% | 88.9% | 0.0%
J23 | 3 | 45 | 0 | 43 | 2 | 43 | 2 | 38 | 0 | 45 | 95.6% | 95.6% | 0.0%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J32 | 4 | 217 | 43 | 173 | 44 | 147 | 70 | 79 | 36 | 181 | 79.7% | 67.7% | 16.6%
J07 | 5 | 61 | 19 | 41 | 20 | 40 | 21 | 20 | 2 | 59 | 67.2% | 65.6% | 3.3%
J06 | 5 | 57 | 12 | 44 | 13 | 42 | 15 | 19 | 1 | 56 | 77.2% | 73.7% | 1.8%
J21 | 6 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 100% | 100% | 0.0%
J20 | 6 | 11 | 1 | 10 | 1 | 10 | 1 | 4 | 0 | 11 | 90.9% | 90.9% | 0.0%
J04 | 7 | 4 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
J10 | 8 | 10 | 3 | 5 | 5 | 4 | 6 | 1 | 0 | 10 | 50.0% | 40.0% | 0.0%
J25 | 8 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 4 | 50.0% | 50.0% | 0.0%
TOTALS |  | 494 | 84 | 403 | 91 | 372 | 122 | 237 | 40 | 454 | 82% | 75% | 8%
A333 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 4 | 0 | 4 | 0 | 2 | 0 | 4 | 100% | 100% | 0.0%
J20 | 6 | 10 | 0 | 10 | 0 | 10 | 0 | 7 | 0 | 10 | 100% | 100% | 0.0%
J21 | 6 | 12 | 0 | 11 | 1 | 11 | 1 | 8 | 0 | 12 | 91.7% | 91.7% | 0.0%
TOTALS |  | 26 | 0 | 25 | 1 | 25 | 1 | 17 | 0 | 26 | 96% | 96% | 0%
ALUMINUM Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 122 | 2 | 115 | 7 | 65 | 57 | 0 | 0 | 122 | 94.3% | 53.3% | 0.0%
J01 | 12 | 17 | 6 | 6 | 11 | 6 | 11 | 0 | 0 | 17 | 35.3% | 35.3% | 0.0%
J19 | 9 | 3 | 0 | 3 | 0 | 1 | 2 | 0 | 0 | 3 | 100% | 33.3% | 0.0%
J25 | 8 | 35 | 13 | 22 | 13 | 12 | 23 | 0 | 0 | 35 | 62.9% | 34.3% | 0.0%
Nozzle |  | 122 | 0 | 122 | 0 | 0 | 122 | 0 | 0 | 122 | 100% | 0.0% | 0.0%
TOTALS |  | 299 | 21 | 268 | 31 | 84 | 215 | 0 | 0 | 299 | 90% | 28% | 0%
304/304L SS CRYO Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 3 | 1 | 3 | 1 | 0 | 0 | 4 | 75.0% | 75.0% | 0.0%
J21 | 6 | 10 | 0 | 9 | 1 | 9 | 1 | 0 | 0 | 10 | 90.0% | 90.0% | 0.0%
TOTALS |  | 14 | 0 | 12 | 2 | 12 | 2 | 0 | 0 | 14 | 86% | 86% | 0%
Galv. Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J06 | 5 | 32 | 2 | 27 | 5 | 24 | 8 | 0 | 21 | 11 | 84.4% | 75.0% | 65.6%
J07 | 5 | 32 | 0 | 29 | 3 | 26 | 6 | 0 | 17 | 15 | 90.6% | 81.3% | 53.1%
TOTALS |  | 64 | 2 | 56 | 8 | 50 | 14 | 0 | 38 | 26 | 88% | 78% | 59%
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 100% | 0.0% | 0.0%
J30 | 1 | 6 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 6 | 100% | 0.0% | 0.0%
TOTALS |  | 7 | 0 | 7 | 0 | 0 | 7 | 0 | 0 | 7 | 100% | 0% | 0%

## Spool Location
Not Workable | 28
Workable | 81
Issued | 117
Pulled | 71
Welded Out | 424
Shipped to Coating | 254
Ready To Deliver | 0
Delivered | 78
On Hold | 121

## Shorts by Scope
| 1194 Spools | 1045 Workable | 965 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 28 | 0
Flanges | 4 | 0 | 0
Fittings | 14 | 0 | 0
Supports | 1 | 0 | 0
TOTAL
Pipe | 130.9 | 0 | 0
Not on Line List

## Purchased by Scope
| 1194 Spools | 1045 Workable | 965 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 3 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 1 | 0 | 0
TOTAL
Pipe | 75.7 | 0 | 0

## No Material by Scope
| 1194 Spools | 1045 Workable | 965 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 25 | 0
Flanges | 4 | 0 | 0
Fittings | 14 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 55.2 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 15

## Spools by Scope
| 1194 Spools | 1045 Workable | 965 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 16 | 0
Flanges | 35 | 0 | 0
Fittings | 2 | 0 | 0
Pipe | 10 | 0 | 0
Supports | 0 | 0 | 0
Issued |  |  |  | 965
Workable (Not Issued) |  |  |  | 81
Issued (Missing Items) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 85
Discrepancies |  |  |  | 0
TOTAL |  |  |  | 1194

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)
PM101XA-JW-97765.02-2
PM110XA-S-97778.02-2A
PM110XA-S-97778.02-2B
PM110XA-S-97778.04-2A
PM110XA-S-97778.04-3A
PM110XA-S-97778.05-1A
PM110XA-S-97778.05-3A
PM110XA-S-97778.05-3B
PM110XA-S-97778.06-1A
PM110XA-S-97778.06-2A
PM110XA-S-97778.07-1A
PM110XA-S-97778.07-1B
PM110XA-S-97778.07-2A
PM110XA-S-98378.05-2A