## PRINTOUT
SASOL: 6112 |  | 15059 Spools |  |  | 7559 Workable |  |  | 15059 Issued
SPOOLS BY SCOPE | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
SPOOLS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Pipe | [5 empty] | Supports
Supports | [5 empty] | TOTAL
Issued
Issued (Missing Items) | [5 empty] | Pipe
Workable (Not Issued)
On Hold (No Shorts)
Discrepancies | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
TOTAL | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Valves
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | Flanges
ITEMS | Performance | Client | Other | TOTAL |  | Fittings
Valves | [5 empty] | Supports
Flanges | [5 empty] | TOTAL
Fittings
Supports | [5 empty] | Pipe
TOTAL
Pipe | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Not on Line List | [5 empty] | Purchased
6112 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
15X | Wash Tower | 351 | 0 | 299 | 52 | 299 | 52 | 81 | 299 | 52 | 85.2% | 85.2% | 85.2%
01X | 1B | 3422 | 0 | 1497 | 1925 | 1497 | 1925 | 458 | 1497 | 1925 | 43.7% | 43.7% | 43.7%
05X | 2 | 282 | 0 | 127 | 155 | 127 | 155 | 25 | 127 | 155 | 45.0% | 45.0% | 45.0%
19X | 4 | 517 | 0 | 301 | 216 | 301 | 216 | 74 | 301 | 216 | 58.2% | 58.2% | 58.2%
17X | 5 | 712 | 0 | 404 | 308 | 404 | 308 | 88 | 404 | 308 | 56.7% | 56.7% | 56.7%
27X | 6 | 603 | 0 | 420 | 183 | 420 | 183 | 64 | 420 | 183 | 69.7% | 69.7% | 69.7%
04X | 7 | 116 | 0 | 64 | 52 | 64 | 52 | 5 | 64 | 52 | 55.2% | 55.2% | 55.2%
02X | 8 | 205 | 0 | 99 | 106 | 99 | 106 | 23 | 99 | 106 | 48.3% | 48.3% | 48.3%
16X | 9 | 443 | 0 | 266 | 177 | 266 | 177 | 16 | 266 | 177 | 60.0% | 60.0% | 60.0%
31X | 10 | 382 | 0 | 27 | 355 | 27 | 355 | 15 | 27 | 355 | 7.1% | 7.1% | 7.1%
11X | 11 | 312 | 0 | 70 | 242 | 70 | 242 | 26 | 70 | 242 | 22.4% | 22.4% | 22.4%
12X | 12 | 384 | 0 | 82 | 302 | 82 | 302 | 14 | 82 | 302 | 21.4% | 21.4% | 21.4%
13X | 13 | 713 | 0 | 183 | 530 | 183 | 530 | 19 | 183 | 530 | 25.7% | 25.7% | 25.7%
14X | 14 | 234 | 0 | 135 | 99 | 135 | 99 | 27 | 134 | 100 | 57.7% | 57.7% | 57.3%
18X | 15 | 791 | 0 | 483 | 308 | 483 | 308 | 95 | 483 | 308 | 61.1% | 61.1% | 61.1%
03X | 16 | 10 | 0 | 2 | 8 | 2 | 8 | 0 | 2 | 8 | 20.0% | 20.0% | 20.0%
24X | 17 | 226 | 0 | 62 | 164 | 62 | 164 | 20 | 62 | 164 | 27.4% | 27.4% | 27.4%
23X | 18 | 932 | 0 | 505 | 427 | 505 | 427 | 114 | 505 | 427 | 54.2% | 54.2% | 54.2%
22X | 19 | 765 | 0 | 466 | 299 | 466 | 299 | 99 | 466 | 299 | 60.9% | 60.9% | 60.9%
08X | 20 | 60 | 0 | 30 | 30 | 30 | 30 | 1 | 30 | 30 | 50.0% | 50.0% | 50.0%
07X | 21 | 31 | 0 | 6 | 25 | 6 | 25 | 0 | 6 | 25 | 19.4% | 19.4% | 19.4%
21X | 22 | 391 | 0 | 243 | 148 | 243 | 148 | 25 | 243 | 148 | 62.1% | 62.1% | 62.1%
20X | 23 | 133 | 0 | 89 | 44 | 89 | 44 | 6 | 89 | 44 | 66.9% | 66.9% | 66.9%
28X | 24 | 1125 | 0 | 672 | 453 | 672 | 453 | 133 | 672 | 453 | 59.7% | 59.7% | 59.7%
26X | 25 | 262 | 0 | 188 | 74 | 188 | 74 | 11 | 188 | 74 | 71.8% | 71.8% | 71.8%
06X | 26 | 127 | 0 | 68 | 59 | 68 | 59 | 3 | 68 | 59 | 53.5% | 53.5% | 53.5%
10X | 27 | 110 | 0 | 36 | 74 | 36 | 74 | 0 | 36 | 74 | 32.7% | 32.7% | 32.7%
09X | 28 | 46 | 0 | 6 | 40 | 6 | 40 | 0 | 6 | 40 | 13.0% | 13.0% | 13.0%
29X | 29 | 231 | 0 | 49 | 182 | 49 | 182 | 8 | 49 | 182 | 21.2% | 21.2% | 21.2%
30X | 31 | 1143 | 0 | 680 | 463 | 680 | 463 | 153 | 680 | 463 | 59.5% | 59.5% | 59.5%
TOTALS |  | 15059 | 0 | 7559 | 7500 | 7559 | 7500 | 1603 | 7558 | 7501 | 50% | 50% | 50%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
15X | Wash Tower | 351 | 0 | 299 | 52 | 299 | 52 | 81 | 299 | 52 | 85.2% | 85.2% | 85.2%
01X | 1B | 3422 | 0 | 1497 | 1925 | 1497 | 1925 | 458 | 1497 | 1925 | 43.7% | 43.7% | 43.7%
05X | 2 | 282 | 0 | 127 | 155 | 127 | 155 | 25 | 127 | 155 | 45.0% | 45.0% | 45.0%
19X | 4 | 517 | 0 | 301 | 216 | 301 | 216 | 74 | 301 | 216 | 58.2% | 58.2% | 58.2%
17X | 5 | 712 | 0 | 404 | 308 | 404 | 308 | 88 | 404 | 308 | 56.7% | 56.7% | 56.7%
27X | 6 | 603 | 0 | 420 | 183 | 420 | 183 | 64 | 420 | 183 | 69.7% | 69.7% | 69.7%
04X | 7 | 116 | 0 | 64 | 52 | 64 | 52 | 5 | 64 | 52 | 55.2% | 55.2% | 55.2%
02X | 8 | 205 | 0 | 99 | 106 | 99 | 106 | 23 | 99 | 106 | 48.3% | 48.3% | 48.3%
16X | 9 | 443 | 0 | 266 | 177 | 266 | 177 | 16 | 266 | 177 | 60.0% | 60.0% | 60.0%
31X | 10 | 382 | 0 | 27 | 355 | 27 | 355 | 15 | 27 | 355 | 7.1% | 7.1% | 7.1%
11X | 11 | 312 | 0 | 70 | 242 | 70 | 242 | 26 | 70 | 242 | 22.4% | 22.4% | 22.4%
12X | 12 | 384 | 0 | 82 | 302 | 82 | 302 | 14 | 82 | 302 | 21.4% | 21.4% | 21.4%
13X | 13 | 713 | 0 | 183 | 530 | 183 | 530 | 19 | 183 | 530 | 25.7% | 25.7% | 25.7%
14X | 14 | 234 | 0 | 135 | 99 | 135 | 99 | 27 | 134 | 100 | 57.7% | 57.7% | 57.3%
18X | 15 | 791 | 0 | 483 | 308 | 483 | 308 | 95 | 483 | 308 | 61.1% | 61.1% | 61.1%
03X | 16 | 10 | 0 | 2 | 8 | 2 | 8 | 0 | 2 | 8 | 20.0% | 20.0% | 20.0%
24X | 17 | 226 | 0 | 62 | 164 | 62 | 164 | 20 | 62 | 164 | 27.4% | 27.4% | 27.4%
23X | 18 | 932 | 0 | 505 | 427 | 505 | 427 | 114 | 505 | 427 | 54.2% | 54.2% | 54.2%
22X | 19 | 765 | 0 | 466 | 299 | 466 | 299 | 99 | 466 | 299 | 60.9% | 60.9% | 60.9%
08X | 20 | 60 | 0 | 30 | 30 | 30 | 30 | 1 | 30 | 30 | 50.0% | 50.0% | 50.0%
07X | 21 | 31 | 0 | 6 | 25 | 6 | 25 | 0 | 6 | 25 | 19.4% | 19.4% | 19.4%
21X | 22 | 391 | 0 | 243 | 148 | 243 | 148 | 25 | 243 | 148 | 62.1% | 62.1% | 62.1%
20X | 23 | 133 | 0 | 89 | 44 | 89 | 44 | 6 | 89 | 44 | 66.9% | 66.9% | 66.9%
28X | 24 | 1125 | 0 | 672 | 453 | 672 | 453 | 133 | 672 | 453 | 59.7% | 59.7% | 59.7%
26X | 25 | 262 | 0 | 188 | 74 | 188 | 74 | 11 | 188 | 74 | 71.8% | 71.8% | 71.8%
06X | 26 | 127 | 0 | 68 | 59 | 68 | 59 | 3 | 68 | 59 | 53.5% | 53.5% | 53.5%
10X | 27 | 110 | 0 | 36 | 74 | 36 | 74 | 0 | 36 | 74 | 32.7% | 32.7% | 32.7%
09X | 28 | 46 | 0 | 6 | 40 | 6 | 40 | 0 | 6 | 40 | 13.0% | 13.0% | 13.0%
29X | 29 | 231 | 0 | 49 | 182 | 49 | 182 | 8 | 49 | 182 | 21.2% | 21.2% | 21.2%
30X | 31 | 1143 | 0 | 680 | 463 | 680 | 463 | 153 | 680 | 463 | 59.5% | 59.5% | 59.5%
TOTALS |  | 15059 | 0 | 7559 | 7500 | 7559 | 7500 | 1603 | 7558 | 7501 | 50% | 50% | 50%

## Areas Summary (By Material)
SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
15X | Wash Tower | 289 | 0 | 289 | 0 | 289 | 0 | 71 | 289 | 0 | 100% | 100% | 100%
01X | 1B | 1278 | 0 | 1271 | 7 | 1271 | 7 | 312 | 1271 | 7 | 99.5% | 99.5% | 99.5%
05X | 2 | 123 | 0 | 123 | 0 | 123 | 0 | 25 | 123 | 0 | 100% | 100% | 100%
12X | 12 | 66 | 0 | 66 | 0 | 66 | 0 | 6 | 66 | 0 | 100% | 100% | 100%
16X | 9 | 263 | 0 | 263 | 0 | 263 | 0 | 14 | 263 | 0 | 100% | 100% | 100%
02X | 8 | 99 | 0 | 99 | 0 | 99 | 0 | 23 | 99 | 0 | 100% | 100% | 100%
04X | 7 | 64 | 0 | 64 | 0 | 64 | 0 | 5 | 64 | 0 | 100% | 100% | 100%
09X | 28 | 6 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 0 | 100% | 100% | 100%
17X | 5 | 397 | 0 | 394 | 3 | 394 | 3 | 81 | 394 | 3 | 99.2% | 99.2% | 99.2%
06X | 26 | 68 | 0 | 68 | 0 | 68 | 0 | 3 | 68 | 0 | 100% | 100% | 100%
07X | 21 | 6 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 0 | 100% | 100% | 100%
08X | 20 | 30 | 0 | 30 | 0 | 30 | 0 | 1 | 30 | 0 | 100% | 100% | 100%
20X | 23 | 89 | 0 | 89 | 0 | 89 | 0 | 6 | 89 | 0 | 100% | 100% | 100%
22X | 19 | 446 | 0 | 446 | 0 | 446 | 0 | 86 | 446 | 0 | 100% | 100% | 100%
26X | 25 | 188 | 0 | 188 | 0 | 188 | 0 | 11 | 188 | 0 | 100% | 100% | 100%
27X | 6 | 403 | 0 | 403 | 0 | 403 | 0 | 54 | 403 | 0 | 100% | 100% | 100%
28X | 24 | 674 | 0 | 669 | 5 | 669 | 5 | 133 | 669 | 5 | 99.3% | 99.3% | 99.3%
18X | 15 | 479 | 0 | 478 | 1 | 478 | 1 | 91 | 478 | 1 | 99.8% | 99.8% | 99.8%
19X | 4 | 287 | 0 | 284 | 3 | 284 | 3 | 62 | 284 | 3 | 99.0% | 99.0% | 99.0%
30X | 31 | 674 | 0 | 670 | 4 | 670 | 4 | 152 | 670 | 4 | 99.4% | 99.4% | 99.4%
21X | 22 | 249 | 0 | 243 | 6 | 243 | 6 | 25 | 243 | 6 | 97.6% | 97.6% | 97.6%
23X | 18 | 498 | 0 | 495 | 3 | 495 | 3 | 107 | 495 | 3 | 99.4% | 99.4% | 99.4%
10X | 27 | 36 | 0 | 36 | 0 | 36 | 0 | 0 | 36 | 0 | 100% | 100% | 100%
14X | 14 | 151 | 0 | 130 | 21 | 130 | 21 | 22 | 129 | 22 | 86.1% | 86.1% | 85.4%
31X | 10 | 14 | 0 | 14 | 0 | 14 | 0 | 4 | 14 | 0 | 100% | 100% | 100%
24X | 17 | 45 | 0 | 45 | 0 | 45 | 0 | 6 | 45 | 0 | 100% | 100% | 100%
11X | 11 | 61 | 0 | 55 | 6 | 55 | 6 | 20 | 55 | 6 | 90.2% | 90.2% | 90.2%
13X | 13 | 172 | 0 | 161 | 11 | 161 | 11 | 9 | 161 | 11 | 93.6% | 93.6% | 93.6%
29X | 29 | 50 | 0 | 47 | 3 | 47 | 3 | 8 | 47 | 3 | 94.0% | 94.0% | 94.0%
TOTALS |  | 7205 | 0 | 7132 | 73 | 7132 | 73 | 1337 | 7131 | 74 | 99% | 99% | 99%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
15X | Wash Tower | 62 | 0 | 10 | 52 | 10 | 52 | 10 | 10 | 52 | 16.1% | 16.1% | 16.1%
01X | 1 | 2144 | 0 | 226 | 1918 | 226 | 1918 | 146 | 226 | 1918 | 10.5% | 10.5% | 10.5%
05X | 2 | 159 | 0 | 4 | 155 | 4 | 155 | 0 | 4 | 155 | 2.5% | 2.5% | 2.5%
12X | 12 | 318 | 0 | 16 | 302 | 16 | 302 | 8 | 16 | 302 | 5.0% | 5.0% | 5.0%
02X | 8 | 106 | 0 | 0 | 106 | 0 | 106 | 0 | 0 | 106 | 0% | 0.0% | 0.0%
04X | 7 | 52 | 0 | 0 | 52 | 0 | 52 | 0 | 0 | 52 | 0% | 0.0% | 0.0%
09X | 28 | 40 | 0 | 0 | 40 | 0 | 40 | 0 | 0 | 40 | 0% | 0.0% | 0.0%
11X | 11 | 251 | 0 | 15 | 236 | 15 | 236 | 6 | 15 | 236 | 6.0% | 6.0% | 6.0%
08X | 20 | 30 | 0 | 0 | 30 | 0 | 30 | 0 | 0 | 30 | 0% | 0.0% | 0.0%
17X | 5 | 315 | 0 | 10 | 305 | 10 | 305 | 7 | 10 | 305 | 3.2% | 3.2% | 3.2%
20X | 23 | 44 | 0 | 0 | 44 | 0 | 44 | 0 | 0 | 44 | 0% | 0.0% | 0.0%
22X | 19 | 319 | 0 | 20 | 299 | 20 | 299 | 13 | 20 | 299 | 6.3% | 6.3% | 6.3%
27X | 6 | 200 | 0 | 17 | 183 | 17 | 183 | 10 | 17 | 183 | 8.5% | 8.5% | 8.5%
28X | 24 | 451 | 0 | 3 | 448 | 3 | 448 | 0 | 3 | 448 | 0.7% | 0.7% | 0.7%
30X | 31 | 469 | 0 | 10 | 459 | 10 | 459 | 1 | 10 | 459 | 2.1% | 2.1% | 2.1%
31X | 10 | 368 | 0 | 13 | 355 | 13 | 355 | 11 | 13 | 355 | 3.5% | 3.5% | 3.5%
13X | 13 | 541 | 0 | 22 | 519 | 22 | 519 | 10 | 22 | 519 | 4.1% | 4.1% | 4.1%
16X | 9 | 180 | 0 | 3 | 177 | 3 | 177 | 2 | 3 | 177 | 1.7% | 1.7% | 1.7%
06X | 26 | 59 | 0 | 0 | 59 | 0 | 59 | 0 | 0 | 59 | 0% | 0.0% | 0.0%
07X | 21 | 25 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 25 | 0% | 0.0% | 0.0%
18X | 15 | 312 | 0 | 5 | 307 | 5 | 307 | 4 | 5 | 307 | 1.6% | 1.6% | 1.6%
19X | 4 | 230 | 0 | 17 | 213 | 17 | 213 | 12 | 17 | 213 | 7.4% | 7.4% | 7.4%
23X | 18 | 434 | 0 | 10 | 424 | 10 | 424 | 7 | 10 | 424 | 2.3% | 2.3% | 2.3%
24X | 17 | 181 | 0 | 17 | 164 | 17 | 164 | 14 | 17 | 164 | 9.4% | 9.4% | 9.4%
21X | 22 | 142 | 0 | 0 | 142 | 0 | 142 | 0 | 0 | 142 | 0% | 0.0% | 0.0%
26X | 25 | 74 | 0 | 0 | 74 | 0 | 74 | 0 | 0 | 74 | 0% | 0.0% | 0.0%
03X | 16 | 10 | 0 | 2 | 8 | 2 | 8 | 0 | 2 | 8 | 20.0% | 20.0% | 20.0%
10X | 27 | 74 | 0 | 0 | 74 | 0 | 74 | 0 | 0 | 74 | 0% | 0.0% | 0.0%
14X | 14 | 83 | 0 | 5 | 78 | 5 | 78 | 5 | 5 | 78 | 6.0% | 6.0% | 6.0%
29X | 29 | 181 | 0 | 2 | 179 | 2 | 179 | 0 | 2 | 179 | 1.1% | 1.1% | 1.1%
TOTALS |  | 7854 | 0 | 427 | 7427 | 427 | 7427 | 266 | 427 | 7427 | 5% | 5% | 5%

## Spool Location
Not Workable
Workable
Issued
Pulled
Welded Out
Shipped to Coating
Delivered

## Shorts by Scope
| 15059 Spools | 7559 Workable | 15059 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0
Not on Line List

## Purchased by Scope
| 15059 Spools | 7559 Workable | 15059 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0

## No Material by Scope
| 15059 Spools | 7559 Workable | 15059 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 0

## Spools by Scope
| 15059 Spools | 7559 Workable | 15059 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Pipe | 0 | 0 | 0
Supports | 0 | 0 | 0
Issued |  |  |  | 15059
Issued (Missing Items) |  |  |  | 0
Workable (Not Issued) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 0
Discrepancies |  |  |  | 0
TOTAL |  |  |  | 15059

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)
MK-02002X-8675-001A
MK-02018X-5447-001A
MK-02005X-7107-001ARB