## PRINTOUT
MARATHON: 6973 |  | 1773 Spools |  |  | 1773 Workable |  |  | 1773 Issued
SPOOLS BY SCOPE | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
SPOOLS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Pipe | [5 empty] | Supports
Supports | [5 empty] | TOTAL
Issued
Issued (Missing Items) | [5 empty] | Pipe
Workable (Not Issued)
On Hold (No Shorts)
Discrepancies | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
TOTAL | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Valves
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | Flanges
ITEMS | Performance | Client | Other | TOTAL |  | Fittings
Valves | [5 empty] | Supports
Flanges | [5 empty] | TOTAL
Fittings
Supports | [5 empty] | Pipe
TOTAL
Pipe | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Not on Line List | [5 empty] | Purchased
6973 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
70 | 1 | 146 | 0 | 146 | 0 | 146 | 0 | 141 | 146 | 0 | 100% | 100% | 100%
40 | 2 | 141 | 0 | 141 | 0 | 141 | 0 | 141 | 141 | 0 | 100% | 100% | 100%
30 | 3 | 194 | 0 | 194 | 0 | 194 | 0 | 185 | 194 | 0 | 100% | 100% | 100%
80 | 4 | 175 | 0 | 175 | 0 | 175 | 0 | 158 | 175 | 0 | 100% | 100% | 100%
10 | 5 | 351 | 0 | 351 | 0 | 351 | 0 | 293 | 351 | 0 | 100% | 100% | 100%
60 | 6 | 448 | 0 | 448 | 0 | 448 | 0 | 448 | 448 | 0 | 100% | 100% | 100%
20 | 7 | 271 | 0 | 271 | 0 | 271 | 0 | 103 | 271 | 0 | 100% | 100% | 100%
50 | 8 | 25 | 0 | 25 | 0 | 25 | 0 | 23 | 25 | 0 | 100% | 100% | 100%
MT | MT | 22 | 0 | 22 | 0 | 22 | 0 | 0 | 21 | 1 | 100% | 100% | 95.5%
TOTALS |  | 1773 | 0 | 1773 | 0 | 1773 | 0 | 1492 | 1772 | 1 | 100% | 100% | 100%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
70 | 1 | 146 | 0 | 146 | 0 | 146 | 0 | 141 | 146 | 0 | 100% | 100% | 100%
40 | 2 | 141 | 0 | 141 | 0 | 141 | 0 | 141 | 141 | 0 | 100% | 100% | 100%
30 | 3 | 194 | 0 | 194 | 0 | 194 | 0 | 185 | 194 | 0 | 100% | 100% | 100%
80 | 4 | 175 | 0 | 175 | 0 | 175 | 0 | 158 | 175 | 0 | 100% | 100% | 100%
10 | 5 | 351 | 0 | 351 | 0 | 351 | 0 | 293 | 351 | 0 | 100% | 100% | 100%
60 | 6 | 448 | 0 | 448 | 0 | 448 | 0 | 448 | 448 | 0 | 100% | 100% | 100%
20 | 7 | 271 | 0 | 271 | 0 | 271 | 0 | 103 | 271 | 0 | 100% | 100% | 100%
50 | 8 | 25 | 0 | 25 | 0 | 25 | 0 | 23 | 25 | 0 | 100% | 100% | 100%
MT | MT | 22 | 0 | 22 | 0 | 22 | 0 | 0 | 21 | 1 | 100% | 100% | 95.5%
TOTALS |  | 1773 | 0 | 1773 | 0 | 1773 | 0 | 1492 | 1772 | 1 | 100% | 100% | 100%

## Areas Summary (By Material)
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
70 | 1 | 128 | 0 | 128 | 0 | 128 | 0 | 123 | 128 | 0 | 100% | 100% | 100%
40 | 2 | 140 | 0 | 140 | 0 | 140 | 0 | 140 | 140 | 0 | 100% | 100% | 100%
30 | 3 | 169 | 0 | 169 | 0 | 169 | 0 | 169 | 169 | 0 | 100% | 100% | 100%
80 | 4 | 134 | 0 | 134 | 0 | 134 | 0 | 132 | 134 | 0 | 100% | 100% | 100%
10 | 5 | 286 | 0 | 286 | 0 | 286 | 0 | 284 | 286 | 0 | 100% | 100% | 100%
50 | 8 | 25 | 0 | 25 | 0 | 25 | 0 | 23 | 25 | 0 | 100% | 100% | 100%
60 | 6 | 448 | 0 | 448 | 0 | 448 | 0 | 448 | 448 | 0 | 100% | 100% | 100%
20 | 7 | 82 | 0 | 82 | 0 | 82 | 0 | 80 | 82 | 0 | 100% | 100% | 100%
TOTALS |  | 1412 | 0 | 1412 | 0 | 1412 | 0 | 1399 | 1412 | 0 | 100% | 100% | 100%
SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
80 | 4 | 41 | 0 | 41 | 0 | 41 | 0 | 26 | 41 | 0 | 100% | 100% | 100%
30 | 3 | 25 | 0 | 25 | 0 | 25 | 0 | 16 | 25 | 0 | 100% | 100% | 100%
70 | 1 | 18 | 0 | 18 | 0 | 18 | 0 | 18 | 18 | 0 | 100% | 100% | 100%
20 | 7 | 176 | 0 | 176 | 0 | 176 | 0 | 10 | 176 | 0 | 100% | 100% | 100%
10 | 5 | 65 | 0 | 65 | 0 | 65 | 0 | 9 | 65 | 0 | 100% | 100% | 100%
40 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 100% | 100% | 100%
MT | MT | 22 | 0 | 22 | 0 | 22 | 0 | 0 | 21 | 1 | 100% | 100% | 95.5%
TOTALS |  | 348 | 0 | 348 | 0 | 348 | 0 | 80 | 347 | 1 | 100% | 100% | 100%
Chrome Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
20 | 7 | 13 | 0 | 13 | 0 | 13 | 0 | 13 | 13 | 0 | 100% | 100% | 100%
TOTALS |  | 13 | 0 | 13 | 0 | 13 | 0 | 13 | 13 | 0 | 100% | 100% | 100%

## Spool Location
Not Workable
Workable
Issued
Pulled
Welded Out
Shipped to Coating
Delivered

## Shorts by Scope
| 1773 Spools | 1773 Workable | 1773 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0
Not on Line List

## Purchased by Scope
| 1773 Spools | 1773 Workable | 1773 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0

## No Material by Scope
| 1773 Spools | 1773 Workable | 1773 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 0

## Spools by Scope
| 1773 Spools | 1773 Workable | 1773 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Pipe | 0 | 0 | 0
Supports | 0 | 0 | 0
Issued |  |  |  | 1773
Issued (Missing Items) |  |  |  | 0
Workable (Not Issued) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 0
Discrepancies |  |  |  | 0
TOTAL |  |  |  | 1773

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)
MK-000-WS-9308-21-1V
MK-000-WS-9308-22-1V
MK-000-WS-9308-22-1VV
MK-000-WS-9361-21-1V
MK-000-WS-9361-21-1VV
MK-000-WS-9362-21-1V
MK-000-WS-9362-21-1VV
MK-000-WS-9295-21-2V
MK-000-WS-9295-21-2VV
MK-000-WS-9361-20-1V
MK-000-WS-9361-20-1VV
MK-000-P-9337-70-1A
MK-000-P-20062-61-4
MK-000-NI-9555-22-2
MK-000-NI-9555-22-3
MK-000-P-9048-10-4
MK-000-SC-9657-21-2
MK-000-H-20064-60-2
MK-000-FW-32054-41-1A
MK-000-FW-32057-41-1A
MK-000-S5-9709-30-3