## PRINTOUT
CP CHEM: 7052 |  | 1019 Spools |  | 542 Workable |  | 511 Issued |  | 3189 Workable Man Hours
SPOOLS BY SCOPE | [5 empty] | Workable Man Hours (By Material)
SPOOLS | Performance | Client | Other | TOTAL |  |  |  | Carbon | Stainless | TOTAL
Valves | [5 empty] | Workable Man Hours |  | 1080 | 2109 | 3189
Flanges
Fittings | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
Pipe | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Supports | [5 empty] | Valves
Issued | [5 empty] | Flanges
Issued (Missing Items) | [5 empty] | Fittings
Workable (Not Issued) | [5 empty] | Supports
On Hold (No Shorts) | [5 empty] | TOTAL
Discrepancies
TOTAL | [5 empty] | Pipe
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Supports | [5 empty] | Supports
TOTAL | [5 empty] | TOTAL
Pipe | [5 empty] | Pipe
Not on Line List | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Purchased
7052 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J14 | 2 | 123 | 3 | 0 | 123 | 0 | 123 | 0 | 0 | 123 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 8 | 36 | 9 | 33 | 12 | 27 | 0 | 45 | 80.0% | 73.3% | 0.0%
J32 | 4 | 242 | 110 | 126 | 116 | 88 | 154 | 2 | 0 | 242 | 52.1% | 36.4% | 0.0%
J06 | 5 | 83 | 51 | 32 | 51 | 13 | 70 | 3 | 0 | 83 | 38.6% | 15.7% | 0.0%
J07 | 5 | 94 | 44 | 50 | 44 | 16 | 78 | 3 | 0 | 94 | 53.2% | 17.0% | 0.0%
J21 | 6 | 42 | 0 | 37 | 5 | 24 | 18 | 7 | 0 | 42 | 88.1% | 57.1% | 0.0%
J20 | 6 | 21 | 4 | 11 | 10 | 10 | 11 | 2 | 0 | 21 | 52.4% | 47.6% | 0.0%
J04 | 7 | 156 | 22 | 131 | 25 | 33 | 123 | 0 | 0 | 156 | 84.0% | 21.2% | 0.0%
J05 | 7 | 42 | 0 | 38 | 4 | 18 | 24 | 0 | 0 | 42 | 90.5% | 42.9% | 0.0%
J25 | 8 | 39 | 24 | 2 | 37 | 0 | 39 | 0 | 0 | 39 | 5.1% | 0.0% | 0.0%
J10 | 8 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 2 | 7 | 2 | 4 | 5 | 1 | 0 | 9 | 77.8% | 44.4% | 0.0%
J13 | 11 | 22 | 6 | 16 | 6 | 12 | 10 | 0 | 0 | 22 | 72.7% | 54.5% | 0.0%
J18 | 11 | 25 | 2 | 23 | 2 | 19 | 6 | 3 | 0 | 25 | 92.0% | 76.0% | 0.0%
J01 | 12 | 53 | 9 | 27 | 26 | 15 | 38 | 6 | 0 | 53 | 50.9% | 28.3% | 0.0%
- | #N/A | 7 | 0 | 3 | 4 | 0 | 7 | 0 | 0 | 7 | 42.9% | 0.0% | 0.0%
TOTALS |  | 1019 | 295 | 586 | 433 | 288 | 731 | 57 | 0 | 1019 | 53% | 28% | 0%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J14 | 2 | 123 | 3 | 0 | 123 | 0 | 123 | 0 | 0 | 123 | 0% | 0.0% | 0.0%
J23 | 3 | 45 | 8 | 36 | 9 | 33 | 12 | 27 | 0 | 45 | 80.0% | 73.3% | 0.0%
J32 | 4 | 242 | 110 | 126 | 116 | 88 | 154 | 2 | 0 | 242 | 52.1% | 36.4% | 0.0%
J06 | 5 | 83 | 51 | 32 | 51 | 13 | 70 | 3 | 0 | 83 | 38.6% | 15.7% | 0.0%
J07 | 5 | 94 | 44 | 50 | 44 | 16 | 78 | 3 | 0 | 94 | 53.2% | 17.0% | 0.0%
J21 | 6 | 42 | 0 | 37 | 5 | 24 | 18 | 7 | 0 | 42 | 88.1% | 57.1% | 0.0%
J20 | 6 | 21 | 4 | 11 | 10 | 10 | 11 | 2 | 0 | 21 | 52.4% | 47.6% | 0.0%
J04 | 7 | 156 | 22 | 131 | 25 | 33 | 123 | 0 | 0 | 156 | 84.0% | 21.2% | 0.0%
J05 | 7 | 42 | 0 | 38 | 4 | 18 | 24 | 0 | 0 | 42 | 90.5% | 42.9% | 0.0%
J25 | 8 | 39 | 24 | 2 | 37 | 0 | 39 | 0 | 0 | 39 | 5.1% | 0.0% | 0.0%
J10 | 8 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J03 | 10 | 9 | 2 | 7 | 2 | 4 | 5 | 1 | 0 | 9 | 77.8% | 44.4% | 0.0%
J13 | 11 | 22 | 6 | 16 | 6 | 12 | 10 | 0 | 0 | 22 | 72.7% | 54.5% | 0.0%
J18 | 11 | 25 | 2 | 23 | 2 | 19 | 6 | 3 | 0 | 25 | 92.0% | 76.0% | 0.0%
J01 | 12 | 53 | 9 | 27 | 26 | 15 | 38 | 6 | 0 | 53 | 50.9% | 28.3% | 0.0%
- | #N/A | 7 | 0 | 3 | 4 | 0 | 7 | 0 | 0 | 7 | 42.9% | 0.0% | 0.0%
TOTALS |  | 1019 | 295 | 542 | 477 | 288 | 731 | 57 | 0 | 1019 | 53% | 28% | 0%

## Areas Summary (By Material)
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J04 | 7 | 152 | 18 | 131 | 21 | 33 | 119 | 0 | 0 | 152 | 86.2% | 21.7% | 0.0%
J05 | 7 | 42 | 0 | 38 | 4 | 18 | 24 | 0 | 0 | 42 | 90.5% | 42.9% | 0.0%
J18 | 11 | 13 | 0 | 13 | 0 | 10 | 3 | 0 | 0 | 13 | 100% | 76.9% | 0.0%
J13 | 11 | 12 | 4 | 8 | 4 | 6 | 6 | 0 | 0 | 12 | 66.7% | 50.0% | 0.0%
J32 | 4 | 38 | 6 | 32 | 6 | 29 | 9 | 0 | 0 | 38 | 84.2% | 76.3% | 0.0%
TOTALS |  | 257 | 28 | 222 | 35 | 96 | 161 | 0 | 0 | 257 | 86% | 37% | 0%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J13 | 11 | 10 | 2 | 8 | 2 | 6 | 4 | 0 | 0 | 10 | 80.0% | 60.0% | 0.0%
J18 | 11 | 12 | 2 | 10 | 2 | 9 | 3 | 3 | 0 | 12 | 83.3% | 75.0% | 0.0%
J01 | 12 | 28 | 3 | 23 | 5 | 13 | 15 | 4 | 0 | 28 | 82.1% | 46.4% | 0.0%
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J03 | 10 | 9 | 2 | 7 | 2 | 4 | 5 | 1 | 0 | 9 | 77.8% | 44.4% | 0.0%
J23 | 3 | 45 | 8 | 36 | 9 | 33 | 12 | 27 | 0 | 45 | 80.0% | 73.3% | 0.0%
- | #N/A | 7 | 0 | 3 | 4 | 0 | 7 | 0 | 0 | 7 | 42.9% | 0.0% | 0.0%
J32 | 4 | 204 | 104 | 94 | 110 | 59 | 145 | 2 | 0 | 204 | 46.1% | 28.9% | 0.0%
J06 | 5 | 73 | 51 | 22 | 51 | 13 | 60 | 3 | 0 | 73 | 30.1% | 17.8% | 0.0%
J07 | 5 | 66 | 44 | 22 | 44 | 16 | 50 | 3 | 0 | 66 | 33.3% | 24.2% | 0.0%
J21 | 6 | 20 | 0 | 20 | 0 | 16 | 4 | 7 | 0 | 20 | 100% | 80.0% | 0.0%
J20 | 6 | 11 | 4 | 3 | 8 | 2 | 9 | 1 | 0 | 11 | 27.3% | 18.2% | 0.0%
J04 | 7 | 4 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 4 | 0% | 0.0% | 0.0%
J10 | 8 | 10 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0% | 0.0% | 0.0%
J25 | 8 | 4 | 2 | 2 | 2 | 0 | 4 | 0 | 0 | 4 | 50.0% | 0.0% | 0.0%
TOTALS |  | 506 | 236 | 253 | 253 | 174 | 332 | 54 | 0 | 506 | 50% | 34% | 0%
A333 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 4 | 50.0% | 50.0% | 0.0%
J20 | 6 | 10 | 0 | 8 | 2 | 8 | 2 | 1 | 0 | 10 | 80.0% | 80.0% | 0.0%
J21 | 6 | 12 | 0 | 8 | 4 | 8 | 4 | 0 | 0 | 12 | 66.7% | 66.7% | 0.0%
TOTALS |  | 26 | 0 | 18 | 8 | 18 | 8 | 3 | 0 | 26 | 69% | 69% | 0%
ALUMINUM Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 122 | 2 | 0 | 122 | 0 | 122 | 0 | 0 | 122 | 0% | 0.0% | 0.0%
J01 | 12 | 17 | 6 | 0 | 17 | 0 | 17 | 0 | 0 | 17 | 0% | 0.0% | 0.0%
J19 | 9 | 3 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0% | 0.0% | 0.0%
J25 | 8 | 35 | 22 | 0 | 35 | 0 | 35 | 0 | 0 | 35 | 0% | 0.0% | 0.0%
TOTALS |  | 177 | 30 | 0 | 177 | 0 | 177 | 0 | 0 | 177 | 0% | 0% | 0%
304/304L SS CRYO Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 2 | 2 | 0 | 4 | 0 | 0 | 4 | 50.0% | 0.0% | 0.0%
J21 | 6 | 10 | 0 | 9 | 1 | 0 | 10 | 0 | 0 | 10 | 90.0% | 0.0% | 0.0%
TOTALS |  | 14 | 0 | 11 | 3 | 0 | 14 | 0 | 0 | 14 | 79% | 0% | 0%
Galv. Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J06 | 5 | 10 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 100% | 0.0% | 0.0%
J07 | 5 | 28 | 0 | 28 | 0 | 0 | 28 | 0 | 0 | 28 | 100% | 0.0% | 0.0%
TOTALS |  | 38 | 0 | 38 | 0 | 0 | 38 | 0 | 0 | 38 | 100% | 0% | 0%
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0% | 0.0% | 0.0%
TOTALS |  | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0% | 0% | 0%

## Spool Location
Not Workable | 182
Workable | 44
Issued | 74
Pulled | 149
Welded Out | 231
Shipped to Coating | 57
Ready To Deliver | 0
Delivered | 0
On Hold | 282

## Shorts by Scope
| 1019 Spools | 542 Workable | 511 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 41 | 0
Flanges | 332 | 0 | 0
Fittings | 27 | 0 | 0
Supports | 1 | 0 | 0
TOTAL
Pipe | 2646.7 | 0 | 0
Not on Line List

## Purchased by Scope
| 1019 Spools | 542 Workable | 511 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 15 | 0
Flanges | 322 | 0 | 0
Fittings | 9 | 0 | 0
Supports | 1 | 0 | 0
TOTAL
Pipe | 693.5 | 0 | 0

## No Material by Scope
| 1019 Spools | 542 Workable | 511 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 26 | 0
Flanges | 10 | 0 | 0
Fittings | 18 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 1953.2 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 11

## Spools by Scope
| 1019 Spools | 542 Workable | 511 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 28 | 0
Flanges | 231 | 0 | 0
Fittings | 91 | 0 | 0
Pipe | 11 | 0 | 0
Supports | 0 | 0 | 0
Issued |  |  |  | 511
Issued (Missing Items) |  |  |  | 44
Workable (Not Issued) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 103
Discrepancies |  |  |  | 0
TOTAL |  |  |  | 1019

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)