## generatedBy_react-csv (88)
spool | piecemark | material | issued | pulled | scope | workable | priority | area | iso | detailing | checking | shop | on_hold | multiplier | jobnum | client | status | items | shorts | schedules | classes | manhours | welds_counted | welds | weldout | rts | rtsc | stc | delivered | i_p | missing_valve_only | p_w | w_rtsc | rtsc_stc | w_stc
2020-01-01 | PK101XA-C-1511.01-1 | 304/304L SS | 2020-09-01 | 2020-09-02 | Other | TRUE | 7 | J04 | 1 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 52.248 | 22 | 22 | [5 empty] | 1
2020-02-01 | PK101XA-C-1513.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 2 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 52.248 | 22 | 22
2020-03-01 | PK101XA-C-1515.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 3 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 52.248 | 22 | 22
2020-04-01 | PK101XA-C-1517.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 4 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 52.248 | 22 | 22
2020-05-01 | PK101XA-C-1519.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 5 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 52.248 | 22 | 22
2020-06-01 | PK101XA-C-1525.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 6 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 44.492 | 19 | 19
2020-07-01 | PK101XA-C-1606E.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 7 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 44.492 | 19 | 19
2020-08-01 | PK101XA-C-1611.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 8 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 52.248 | 22 | 22
2020-09-01 | PK101XA-C-1613.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 9 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 52.248 | 22 | 22
2020-10-01 | PK101XA-C-1615.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 10 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 52.248 | 22 | 22
2020-11-01 | PK101XA-C-1617.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 11 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 52.248 | 22 | 22
2020-12-01 | PK101XA-C-1619.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 12 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 52.248 | 22 | 22
13-1 | PK101XA-C-97624.01-1 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J05 | 13 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S |  | 10.64 | 4 | 4 | [5 empty] | 5
13-2 | PK101XA-C-97624.01-2 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 13 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object] |  | 80S,80S,80S |  | 5.32 | 2 | 2
14-1 | PK101XA-C-97624.02-1 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J05 | 14 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 26.32 | 10 | 10 | [5 empty] | 5
14-2 | PK101XA-C-97624.02-2 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 14 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object] |  |  |  | 0 | 0 | 0
14-3 | PK101XA-C-97624.02-3 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 14 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object] |  |  |  | 0 | 0 | 0
15-1 | PK101XA-C-97624.03-1 | 304/304L SS |  |  | Other |  | 7 | J05 | 15 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS | 40S,80S,80S,80S,80S,80S,80S,40Sx80S,80S |  | 26.348 | 10 | 10
16-1 | PK101XA-C-102338.01-1 | 304/304L SS |  |  | Other |  | 7 | J05 | 16 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS | 40Sx80S,40S,80S,40S,80S,80S |  | 16.016 | 6 | 6
16-2 | PK101XA-C-102338.01-2 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J05 | 16 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | 80S,80S,80S |  | 5.32 | 2 | 2 | [5 empty] | 5
17-1 | PK101XA-C-102338.02-1 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J05 | 17 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S,80S,80S |  | 26.32 | 10 | 10 | [5 empty] | 5
17-2 | PK101XA-C-102338.02-2 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 17 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object] |  |  |  | 0 | 0 | 0
17-3 | PK101XA-C-102338.02-3 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 17 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object] |  |  |  | 0 | 0 | 0
18-1 | PK101XA-C-102338.03-1 | 304/304L SS |  |  | Other |  | 7 | J05 | 18 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS | 80S,80S,80S,40S,80S,80S,40Sx80S,80S,80S |  | 26.348 | 10 | 10
19-1 | PK101XA-C-102339.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J05 | 19 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.38 | 1 | 1 | [5 empty] | 7
20-1 | PK101XA-C-102340.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J05 | 20 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.38 | 1 | 1 | [5 empty] | 7
21-1 | PK101XA-CCW-1502.01-1 | CS |  |  | Other |  | 11 | J13 | 21 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] |  | STD |  | 0 | 0 | 0
21-2 | PK101XA-CCW-1502.01-2 | CS |  |  | Other |  | 11 | J13 | 21 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,XS |  | 7.408 | 3 | 3
22-1 | PK101XA-CCW-1504.01-1 | CS |  |  | Other |  | 11 | J18 | 22 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] |  | STD |  | 0 | 0 | 0
22-2 | PK101XA-CCW-1504.01-2 | CS |  |  | Other |  | 11 | J18 | 22 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,STD,STD,STD |  | 7.408 | 3 | 3
23-1 | PK101XA-CCW-1513.01-1 | CS |  |  | Other |  | 12 | J01 | 23 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FLANGES | XS,XS,STD,STD,XS,STD | 3000 | 12.816 | 6 | 6
23-2 | PK101XA-CCW-1513.01-2 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 12 | J01 | 23 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 2.208 | 2 | 2 | 2020-08-26 |  |  |  |  | 2 |  | 7
23-3 | PK101XA-CCW-1513.01-3 | CS | 2020-08-13 | 2020-08-28 | Other | TRUE | 12 | J01 | 23 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD |  | 24.576 | 6 | 6 | 2020-09-01 |  |  |  |  | 15 |  | 4
24-1 | PK101XA-CCW-1514.01-1 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 12 | J01 | 24 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-28 |  |  |  |  | 2 |  | 9
24-2 | PK101XA-CCW-1514.01-2 | CS |  |  | Other |  | 12 | J01 | 24 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FLANGES | STD,XS,STD,STD,XS,XS | 3000 | 0 | 0 | 0
24-3 | PK101XA-CCW-1514.01-3 | CS | 2020-08-13 | 2020-08-26 | Other | TRUE | 12 | J01 | 24 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD |  | 0 | 0 | 0 | 2020-08-28 |  |  |  |  | 13 |  | 2
25-1 | PK101XA-CCW-3888.01-1 | CS | 2020-09-01 |  | Other | TRUE | 12 | J01 | 25 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 7.552 | 8 | 8
25-2 | PK101XA-CCW-3888.01-2 | CS | 2020-09-01 |  | Other | TRUE | 12 | J01 | 25 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 13.216 | 14 | 14
25-3 | PK101XA-CCW-3888.01-3 | CS | 2020-08-06 | 2020-08-17 | Other | TRUE | 12 | J01 | 25 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 11 |  | 0 | 3 | 4 | 7
26-1 | PK101XA-CCW-3888A.01-1 | CS | 2020-09-01 |  | Other | TRUE | 12 | J01 | 26 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 13.216 | 14 | 14
26-2 | PK101XA-CCW-3888A.01-2 | CS | 2020-09-01 |  | Other | TRUE | 12 | J01 | 26 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 7.552 | 8 | 8
26-3 | PK101XA-CCW-3888A.01-3 | CS | 2020-08-06 | 2020-08-17 | Other | TRUE | 12 | J01 | 26 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 11 |  | 0 | 3 | 4 | 7
27-1 | PK101XA-CW-1539.01-1 | CS | 2020-08-13 | 2020-08-24 | Other | TRUE | 11 | J18 | 27 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD,STD,STD,STD,STD,STD,STD,STD | 30003000 | 52.24 | 17 | 17 | 2020-08-31 |  |  |  |  | 11 |  | 7
27-2 | PK101XA-CW-1539.01-2 | CS | 2020-08-05 | 2020-08-13 | Other | TRUE | 11 | J18 | 27 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  | STD |  | 0 | 0 | 0 | 2020-08-20 |  |  |  |  | 8 |  | 7
28-1 | PK101XA-CW-1539.02-1 | CS | 2020-08-05 | 2020-08-24 | Other | TRUE | 11 | J18 | 28 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD |  | 6.72 | 3 | 3 | 2020-08-25 |  |  |  |  | 19 |  | 1
29-1 | PK101XA-CW-1540.01-1 | CS | 2020-08-17 | 2020-08-31 | Other | TRUE | 11 | J18 | 29 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,XS,STD,STD,STD,STD | 300030003000 | 61.248 | 16 | 16 | [5 empty] | 14
30-1 | PK101XA-CW-1540.02-1 | CS | 2020-08-13 | 2020-08-24 | Other | TRUE | 11 | J18 | 30 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD |  | 19.376 | 5 | 5 | 2020-08-26 |  |  |  |  | 11 |  | 2
30-2 | PK101XA-CW-1540.02-2 | CS | 2020-08-05 | 2020-08-17 | Other | TRUE | 11 | J18 | 30 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  | STD |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 12 |  | 0 | 3 | 4 | 7
31-1 | PK101XA-CW-1557.01-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 11 | J18 | 31 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1 | 2020-08-12 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 1 | 8 | 4 | 12
32-1 | PK101XA-CW-1558.01-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 11 | J18 | 32 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1 | 2020-08-13 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 2 | 7 | 4 | 11
33-1 | PK101XA-CW-100420.01-1 | CS | 2020-08-13 | 2020-08-24 | Other | TRUE | 11 | J13 | 33 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD,STD,STD,STD,STD,STD,STD,STD | 30003000 | 50 | 16 | 16 | [5 empty] | 11
34-1 | PK101XA-CW-100420.02-1 | CS | 2020-08-05 | 2020-08-24 | Other | TRUE | 11 | J13 | 34 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD |  | 6.72 | 3 | 3 | 2020-08-25 |  |  |  |  | 19 |  | 1
35-1 | PK101XA-CW-100421.01-1 | CS | 2020-08-13 | 2020-08-24 | Other | TRUE | 11 | J13 | 35 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD,STD,STD | 30003000 | 56 | 13 | 13 | [5 empty] | 11
36-1 | PK101XA-CW-100421.02-1 | CS | 2020-08-13 | 2020-08-24 | Other | TRUE | 11 | J13 | 36 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD |  | 19.376 | 5 | 5 | 2020-08-25 |  |  |  |  | 11 |  | 1
43-1 | PK101XA-FW-150001.01-1 | CS | 2020-08-06 | 2020-08-12 | Other | TRUE | 1 | J30 | 43 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object] |  | STD,STD |  | 0 | 0 | 0 | 2020-08-12 |  | 2020-08-20 | 2020-08-24 |  | 6 |  | 0 | 8 | 4 | 12
44-1 | PK101XA-P-1504.01-1 | 304/304L SS | 2020-08-17 | 2020-08-18 | Other | TRUE | 11 | J18 | 44 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S,40S,40S,40S | 300030003000 | 78.876 | 14 | 14 | 2020-08-25 |  |  |  |  | 1 |  | 7
44-2 | PK101XA-P-1504.01-2 | 304/304L SS | 2020-08-11 | 2020-08-11 | Other | TRUE | 11 | J18 | 44 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  | 40S |  | 0 | 0 | 0 | 2020-08-12 |  |  |  |  | 0 |  | 1
45-1 | PK101XA-P-1504.02-1 | 304/304L SS | 2020-08-04 | 2020-08-06 | Other | TRUE | 11 | J18 | 45 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 10.472 | 2 | 2 | 2020-08-11 |  |  |  |  | 2 |  | 5
46-1 | PK101XA-P-1508.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 11 | J18 | 46 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,80S,40S | 30003000 | 31.976 | 8 | 8 | [5 empty] | 7
47-1 | PK101XA-P-1508.02-1 | 304/304L SS | 2020-08-17 | 2020-08-18 | Other | TRUE | 11 | J18 | 47 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 0 | 0 | 0 | 2020-08-19 |  |  |  |  | 1 |  | 1
48-1 | PK101XA-P-1508.03-1 | 304/304L SS | 2020-08-11 | 2020-08-11 | Other | TRUE | 11 | J18 | 48 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 12.544 | 2 | 2 | 2020-08-12 |  |  |  |  | 0 |  | 1
48-2 | PK101XA-P-1508.03-2 | 304/304L SS | 2020-08-17 | 2020-08-18 | Other | TRUE | 11 | J18 | 48 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S |  | 25.088 | 4 | 4 | 2020-08-20 |  |  |  |  | 1 |  | 2
48-3 | PK101XA-P-1508.03-3 | 304/304L SS | 2020-08-13 | 2020-08-17 | Other | TRUE | 11 | J18 | 48 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S |  | 31.36 | 5 | 5 | 2020-08-19 |  |  |  |  | 4 |  | 2
48-4 | PK101XA-P-1508.03-4 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 11 | J18 | 48 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
49-1 | PK101XA-P-1508.04-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 11 | J18 | 49 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S,40S |  | 32.704 | 6 | 6
49-2 | PK101XA-P-1508.04-2 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 11 | J18 | 49 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object] |  |  |  | 0 | 0 | 0
50-1 | PK101XA-P-1508.05-1 | 304/304L SS | 2020-08-17 | 2020-08-18 | Other | TRUE | 11 | J18 | 50 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,80S | 30003000 | 29.568 | 8 | 8 | 2020-08-20 |  |  |  |  | 1 |  | 2
51-1 | PK101XA-P-1508.06-1 | 304/304L SS | 2020-08-17 | 2020-08-18 | Other | TRUE | 11 | J18 | 51 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,80S,40S,40S,40S,40S | 3000 | 44.632 | 10 | 10 | 2020-08-26 |  |  |  |  | 1 |  | 8
52-1 | PK101XA-P-1603.01-1 | 304/304L SS | 2020-08-17 | 2020-08-18 | Other | TRUE | 11 | J13 | 52 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S,40S,40S,40S | 30003000 | 68.852 | 12 | 12 | 2020-08-25 |  |  |  |  | 1 |  | 7
52-2 | PK101XA-P-1603.01-2 | 304/304L SS | 2020-08-11 | 2020-08-11 | Other | TRUE | 11 | J13 | 52 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  | 40S |  | 0 | 0 | 0 | 2020-08-12 |  |  |  |  | 0 |  | 1
53-1 | PK101XA-P-1603.02-1 | 304/304L SS | 2020-08-04 | 2020-08-06 | Other | TRUE | 11 | J13 | 53 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 10.472 | 2 | 2 | 2020-08-11 |  |  |  |  | 2 |  | 5
54-1 | PK101XA-P-1605.01-1 | 304/304L SS |  |  | Other |  | 11 | J13 | 54 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 25.088 | 4 | 4
55-1 | PK101XA-P-1607.01-1 | 304/304L SS | 2020-08-17 | 2020-08-18 | Other | TRUE | 11 | J13 | 55 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 25.088 | 4 | 4 | 2020-08-19 |  |  |  |  | 1 |  | 1
55-2 | PK101XA-P-1607.01-2 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 11 | J13 | 55 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
56-1 | PK101XA-P-1607.02-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 11 | J13 | 56 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,40S,40S,40S,40S | 30003000 | 24.64 | 8 | 8 | [5 empty] | 7
56-2 | PK101XA-P-1607.02-2 | 304/304L SS | 2020-08-11 |  | Other | TRUE | 11 | J13 | 56 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object] |  |  |  | 0 | 0 | 0
57-1 | PK101XA-P-1607.03-1 | 304/304L SS | 2020-08-17 | 2020-08-18 | Other | TRUE | 11 | J13 | 57 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40S,40S,40S,40S | 3000 | 44.632 | 10 | 10 | 2020-08-25 |  |  |  |  | 1 |  | 7
58-1 | PK101XA-P-1608.01-1 | 304/304L SS |  |  | Other |  | 11 | J13 | 58 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S |  | 16.744 | 3 | 3
59-1 | PK101XA-P-1609.01-1 | 304/304L SS |  |  | Other |  | 11 | J13 | 59 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 40S,40S,40S,40S,40S,10S,10Sx40S |  | 43.82 | 8 | 8
60-1 | PK101XA-P-102037.01-1 | 304/304L SS |  |  | Other |  | 11 | J13 | 60 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 10S,10S,10S,10S,10S |  | 37.072 | 4 | 4
61-1 | PK102XA-C-97624.01-1 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J05 | 61 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 10.64 | 4 | 4 | [5 empty] | 5
61-2 | PK102XA-C-97624.01-2 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 61 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 13.3 | 5 | 5
61-3 | PK102XA-C-97624.01-3 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 61 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 15.96 | 6 | 6
61-4 | PK102XA-C-97624.01-4 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 61 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object] |  | 80S,80S,80S |  | 5.32 | 2 | 2
61-5 | PK102XA-C-97624.01-5 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 61 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 13.3 | 5 | 5
61-6 | PK102XA-C-97624.01-6 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 61 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object] |  | 80S,80S,80S |  | 5.32 | 2 | 2
61-7 | PK102XA-C-97624.01-7 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 61 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 15.624 | 6 | 6
61-8 | PK102XA-C-97624.01-8 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 7 | J05 | 61 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
62-1 | PK102XA-C-100299.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 62 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 20.944 | 8 | 8
62-2 | PK102XA-C-100299.01-2 | 304/304L SS | 2020-08-17 | 2020-08-18 | Other | TRUE | 7 | J05 | 62 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 80S,80S |  | 8.96 | 4 | 4 | 2020-08-18 |  |  |  |  | 1 |  | 0
63-1 | PK102XA-T-400089.01-1 | A333 |  |  | Other |  | 12 | J01 | 63 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS | XS,XS,XS,XS,160 | 3000 | 8.832 | 8 | 8 | [6 empty] | TRUE
63-2 | PK102XA-T-400089.01-2 | A333 |  |  | Other |  | 12 | J01 | 63 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS | XS,XS |  | 5.12 | 4 | 4 | [6 empty] | TRUE
63-3 | PK102XA-T-400089.01-3 | A333 | 2020-08-03 | 2020-08-03 | Other | TRUE | 12 | J01 | 63 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-05 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 2 | 15 | 4 | 19
63-4 | PK102XA-T-400089.01-4 | A333 | 2020-08-03 | 2020-08-03 | Other | TRUE | 12 | J01 | 63 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-05 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 2 | 15 | 4 | 19
64-1 | PK103XA-CS-97376.01-1 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 12 | J01 | 64 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-10 |  |  |  |  | 1 |  | 4
64-2 | PK103XA-CS-97376.01-2 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 12 | J01 | 64 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 4.224 | 4 | 4 | 2020-08-25 |  |  |  |  | 2 |  | 6
65-1 | PK103XA-CW-4494.01-1 | CS |  |  | Other |  | 10 | J03 | 65 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,STD,STD,STD,160,STD,STD | 3000 | 32.688 | 9 | 9
66-1 | PK103XA-CW-4528.01-1 | CS |  |  | Other |  | 10 | J03 | 66 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | STD,STD,XS,STD,STD,STD,160,STD | 3000 | 43.12 | 11 | 11
67-1 | PK103XA-CW-97424.01-1 | CS | 2020-08-13 | 2020-08-28 | Other | TRUE | 10 | J03 | 67 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD |  | 27.216 | 6 | 6 | [5 empty] | 15
68-1 | PK103XA-PL-4396.01-1 | CS | 2020-08-17 | 2020-08-31 | Other | TRUE | 10 | J03 | 68 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,XS,STD,STD,XS,STD,STD | 3000 | 87.952 | 16 | 16 | [5 empty] | 14
68-2 | PK103XA-PL-4396.01-2 | CS | 2020-08-13 | 2020-08-26 | Other | TRUE | 10 | J03 | 68 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | STD,STD,STD |  | 0 | 0 | 0 | 2020-08-31 |  |  |  |  | 13 |  | 5
69-1 | PK103XA-PL-4398.01-1 | CS | 2020-08-11 | 2020-08-20 | Other | TRUE | 10 | J03 | 69 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 8.832 | 8 | 8 | 2020-08-20 |  |  |  |  | 9 |  | 0
69-2 | PK103XA-PL-4398.01-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 10 | J03 | 69 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
70-1 | PK103XA-PL-97368.01-1 | CS | 2020-08-11 | 2020-08-28 | Other | TRUE | 10 | J03 | 70 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,XS,STD,STD,STD,STD,STD |  | 32.048 | 8 | 8 | 2020-09-01 |  |  |  |  | 17 |  | 4
71-1 | PK103XA-PL-97368.02-1 | CS | 2020-08-11 | 2020-08-28 | Other | TRUE | 10 | J03 | 71 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,XS,STD,STD,STD,STD,STD |  | 40.336 | 10 | 10 | [5 empty] | 17
72-1 | PK104XA-CNV-107.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 72 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 35.904 | 4 | 4
72-2 | PK104XA-CNV-107.01-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 72 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 35.904 | 4 | 4
72-3 | PK104XA-CNV-107.01-3 | ALUMINUM |  |  | Other |  | 2 | J14 | 72 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 35.904 | 4 | 4
72-4 | PK104XA-CNV-107.01-4 | ALUMINUM |  |  | Other |  | 2 | J14 | 72 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 35.904 | 4 | 4
73-1 | PK104XA-CNV-107.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 73 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 35.904 | 4 | 4
74-1 | PK104XA-CNV-301.01-1 | ALUMINUM |  |  | Other |  | 12 | J01 | 74 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 41.088 | 4 | 4
74-2 | PK104XA-CNV-301.01-2 | ALUMINUM |  |  | Other |  | 12 | J01 | 74 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 40 |  | 41.088 | 4 | 4
74-3 | PK104XA-CNV-301.01-3 | ALUMINUM |  |  | Other |  | 12 | J01 | 74 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 40 |  | 41.088 | 4 | 4
74-4 | PK104XA-CNV-301.01-4 | ALUMINUM |  |  | Other |  | 12 | J01 | 74 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 10 |  | 41.088 | 4 | 4
75-1 | PK104XA-CNV-301.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 75 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 10 |  | 41.088 | 4 | 4
76-1 | PK104XA-CNV-310.01-1 | ALUMINUM |  |  | Other |  | 12 | J01 | 76 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 17.472 | 4 | 4
77-1 | PK104XA-CNV-325.01-1 | ALUMINUM |  |  | Other |  | 12 | J01 | 77 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 40 |  | 49.152 | 4 | 4
77-2 | PK104XA-CNV-325.01-2 | ALUMINUM |  |  | Other |  | 12 | J01 | 77 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 36.864 | 3 | 3
78-1 | PK104XA-CNV-325.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 78 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
79-1 | PK104XA-CNV-325.03-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 79 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
80-1 | PK104XA-CNV-325.04-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 80 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
81-1 | PK104XA-CNV-325.05-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 81 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
82-1 | PK104XA-CNV-325.13-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 82 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
83-1 | PK104XA-CNV-325.14-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 83 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
84-1 | PK104XA-CNV-325.15-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 84 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
85-1 | PK104XA-CNV-325.18-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 85 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
86-1 | PK104XA-CNV-1603.01-1 | ALUMINUM |  |  | Other |  | 12 | J01 | 86 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
86-2 | PK104XA-CNV-1603.01-2 | ALUMINUM |  |  | Other |  | 12 | J01 | 86 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 49.152 | 4 | 4
86-3 | PK104XA-CNV-1603.01-3 | ALUMINUM |  |  | Other |  | 12 | J01 | 86 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 49.152 | 4 | 4
87-1 | PK104XA-CNV-1603.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 87 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
88-1 | PK104XA-CNV-3519A.01-1 | ALUMINUM |  |  | Other |  | 9 | J19 | 88 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 40 |  | 42.432 | 10 | 10
89-1 | PK104XA-CNV-3520A.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 89 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 40 |  | 42.432 | 10 | 10
90-1 | PK104XA-CNV-3521A.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 90 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 40 |  | 42.432 | 10 | 10
91-1 | PK104XA-CNV-3522A.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 91 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 40 |  | 42.432 | 10 | 10
92-1 | PK104XA-CNV-97726.01-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 92 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES |  |  | 49.152 | 4 | 4
92-2 | PK104XA-CNV-97726.01-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 92 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 40 |  | 49.152 | 4 | 4
92-3 | PK104XA-CNV-97726.01-3 | ALUMINUM |  |  | Other |  | 8 | J25 | 92 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 49.152 | 4 | 4
93-1 | PK104XA-CNV-97726.02-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 93 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
93-2 | PK104XA-CNV-97726.02-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 93 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
94-1 | PK104XA-CNV-97727.01-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 94 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 49.152 | 4 | 4
94-2 | PK104XA-CNV-97727.01-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 94 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 40 |  | 49.152 | 4 | 4
95-1 | PK104XA-CNV-97727.02-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 95 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 40 |  | 49.152 | 4 | 4
95-2 | PK104XA-CNV-97727.02-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 95 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 40 |  | 49.152 | 4 | 4
96-1 | PK104XA-CNV-97728.01-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 96 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 49.152 | 4 | 4
96-2 | PK104XA-CNV-97728.01-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 96 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 49.152 | 4 | 4
96-3 | PK104XA-CNV-97728.01-3 | ALUMINUM |  |  | Other |  | 8 | J25 | 96 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 40 |  | 49.152 | 4 | 4
97-1 | PK104XA-CNV-97728.02-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 97 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 49.152 | 4 | 4
97-2 | PK104XA-CNV-97728.02-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 97 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 40 |  | 49.152 | 4 | 4
98-1 | PK104XA-CW-100406.01-1 | CS | 2020-08-24 | 2020-08-31 | Other | TRUE | 3 | J23 | 98 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 12.096 | 8 | 8 | [5 empty] | 7
98-2 | PK104XA-CW-100406.01-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 98 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 8.08 | 5 | 5 | 2020-08-18 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 7 | 2 | 4 | 6
98-3 | PK104XA-CW-100406.01-3 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 98 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 12.928 | 8 | 8 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
98-4 | PK104XA-CW-100406.01-4 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 98 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-17 |  |  |  |  | 0 |  | 6
98-5 | PK104XA-CW-100406.01-5 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 98 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
98-6 | PK104XA-CW-100406.01-6 | CS |  |  | Other |  | 3 | J23 | 98 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,160,XS | 3000 | 8.768 | 6 | 6
98-7 | PK104XA-CW-100406.01-7 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 98 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object] |  | XS,XS |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
99-1 | PK104XA-CW-100406.02-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 99 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 14.544 | 9 | 9 | 2020-08-19 |  |  |  |  | 0 |  | 8
99-2 | PK104XA-CW-100406.02-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 99 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
99-3 | PK104XA-CW-100406.02-3 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 99 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 11.312 | 7 | 7 | 2020-08-20 |  |  |  |  | 0 |  | 9
99-4 | PK104XA-CW-100406.02-4 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 99 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
99-5 | PK104XA-CW-100406.02-5 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 99 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-20 |  |  |  |  | 0 |  | 9
99-6 | PK104XA-CW-100406.02-6 | CS | 2020-08-24 | 2020-08-31 | Other | TRUE | 3 | J23 | 99 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,STD,XS,STD |  | 16.416 | 10 | 10 | [5 empty] | 7
100-1 | PK104XA-CW-100407.01-1 | CS | 2020-08-24 | 2020-08-31 | Other | TRUE | 3 | J23 | 100 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,STD,XS,XS,XS,STD,XS |  | 14.8 | 9 | 9 | [5 empty] | 7
100-2 | PK104XA-CW-100407.01-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 100 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
100-3 | PK104XA-CW-100407.01-3 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 100 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
100-4 | PK104XA-CW-100407.01-4 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 100 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 9.696 | 6 | 6 | 2020-08-19 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 8 | 1 | 4 | 5
100-5 | PK104XA-CW-100407.01-5 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 100 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-13 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 2 | 7 | 4 | 11
100-6 | PK104XA-CW-100407.01-6 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 3 | J23 | 100 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 16.16 | 10 | 10 | 2020-08-19 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 8 | 1 | 4 | 5
101-1 | PK104XA-CW-100407.02-1 | CS |  |  | Other |  | 3 | J23 | 101 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,160,XS,XS | 3000 | 8.768 | 6 | 6
101-2 | PK104XA-CW-100407.02-2 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 3 | J23 | 101 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-11 |  | 2020-08-20 | 2020-08-24 |  | 1 |  | 5 | 9 | 4 | 13
101-3 | PK104XA-CW-100407.02-3 | CS | 2020-08-05 | 2020-08-10 | Other | TRUE | 3 | J23 | 101 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-12 |  | 2020-08-20 | 2020-08-24 |  | 5 |  | 2 | 8 | 4 | 12
101-4 | PK104XA-CW-100407.02-4 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 3 | J23 | 101 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 12.928 | 8 | 8 | 2020-08-13 |  | 2020-08-20 | 2020-08-24 |  | 1 |  | 7 | 7 | 4 | 11
101-5 | PK104XA-CW-100407.02-5 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 3 | J23 | 101 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object] |  | XS,XS |  | 8.08 | 5 | 5 | 2020-08-11 |  |  |  |  | 1 |  | 5
101-6 | PK104XA-CW-100407.02-6 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 3 | J23 | 101 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 9.184 | 6 | 6 | 2020-08-20 |  |  |  |  | 2 |  | 1
101-7 | PK104XA-CW-100407.02-7 | CS | 2020-08-06 | 2020-08-10 | Other | TRUE | 3 | J23 | 101 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 0 | 0 | 0 | 2020-08-13 |  | 2020-08-20 | 2020-08-24 |  | 4 |  | 3 | 7 | 4 | 11
103-1 | PK104XA-FW-900001.01-1 | CS | 2020-08-06 | 2020-08-12 | Other | TRUE | 1 | J30 | 103 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object] |  | STD,STD |  | 4.704 | 1 | 1 | 2020-08-12 |  | 2020-08-20 | 2020-08-24 |  | 6 |  | 0 | 8 | 4 | 12
104-1 | PK104XA-FW-900001.02-1 | CS | 2020-08-06 | 2020-08-12 | Other | TRUE | 1 | J30 | 104 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object] |  | STD,STD |  | 4.704 | 1 | 1 | 2020-08-12 |  | 2020-08-20 | 2020-08-24 |  | 6 |  | 0 | 8 | 4 | 12
105-1 | PK104XA-GN-02.01-1 | CS |  |  | Other |  | #N/A | - | 105 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | XS,XS,XS |  | 3.232 | 2 | 2
105-2 | PK104XA-GN-02.01-2 | CS | 2020-09-01 | 2020-09-02 | Other | TRUE | #N/A | - | 105 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object] |  |  |  | 0 | 0 | 0 | [5 empty] | 1
106-1 | PK104XA-GN-97723.01-1 | CS |  |  | Other | TRUE | 3 | J23 | 106 |  | UP |  |  | 1 | 7052 | CP CHEM | Workable | [object Object],[object Object],[object Object] |  | STD,STD,STD |  | 12.768 | 7 | 7
106-2 | PK104XA-GN-97723.01-2 | CS |  |  | Other |  | 3 | J23 | 106 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160,STD,STD,STD,STD,STD | 3000 | 14.896 | 9 | 9
106-3 | PK104XA-GN-97723.01-3 | CS |  |  | Other | TRUE | 3 | J23 | 106 |  | UP |  |  | 1 | 7052 | CP CHEM | Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD,STD,STD,STD |  | 16.848 | 9 | 9
106-4 | PK104XA-GN-97723.01-4 | CS |  |  | Other | TRUE | 3 | J23 | 106 |  | UP |  |  | 1 | 7052 | CP CHEM | Workable | [object Object],[object Object],[object Object],[object Object] |  | XS,STD,STD,STD |  | 0 | 0 | 0
107-1 | PK104XA-GN-98398.01-1 | CS |  |  | Other |  | 3 | J23 | 107 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160,XS,STD,STD,STD,STD | 3000 | 27.28 | 11 | 11
108-1 | PK104XA-GN-3608.01-1 | CS |  |  | Other |  | #N/A | - | 108 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FLANGES | XS,XS,XS,XS,XS,XS |  | 14.544 | 9 | 9
109-1 | PK104XA-PA-3519.01-1 | ALUMINUM |  |  | Other |  | 9 | J19 | 109 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 10,10 |  | 94.848 | 7 | 7
110-1 | PK104XA-PA-3520.01-1 | ALUMINUM |  |  | Other |  | 9 | J19 | 110 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 10,10 |  | 98.976 | 8 | 8
111-1 | PK104XA-PA-3521.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 111 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 10,10 |  | 98.976 | 8 | 8
112-1 | PK104XA-PA-3522.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 112 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 10,10 |  | 98.976 | 8 | 8
113-1 | PK104XA-V-100410.01-1 | CS | 2020-08-06 | 2020-08-10 | Other | TRUE | 3 | J23 | 113 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD |  | 9.36 | 5 | 5 | 2020-08-18 |  | 2020-08-20 | 2020-08-24 |  | 4 |  | 8 | 2 | 4 | 6
113-2 | PK104XA-V-100410.01-2 | CS | 2020-08-06 | 2020-08-10 | Other | TRUE | 3 | J23 | 113 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD |  | 9.36 | 5 | 5 | 2020-08-18 |  | 2020-08-20 | 2020-08-24 |  | 4 |  | 8 | 2 | 4 | 6
113-3 | PK104XA-V-100410.01-3 | CS | 2020-08-06 | 2020-08-10 | Other | TRUE | 3 | J23 | 113 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD |  | 7.488 | 4 | 4 | 2020-08-18 |  | 2020-08-20 | 2020-08-24 |  | 4 |  | 8 | 2 | 4 | 6
113-4 | PK104XA-V-100410.01-4 | CS | 2020-08-06 | 2020-08-10 | Other | TRUE | 3 | J23 | 113 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD,STD |  | 11.232 | 6 | 6 | 2020-08-13 |  | 2020-08-20 | 2020-08-24 |  | 4 |  | 3 | 7 | 4 | 11
113-5 | PK104XA-V-100410.01-5 | CS | 2020-08-06 | 2020-08-10 | Other | TRUE | 3 | J23 | 113 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object] |  | STD,STD,STD |  | 3.744 | 2 | 2 | 2020-08-13 |  | 2020-08-20 | 2020-08-24 |  | 4 |  | 3 | 7 | 4 | 11
113-6 | PK104XA-V-100410.01-6 | CS | 2020-08-06 | 2020-08-10 | Other | TRUE | 3 | J23 | 113 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object] |  | STD,STD |  | 1.872 | 1 | 1 | 2020-08-13 |  | 2020-08-20 | 2020-08-24 |  | 4 |  | 3 | 7 | 4 | 11
114-1 | PK104XA-W-3696.01-1 | CS | 2020-08-05 | 2020-08-10 | Other |  | 3 | J23 | 114 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object] |  | STD,STD |  | 1.872 | 1 | 1 | 2020-08-12 |  | 2020-08-20 | 2020-08-24 |  | 5 |  | 2 | 8 | 4 | 12
114-2 | PK104XA-W-3696.01-2 | CS | 2020-08-05 | 2020-08-10 | Other |  | 3 | J23 | 114 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object] |  | STD,STD,STD |  | 3.744 | 2 | 2 | 2020-08-12 |  | 2020-08-20 | 2020-08-24 |  | 5 |  | 2 | 8 | 4 | 12
114-3 | PK104XA-W-3696.01-3 | CS | 2020-08-05 | 2020-08-10 | Other |  | 3 | J23 | 114 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object] |  | STD,STD,STD |  | 3.744 | 2 | 2 | 2020-08-13 |  | 2020-08-20 | 2020-08-24 |  | 5 |  | 3 | 7 | 4 | 11
114-4 | PK104XA-W-3696.01-4 | CS | 2020-08-20 |  | Other |  | 3 | J23 | 114 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD,STD,STD |  | 16.848 | 9 | 9
115-1 | PK104XA-WC-08.02-1 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 3 | J23 | 115 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-11 |  | 2020-08-20 | 2020-08-24 |  | 1 |  | 5 | 9 | 4 | 13
115-2 | PK104XA-WC-08.02-2 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 3 | J23 | 115 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 4.848 | 3 | 3 | 2020-08-11 |  | 2020-08-20 | 2020-08-24 |  | 1 |  | 5 | 9 | 4 | 13
115-3 | PK104XA-WC-08.02-3 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 3 | J23 | 115 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 8.08 | 5 | 5 | 2020-08-11 |  | 2020-08-20 | 2020-08-24 |  | 1 |  | 5 | 9 | 4 | 13
115-4 | PK104XA-WC-08.02-4 | CS |  |  | Other |  | 3 | J23 | 115 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS | XS,XS,XS,XS,XS |  | 7.68 | 6 | 6 | [6 empty] | TRUE
116-1 | PK104XA-WC-08.01-1 | CS |  |  | Other |  | #N/A | - | 116 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | XS,XS,XS |  | 3.232 | 2 | 2
116-2 | PK104XA-WC-08.01-2 | CS | 2020-09-01 | 2020-09-02 | Other | TRUE | #N/A | - | 116 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object] |  |  |  | 0 | 0 | 0 | [5 empty] | 1
117-1 | PK104XA-WC-3610.01-1 | CS | 2020-09-01 |  | Other | TRUE | #N/A | - | 117 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object] |  | XS |  | 14.272 | 12 | 12
117-2 | PK104XA-WC-3610.01-2 | CS |  |  | Other |  | #N/A | - | 117 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object] | FLANGES | XS,XS, | 30003000 | 0 | 0 | 0
118-1 | PK104XA-YB-97367.01-1 | ALUMINUM |  |  | Other |  | 12 | J01 | 118 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10,80S |  | 114.912 | 8 | 8
119-1 | PK104XA-YB-97367.02-1 | ALUMINUM |  |  | Other |  | 12 | J01 | 119 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
119-2 | PK104XA-YB-97367.02-2 | ALUMINUM |  |  | Other |  | 12 | J01 | 119 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
120-1 | PK104XA-YB-98341.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 120 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 80S,10 |  | 114.912 | 8 | 8
121-1 | PK104XA-YB-98341.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 121 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
121-2 | PK104XA-YB-98341.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 121 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
122-1 | PK104XA-YB-98342.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 122 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 80S,10 |  | 114.912 | 8 | 8
123-1 | PK104XA-YB-98342.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 123 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
123-2 | PK104XA-YB-98342.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 123 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
124-1 | PK104XA-YB-98343.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 124 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 80S,10 |  | 114.912 | 8 | 8
125-1 | PK104XA-YB-98343.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 125 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
125-2 | PK104XA-YB-98343.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 125 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
126-1 | PK104XA-YB-98344.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 126 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 80S,10 |  | 114.912 | 8 | 8
127-1 | PK104XA-YB-98344.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 127 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
127-2 | PK104XA-YB-98344.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 127 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
128-1 | PK104XA-YB-98345.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 128 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 10,80S |  | 114.912 | 8 | 8
129-1 | PK104XA-YB-98345.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 129 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
129-2 | PK104XA-YB-98345.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 129 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
130-1 | PK104XA-YB-98346.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 130 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 80S,10 |  | 114.912 | 8 | 8
131-1 | PK104XA-YB-98346.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 131 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
131-2 | PK104XA-YB-98346.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 131 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
132-1 | PK104XA-YB-98347.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 132 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES | 10,80S |  | 114.912 | 8 | 8
133-1 | PK104XA-YB-98347.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 133 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
133-2 | PK104XA-YB-98347.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 133 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
134-1 | PK104XA-YB-98348.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 134 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 80S,10 |  | 114.912 | 8 | 8
135-1 | PK104XA-YB-98348.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 135 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
135-2 | PK104XA-YB-98348.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 135 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
136-1 | PK104XA-YB-98349.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 136 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 10,80S |  | 114.912 | 8 | 8
137-1 | PK104XA-YB-98349.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 137 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
137-2 | PK104XA-YB-98349.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 137 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
138-1 | PK104XA-YB-98350.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 138 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 10,80S |  | 114.912 | 8 | 8
139-1 | PK104XA-YB-98350.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 139 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
139-2 | PK104XA-YB-98350.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 139 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
140-1 | PK104XA-YB-98351.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 140 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 80S,10 |  | 114.912 | 8 | 8
141-1 | PK104XA-YB-98351.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 141 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
141-2 | PK104XA-YB-98351.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 141 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
142-1 | PK104XA-YB-98352.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 142 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10,80S |  | 114.912 | 8 | 8
143-1 | PK104XA-YB-98352.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 143 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
143-2 | PK104XA-YB-98352.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 143 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
144-1 | PK104XA-YB-98353.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 144 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10,80S |  | 114.912 | 8 | 8
145-1 | PK104XA-YB-98353.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 145 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
145-2 | PK104XA-YB-98353.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 145 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
146-1 | PK104XA-YB-98354.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 146 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 80S,10 |  | 114.912 | 8 | 8
147-1 | PK104XA-YB-98354.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 147 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
147-2 | PK104XA-YB-98354.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 147 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
148-1 | PK104XA-YB-98355.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 148 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 80S,10 |  | 114.912 | 8 | 8
149-1 | PK104XA-YB-98355.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 149 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
149-2 | PK104XA-YB-98355.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 149 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
150-1 | PK104XA-YB-98356.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 150 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 80S,10 |  | 114.912 | 8 | 8
151-1 | PK104XA-YB-98356.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 151 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
151-2 | PK104XA-YB-98356.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 151 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
152-1 | PK104XA-YB-98357.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 152 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10,80S |  | 114.912 | 8 | 8
153-1 | PK104XA-YB-98357.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 153 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
153-2 | PK104XA-YB-98357.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 153 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
154-1 | PK104XA-YB-98358.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 154 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10,80S |  | 114.912 | 8 | 8
155-1 | PK104XA-YB-98358.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 155 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
155-2 | PK104XA-YB-98358.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 155 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
156-1 | PK104XA-YB-98359.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 156 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 80S,10 |  | 114.912 | 8 | 8
157-1 | PK104XA-YB-98359.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 157 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
157-2 | PK104XA-YB-98359.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 157 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
158-1 | PK104XA-YB-98360.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 158 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 10,80S |  | 114.912 | 8 | 8
159-1 | PK104XA-YB-98360.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 159 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
159-2 | PK104XA-YB-98360.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 159 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
160-1 | PK104XA-YB-98361.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 160 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 80S,10 |  | 114.912 | 8 | 8
161-1 | PK104XA-YB-98361.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 161 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
161-2 | PK104XA-YB-98361.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 161 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
162-1 | PK104XA-YB-98362.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 162 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10,80S |  | 114.912 | 8 | 8
163-1 | PK104XA-YB-98362.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 163 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
163-2 | PK104XA-YB-98362.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 163 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
164-1 | PK104XA-YB-98363.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 164 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10,80S |  | 114.912 | 8 | 8
165-1 | PK104XA-YB-98363.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 165 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
165-2 | PK104XA-YB-98363.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 165 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
166-1 | PK104XA-YB-98364.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 166 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 80S,10 |  | 114.912 | 8 | 8
167-1 | PK104XA-YB-98364.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 167 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
167-2 | PK104XA-YB-98364.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 167 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
168-1 | PK104XA-YB-98365.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 168 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,PIPE,FLANGES | 80S,10 |  | 114.912 | 8 | 8
169-1 | PK104XA-YB-98365.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 169 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
169-2 | PK104XA-YB-98365.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 169 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
170-1 | PK104XA-YB-98366.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 170 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 80S,10 |  | 114.912 | 8 | 8
171-1 | PK104XA-YB-98366.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 171 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
171-2 | PK104XA-YB-98366.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 171 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
172-1 | PK104XA-YB-98367.01-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 172 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FLANGES,FLANGES,PIPE | 80S,10 |  | 114.912 | 8 | 8
173-1 | PK104XA-YB-98367.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 173 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
173-2 | PK104XA-YB-98367.02-2 | ALUMINUM |  |  | Other |  | 2 | J14 | 173 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | 10 |  | 84.192 | 6 | 6
201-1 | PK110XA-C-97624.01-1 | 304/304L SS |  |  | Other |  | 7 | J05 | 201 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS | 40S,80S,40S,40Sx80S,40S,40S |  | 16.1 | 6 | 6
201-2 | PK110XA-C-97624.01-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 201 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
201-3 | PK110XA-C-97624.01-3 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 201 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 13.44 | 5 | 5 | 2020-09-02 |  |  |  |  | 1 |  | 8
201-4 | PK110XA-C-97624.01-4 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 201 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-31 |  |  |  |  | 1 |  | 6
201-5 | PK110XA-C-97624.01-5 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 201 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
201-6 | PK110XA-C-97624.01-6 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 201 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
201-7 | PK110XA-C-97624.01-7 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 201 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-31 |  |  |  |  | 1 |  | 6
201-8 | PK110XA-C-97624.01-8 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 201 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-31 |  |  |  |  | 1 |  | 6
201-9 | PK110XA-C-97624.01-9 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 201 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
201-10 | PK110XA-C-97624.01-10 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 201 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
201-11 | PK110XA-C-97624.01-11 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J05 | 201 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40Sx80S |  | 8.036 | 3 | 3
202-1 | PK110XA-C-102338.01-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 202 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
202-2 | PK110XA-C-102338.01-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 202 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-31 |  |  |  |  | 1 |  | 6
202-3 | PK110XA-C-102338.01-3 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 202 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
202-4 | PK110XA-C-102338.01-4 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 202 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
202-5 | PK110XA-C-102338.01-5 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 202 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-31 |  |  |  |  | 1 |  | 6
202-6 | PK110XA-C-102338.01-6 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 202 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-31 |  |  |  |  | 1 |  | 6
202-7 | PK110XA-C-102338.01-7 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J05 | 202 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
203-1 | PK110XA-CNV-304.01-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 203 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
203-2 | PK110XA-CNV-304.01-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 203 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
204-1 | PK110XA-CNV-329.01-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 204 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
204-2 | PK110XA-CNV-329.01-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 204 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
205-1 | PK110XA-CS-97779.03-1 | CS |  |  | Other |  | 12 | J01 | 205 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 3.408 | 3 | 3
206-1 | PK110XA-CS-100001.01-1 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 12 | J01 | 206 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1 | 2020-08-10 |  |  |  |  | 1 |  | 4
207-1 | PK110XA-CW-3707.01-1 | CS |  |  | Other |  | 12 | J01 | 207 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 4.224 | 4 | 4
208-1 | PK110XA-CW-3708.01-1 | CS |  |  | Other |  | 12 | J01 | 208 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 3.12 | 3 | 3
209-1 | PK110XA-N-100004.01-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 12 | J01 | 209 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 8.08 | 5 | 5 | 2020-08-17 |  |  |  |  | 0 |  | 6
209-2 | PK110XA-N-100004.01-2 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 12 | J01 | 209 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 4.224 | 4 | 4 | 2020-08-25 |  |  |  |  | 2 |  | 6
210-1 | PK110XA-CW-300002.01-1 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 12 | J01 | 210 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD |  | 5.616 | 3 | 3 | [5 empty] | 11
210-2 | PK110XA-CW-300002.01-2 | CS | 2020-08-24 | 2020-08-31 | Other | TRUE | 12 | J01 | 210 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | XS |  | 4.224 | 4 | 4 | [5 empty] | 7
210-3 | PK110XA-CW-300002.01-3 | CS | 2020-08-05 | 2020-08-17 | Other | TRUE | 12 | J01 | 210 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  | STD |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 12 |  | 0 | 3 | 4 | 7
210-4 | PK110XA-CW-300002.01-4 | CS | 2020-08-05 | 2020-08-17 | Other | TRUE | 12 | J01 | 210 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  | STD |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 12 |  | 0 | 3 | 4 | 7
211-1 | PK110XA-CW-300001.01-1 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 12 | J01 | 211 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD |  | 5.616 | 3 | 3 | [5 empty] | 11
211-2 | PK110XA-CW-300001.01-2 | CS | 2020-08-26 | 2020-08-28 | Other | TRUE | 12 | J01 | 211 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | XS |  | 4.224 | 4 | 4 | [5 empty] | 2
211-3 | PK110XA-CW-300001.01-3 | CS | 2020-08-20 | 2020-08-25 | Other | TRUE | 12 | J01 | 211 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object] |  | STD |  | 0 | 0 | 0 | [5 empty] | 5
211-4 | PK110XA-CW-300001.01-4 | CS | 2020-08-20 | 2020-08-25 | Other | TRUE | 12 | J01 | 211 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object] |  | STD |  | 0 | 0 | 0 | [5 empty] | 5
212-1 | PK110XA-V-100011.01-1 | 304/304L SS CRYO |  |  | Other |  | 12 | J01 | 212 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | FITTINGS | 40S,40S,10Sx40S,40S |  | 10.472 | 3 | 3
212-2 | PK110XA-V-100011.01-2 | 304/304L SS CRYO |  |  | Other |  | 12 | J01 | 212 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS | 80S |  | 7.392 | 4 | 4 | [6 empty] | TRUE
212-3 | PK110XA-V-100011.01-3 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 12 | J01 | 212 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object] |  | 40S |  | 0 | 0 | 0 | [5 empty] | 5
212-4 | PK110XA-V-100011.01-4 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 12 | J01 | 212 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object] |  | 40S |  | 0 | 0 | 0 | [5 empty] | 5
213-1 | PK110XA-W-1501.01-1 | CS | 2020-08-20 |  | Other | TRUE | 4 | J32 | 213 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,XS |  | 9.104 | 5 | 5
214-1 | PM101XA-A-100391.01-1 | Galv. |  |  | Other | TRUE | 5 | J06 | 214 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
214-2 | PM101XA-A-100391.01-2 | Galv. |  |  | Other | TRUE | 5 | J06 | 214 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
214-3 | PM101XA-A-100391.01-3 | Galv. |  |  | Other | TRUE | 5 | J06 | 214 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
214-4 | PM101XA-A-100391.01-4 | Galv. |  |  | Other | TRUE | 5 | J06 | 214 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
214-5 | PM101XA-A-100391.01-5 | Galv. |  |  | Other | TRUE | 5 | J06 | 214 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
214-6 | PM101XA-A-100391.01-6 | Galv. |  |  | Other | TRUE | 5 | J06 | 214 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
214-7 | PM101XA-A-100391.01-7 | Galv. |  |  | Other | TRUE | 5 | J06 | 214 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
214-8 | PM101XA-A-100391.01-8 | Galv. |  |  | Other | TRUE | 5 | J06 | 214 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
214-9 | PM101XA-A-100391.01-9 | Galv. |  |  | Other | TRUE | 5 | J06 | 214 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
214-10 | PM101XA-A-100391.01-10 | Galv. |  |  | Other | TRUE | 5 | J06 | 214 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
215-1 | PM101XA-A-100391.02-1 | CS |  |  | Other |  | 5 | J06 | 215 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  | XS |  | 0 | 0 | 0
215-2 | PM101XA-A-100391.02-2 | CS |  |  | Other |  | 5 | J06 | 215 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  | XS |  | 0 | 0 | 0
216-1 | PM101XA-A-100391.03-1 | CS |  |  | Other |  | 5 | J06 | 216 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  | XS |  | 0 | 0 | 0
217-1 | PM101XA-A-100391.04-1 | CS |  |  | Other |  | 5 | J06 | 217 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  | XS |  | 0 | 0 | 0
217-2 | PM101XA-A-100391.04-2 | CS |  |  | Other |  | 5 | J06 | 217 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  | XS |  | 0 | 0 | 0
217-3 | PM101XA-A-100391.04-3 | CS |  |  | Other |  | 5 | J06 | 217 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  | XS |  | 0 | 0 | 0
218-1 | PM101XA-A-100391.05-1 | CS | 2020-08-03 |  | Other |  | 5 | J06 | 218 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Issued | [object Object] |  | XS |  | 0 | 0 | 0
218-2 | PM101XA-A-100391.05-2 | CS | 2020-08-03 |  | Other |  | 5 | J06 | 218 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Issued | [object Object] |  | XS |  | 0 | 0 | 0
218-3 | PM101XA-A-100391.05-3 | CS | 2020-08-03 |  | Other |  | 5 | J06 | 218 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Issued | [object Object] |  | XS |  | 0 | 0 | 0
218-4 | PM101XA-A-100391.05-4 | CS | 2020-08-03 |  | Other |  | 5 | J06 | 218 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Issued | [object Object] |  | XS |  | 0 | 0 | 0
218-5 | PM101XA-A-100391.05-5 | CS |  |  | Other |  | 5 | J06 | 218 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  | XS |  | 0 | 0 | 0
218-6 | PM101XA-A-100391.05-6 | CS | 2020-08-03 |  | Other |  | 5 | J06 | 218 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Issued | [object Object] |  | XS |  | 0 | 0 | 0
218-7 | PM101XA-A-100391.05-7 | CS |  |  | Other |  | 5 | J06 | 218 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  | XS |  | 0 | 0 | 0
219-1 | PM101XA-A-100391.06-1 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-2 | PM101XA-A-100391.06-2 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-3 | PM101XA-A-100391.06-3 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-4 | PM101XA-A-100391.06-4 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-5 | PM101XA-A-100391.06-5 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-6 | PM101XA-A-100391.06-6 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-7 | PM101XA-A-100391.06-7 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-8 | PM101XA-A-100391.06-8 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-9 | PM101XA-A-100391.06-9 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-10 | PM101XA-A-100391.06-10 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-11 | PM101XA-A-100391.06-11 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-12 | PM101XA-A-100391.06-12 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-13 | PM101XA-A-100391.06-13 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-14 | PM101XA-A-100391.06-14 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-15 | PM101XA-A-100391.06-15 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-16 | PM101XA-A-100391.06-16 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-17 | PM101XA-A-100391.06-17 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
219-18 | PM101XA-A-100391.06-18 | Galv. |  |  | Other | TRUE | 5 | J07 | 219 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
220-1 | PM101XA-A-100391.07-1 | Galv. |  |  | Other | TRUE | 5 | J07 | 220 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
220-2 | PM101XA-A-100391.07-2 | Galv. |  |  | Other | TRUE | 5 | J07 | 220 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
220-3 | PM101XA-A-100391.07-3 | Galv. |  |  | Other | TRUE | 5 | J07 | 220 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
220-4 | PM101XA-A-100391.07-4 | Galv. |  |  | Other | TRUE | 5 | J07 | 220 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
220-5 | PM101XA-A-100391.07-5 | Galv. |  |  | Other | TRUE | 5 | J07 | 220 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
221-1 | PM101XA-A-100391.08-1 | Galv. |  |  | Other | TRUE | 5 | J07 | 221 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
222-1 | PM101XA-A-100391.09-1 | Galv. |  |  | Other | TRUE | 5 | J07 | 222 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
222-2 | PM101XA-A-100391.09-2 | Galv. |  |  | Other | TRUE | 5 | J07 | 222 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
222-3 | PM101XA-A-100391.09-3 | Galv. |  |  | Other | TRUE | 5 | J07 | 222 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
222-4 | PM101XA-A-100391.09-4 | Galv. |  |  | Other | TRUE | 5 | J07 | 222 | X |  |  |  | 1 | 7052 | CP CHEM | Workable | [object Object] |  | XS |  | 0 | 0 | 0
223-1 | PM101XA-C-97549.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 223 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 21.42 | 9 | 9 | [5 empty] | 7
223-2 | PM101XA-C-97549.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 223 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 9.464 | 4 | 4 | [5 empty] | 7
223-3 | PM101XA-C-97549.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 223 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
224-1 | PM101XA-C-97550.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 224 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 16.66 | 7 | 7 | [5 empty] | 7
224-2 | PM101XA-C-97550.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 224 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 11.732 | 5 | 5 | [5 empty] | 7
224-3 | PM101XA-C-97550.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 224 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
225-1 | PM101XA-C-97551.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 225 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 16.66 | 7 | 7 | [5 empty] | 7
225-2 | PM101XA-C-97551.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 225 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 11.732 | 5 | 5 | [5 empty] | 7
225-3 | PM101XA-C-97551.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 225 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
226-1 | PM101XA-C-97552.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 226 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 23.8 | 10 | 10 | [5 empty] | 7
226-2 | PM101XA-C-97552.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 226 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 11.732 | 5 | 5 | [5 empty] | 7
226-3 | PM101XA-C-97552.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 226 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
227-1 | PM101XA-C-97553.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 227 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 19.04 | 8 | 8 | [5 empty] | 7
227-2 | PM101XA-C-97553.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 227 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 11.732 | 5 | 5 | [5 empty] | 7
227-3 | PM101XA-C-97553.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 227 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
228-1 | PM101XA-C-97554.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 228 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 21.42 | 9 | 9 | [5 empty] | 7
228-2 | PM101XA-C-97554.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 228 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 11.732 | 5 | 5 | [5 empty] | 7
228-3 | PM101XA-C-97554.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 228 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
229-1 | PM101XA-C-97555.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 229 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 21.42 | 9 | 9 | [5 empty] | 7
229-2 | PM101XA-C-97555.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 229 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 9.464 | 4 | 4 | [5 empty] | 7
229-3 | PM101XA-C-97555.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 229 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
230-1 | PM101XA-C-97556.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 230 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 16.66 | 7 | 7 | [5 empty] | 7
230-2 | PM101XA-C-97556.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 230 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 11.732 | 5 | 5 | [5 empty] | 7
230-3 | PM101XA-C-97556.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 230 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
231-1 | PM101XA-C-97557.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 231 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 16.66 | 7 | 7 | [5 empty] | 7
231-2 | PM101XA-C-97557.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 231 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 11.732 | 5 | 5 | [5 empty] | 7
231-3 | PM101XA-C-97557.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 231 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
232-1 | PM101XA-C-97558.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 232 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 23.8 | 10 | 10 | [5 empty] | 7
232-2 | PM101XA-C-97558.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 232 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 11.732 | 5 | 5 | [5 empty] | 7
232-3 | PM101XA-C-97558.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 232 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
233-1 | PM101XA-C-97559.01-1 | 304/304L SS | 2020-08-24 |  | Other | TRUE | 7 | J04 | 233 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 23.8 | 10 | 10
233-2 | PM101XA-C-97559.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 233 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 11.732 | 5 | 5 | [5 empty] | 7
233-3 | PM101XA-C-97559.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 233 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
234-1 | PM101XA-C-97560.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 234 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 16.66 | 7 | 7 | [5 empty] | 7
234-2 | PM101XA-C-97560.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 234 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 11.732 | 5 | 5 | [5 empty] | 7
234-3 | PM101XA-C-97560.01-3 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 234 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
235-1 | PM101XA-C-97625.01-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 235 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,40S,40S,40S,40S,80S,40S | 3000 | 23.156 | 9 | 9 | [5 empty] | 1
235-2 | PM101XA-C-97625.01-2 | 304/304L SS |  |  | Other |  | 7 | J04 | 235 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,80S,80S,80S | 30003000 | 42.588 | 17 | 17
235-3 | PM101XA-C-97625.01-3 | 304/304L SS |  |  | Other |  | 7 | J04 | 235 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40S,80S | 3000 | 0 | 0 | 0
236-1 | PM101XA-C-97625.02-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 236 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,80S,40S,40S,40S,80S,40S,40S | 30003000 | 35.56 | 14 | 14 | [5 empty] | 1
236-2 | PM101XA-C-97625.02-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 236 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S,40S,40S,40S |  | 21.504 | 8 | 8 | 2020-09-02 |  |  |  |  | 1 |  | 8
237-1 | PM101XA-C-97625.03-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 237 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,80S,40S,40S,40S,40S,80S,40S | 3000 | 33.908 | 13 | 13
237-2 | PM101XA-C-97625.03-2 | 304/304L SS |  |  | Other |  | 7 | J04 | 237 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,80S,40S,40S | 3000 | 42.588 | 17 | 17
237-3 | PM101XA-C-97625.03-3 | 304/304L SS |  |  | Other |  | 7 | J04 | 237 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,80S,40S,80S,80S | 30003000 | 0 | 0 | 0
238-1 | PM101XA-C-97625.04-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 238 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,80S,40S,40S,80S,40S,80S | 30003000 | 35.56 | 14 | 14 | [5 empty] | 1
238-2 | PM101XA-C-97625.04-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 238 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S,40S,40S,40S |  | 26.88 | 10 | 10 | 2020-09-02 |  |  |  |  | 1 |  | 8
239-1 | PM101XA-CS-97779.01-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 5 | J07 | 239 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS,XS,XS | 3000 | 18.144 | 12 | 12 | 2020-09-01 |  |  |  |  | 0 |  | 21
239-2 | PM101XA-CS-97779.01-2 | CS | 2020-08-05 | 2020-08-10 | Other | TRUE | 5 | J07 | 239 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object] |  | XS,XS |  | 1.2 | 1 | 1 | 2020-08-12 |  | 2020-08-20 | 2020-08-24 |  | 5 |  | 2 | 8 | 4 | 12
240-1 | PM101XA-CS-97779.02-1 | CS | 2020-09-01 |  | Other | TRUE | 5 | J07 | 240 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 8.08 | 5 | 5
240-2 | PM101XA-CS-97779.02-2 | CS | 2020-08-13 | 2020-08-19 | Other | TRUE | 5 | J07 | 240 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 8.08 | 5 | 5 | 2020-09-01 |  |  |  |  | 6 |  | 13
241-1 | PM101XA-CS-97782.01-1 | CS |  |  | Other |  | 5 | J07 | 241 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 1.6016e+17 |  | 17.712 | 9 | 9
241-2 | PM101XA-CS-97782.01-2 | CS |  |  | Other |  | 5 | J07 | 241 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160 |  | 5.904 | 3 | 3
242-1 | PM101XA-CS-98376.01-1 | CS |  |  | Other |  | 5 | J06 | 242 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 1.6016e+17 |  | 17.712 | 9 | 9
242-2 | PM101XA-CS-98376.01-2 | CS |  |  | Other |  | 5 | J06 | 242 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
243-1 | PM101XA-CS-98379.01-1 | CS |  |  | Other |  | 5 | J07 | 243 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS,VALVES / IN-LINE ITEMS,VALVES / IN-LINE ITEMS,FITTINGS,PIPE,PIPE,PIPE,VALVES / IN-LINE ITEMS | XS,160,XSx160,160,160,160,160 |  | 34.24 | 25 | 25
244-1 | PM101XA-CS-98379.02-1 | CS |  |  | Other |  | 5 | J07 | 244 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,FITTINGS,PIPE | 160160160160160 | 6000 | 14.128 | 8 | 8
245-1 | PM101XA-CS-98387.01-1 | CS |  |  | Other |  | 5 | J06 | 245 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE,PIPE,VALVES / IN-LINE ITEMS,VALVES / IN-LINE ITEMS,VALVES / IN-LINE ITEMS,VALVES / IN-LINE ITEMS | XS,160,160,XSx160,160,160,160,160,160 |  | 36.08 | 27 | 27
246-1 | PM101XA-CS-98387.02-1 | CS |  |  | Other |  | 5 | J06 | 246 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 1.6016e+17 | 6000 | 16.784 | 10 | 10
247-1 | PM101XA-CS-98413.01-1 | CS |  |  | Other |  | 5 | J06 | 247 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,160,XS,XS,XS,XS,XS,XS | 3000 | 17.376 | 10 | 10
248-1 | PM101XA-JW-97740.01-1 | CS |  |  | Other |  | 5 | J07 | 248 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  | XS |  | 0 | 0 | 0
248-2 | PM101XA-JW-97740.01-2 | CS |  |  | Other |  | 5 | J07 | 248 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160,XS,XS,XS,XS | 6000 | 16.528 | 7 | 7
248-3 | PM101XA-JW-97740.01-3 | CS | 2020-08-05 | 2020-08-24 | Other | TRUE | 5 | J07 | 248 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 9.504 | 3 | 3 | [5 empty] | 19
248-4 | PM101XA-JW-97740.01-4 | CS | 2020-08-05 | 2020-08-20 | Other | TRUE | 5 | J07 | 248 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XSx160,XS,XS,XS,XS,160,XS |  | 34.624 | 11 | 11 | 2020-08-25 |  |  |  |  | 15 |  | 5
249-1 | PM101XA-JW-97745.01-1 | CS | 2020-08-05 | 2020-08-24 | Other | TRUE | 5 | J07 | 249 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 0 | 0 | 0 | 2020-08-25 |  |  |  |  | 19 |  | 1
249-2 | PM101XA-JW-97745.01-2 | CS |  |  | Other |  | 5 | J07 | 249 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
249-3 | PM101XA-JW-97745.01-3 | CS | 2020-09-01 |  | Other | TRUE | 5 | J07 | 249 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,160,XSx160 |  | 0 | 0 | 0
250-1 | PM101XA-JW-97745.02-1 | CS |  |  | Other |  | 5 | J07 | 250 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160,XS,XS,XS,XS,XS,XS,XS,XS,XS,XS | 60006000 | 62.064 | 21 | 21
250-2 | PM101XA-JW-97745.02-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 5 | J07 | 250 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
251-1 | PM101XA-JW-97746.01-1 | CS |  |  | Other |  | 5 | J06 | 251 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,160,XS,XS | 6000 | 19.696 | 8 | 8
251-2 | PM101XA-JW-97746.01-2 | CS | 2020-08-05 | 2020-08-25 | Other | TRUE | 5 | J06 | 251 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XSx160,XS,XS,XS,160 |  | 25.12 | 8 | 8 | [5 empty] | 20
252-1 | PM101XA-JW-97751.01-1 | CS | 2020-08-05 | 2020-08-20 | Other | TRUE | 5 | J06 | 252 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 0 | 0 | 0 | 2020-08-24 |  |  |  |  | 15 |  | 4
252-2 | PM101XA-JW-97751.01-2 | CS |  |  | Other |  | 5 | J06 | 252 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
252-3 | PM101XA-JW-97751.01-3 | CS | 2020-09-01 |  | Other | TRUE | 5 | J06 | 252 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,160,XSx160 |  | 0 | 0 | 0
253-1 | PM101XA-JW-97751.02-1 | CS |  |  | Other |  | 5 | J06 | 253 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,XS,XS,XS,XS,XS,XS,160,XS | 60006000 | 62.064 | 21 | 21
253-2 | PM101XA-JW-97751.02-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 5 | J06 | 253 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
254-1 | PM101XA-JW-97755.01-1 | CS |  |  | Other |  | 5 | J07 | 254 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,XS,XS,XS,160,XS,XS | 6000 | 36.784 | 12 | 12
254-2 | PM101XA-JW-97755.01-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 5 | J07 | 254 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
255-1 | PM101XA-JW-97755.02-1 | CS | 2020-08-05 | 2020-08-24 | Other | TRUE | 5 | J07 | 255 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,160,XS,XS,XS,160,XSx160,XSx160,XSx160,XS |  | 46.256 | 13 | 13 | 2020-08-25 |  |  |  |  | 19 |  | 1
256-1 | PM101XA-JW-97758.01-1 | CS | 2020-08-05 | 2020-08-25 | Other | TRUE | 5 | J07 | 256 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS,XS |  | 41.616 | 12 | 12 | 2020-08-25 |  |  |  |  | 20 |  | 0
256-2 | PM101XA-JW-97758.01-2 | CS |  |  | Other |  | 5 | J07 | 256 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 5.152 | 4 | 4
257-1 | PM101XA-JW-97758.02-1 | CS |  |  | Other |  | 5 | J07 | 257 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 160,XS,XS,XSx160,XS |  | 25.888 | 6 | 6
257-2 | PM101XA-JW-97758.02-2 | CS |  |  | Other |  | 5 | J07 | 257 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,160,XS | 6000 | 24.528 | 8 | 8
257-3 | PM101XA-JW-97758.02-3 | CS |  |  | Other |  | 5 | J07 | 257 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  |  |  | 0 | 0 | 0
258-1 | PM101XA-JW-97759.01-1 | CS | 2020-08-13 | 2020-08-24 | Other | TRUE | 5 | J07 | 258 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 30.304 | 10 | 10 | 2020-08-26 |  |  |  |  | 11 |  | 2
258-2 | PM101XA-JW-97759.01-2 | CS | 2020-08-05 | 2020-08-13 | Other | TRUE | 5 | J07 | 258 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-25 |  |  |  |  | 8 |  | 12
259-1 | PM101XA-JW-97760.01-1 | CS | 2020-08-06 | 2020-08-12 | Other | TRUE | 5 | J07 | 259 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 8.816 | 3 | 3 | 2020-08-13 |  |  |  |  | 6 |  | 1
259-2 | PM101XA-JW-97760.01-2 | CS |  |  | Other |  | 5 | J07 | 259 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | XS,XS,XS,160,160,XS,XS | 60006000 | 40.336 | 15 | 15
260-1 | PM101XA-JW-97760.02-1 | CS |  |  | Other |  | 5 | J07 | 260 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XSx160,160,XS,XS,XS,XSx160,XS,XS |  | 55.376 | 15 | 15
260-2 | PM101XA-JW-97760.02-2 | CS | 2020-08-05 | 2020-08-24 | Other | TRUE | 5 | J07 | 260 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 0 | 0 | 0 | 2020-08-24 |  |  |  |  | 19 |  | 0
261-1 | PM101XA-JW-97760.03-1 | CS |  |  | Other | TRUE | 5 | J07 | 261 |  | UP |  |  | 1 | 7052 | CP CHEM | Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 22.176 | 7 | 7
261-2 | PM101XA-JW-97760.03-2 | CS |  |  | Other |  | 5 | J07 | 261 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,XS,XS,160 | 6000 | 31.904 | 10 | 10
262-1 | PM101XA-JW-97761.01-1 | CS |  |  | Other |  | 5 | J07 | 262 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 160,XS,XSx160,XS,XS |  | 29.056 | 7 | 7
262-2 | PM101XA-JW-97761.01-2 | CS |  |  | Other |  | 5 | J07 | 262 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,160 | 6000 | 31.44 | 8 | 8
262-3 | PM101XA-JW-97761.01-3 | CS |  |  | Other |  | 5 | J07 | 262 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  |  |  | 0 | 0 | 0
263-1 | PM101XA-JW-97762.01-1 | CS | 2020-08-06 | 2020-08-12 | Other | TRUE | 5 | J07 | 263 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 8.816 | 3 | 3 | 2020-08-13 |  |  |  |  | 6 |  | 1
263-2 | PM101XA-JW-97762.01-2 | CS |  |  | Other |  | 5 | J07 | 263 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | XS,XS,XS,160,160,XS,XS | 60006000 | 40.336 | 15 | 15
264-1 | PM101XA-JW-97762.02-1 | CS | 2020-08-05 | 2020-08-24 | Other | TRUE | 5 | J07 | 264 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 17.632 | 6 | 6 | 2020-08-25 |  |  |  |  | 19 |  | 1
265-1 | PM101XA-JW-97765.01-1 | CS | 2020-08-05 | 2020-08-20 | Other | TRUE | 5 | J06 | 265 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS,XS,XS |  | 48.096 | 16 | 16 | 2020-08-24 |  |  |  |  | 15 |  | 4
265-2 | PM101XA-JW-97765.01-2 | CS | 2020-08-20 | 2020-08-25 | Other | TRUE | 5 | J06 | 265 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object] |  |  |  | 0 | 0 | 0 | [5 empty] | 5
265-3 | PM101XA-JW-97765.01-3 | CS |  |  | Other |  | 5 | J06 | 265 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 0 | 0 | 0
265-4 | PM101XA-JW-97765.01-4 | CS | 2020-08-05 | 2020-08-24 | Other | TRUE | 5 | J06 | 265 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,160,XS,XS,XSx160 |  | 0 | 0 | 0 | 2020-08-26 |  |  |  |  | 19 |  | 2
266-1 | PM101XA-JW-97765.02-1 | CS |  |  | Other |  | 5 | J06 | 266 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,160,XS,XS | 6000 | 24.528 | 8 | 8
267-1 | PM101XA-JW-98382.01-1 | CS |  |  | Other |  | 5 | J06 | 267 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,XS,XS,XS,160,XS,XS | 6000 | 36.784 | 12 | 12
267-2 | PM101XA-JW-98382.01-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 5 | J06 | 267 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
268-1 | PM101XA-JW-98382.02-1 | CS | 2020-08-06 | 2020-08-25 | Other | TRUE | 5 | J06 | 268 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,160,160,XS,XS,XS,XSx160,XSx160,XSx160,XS,XS |  | 46.256 | 13 | 13 | 2020-08-28 |  |  |  |  | 19 |  | 3
269-1 | PM101XA-JW-98388.01-1 | CS | 2020-08-06 | 2020-08-24 | Other | TRUE | 5 | J06 | 269 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 23.968 | 8 | 8 | 2020-08-25 |  |  |  |  | 18 |  | 1
269-2 | PM101XA-JW-98388.01-2 | CS | 2020-08-06 | 2020-08-20 | Other | TRUE | 5 | J06 | 269 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 12.672 | 4 | 4 | 2020-08-24 |  |  |  |  | 14 |  | 4
269-3 | PM101XA-JW-98388.01-3 | CS | 2020-08-06 | 2020-08-17 | Other | TRUE | 5 | J06 | 269 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 11 |  | 0 | 3 | 4 | 7
270-1 | PM101XA-JW-98389.01-1 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 5 | J06 | 270 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 8.816 | 3 | 3 | 2020-08-11 |  |  |  |  | 1 |  | 5
270-2 | PM101XA-JW-98389.01-2 | CS |  |  | Other |  | 5 | J06 | 270 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | XS,XS,XS,XS,160,160,XS | 60006000 | 47.248 | 15 | 15
271-1 | PM101XA-JW-98389.02-1 | CS | 2020-08-05 | 2020-08-24 | Other | TRUE | 5 | J06 | 271 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 20.8 | 7 | 7 | 2020-08-24 |  |  |  |  | 19 |  | 0
272-1 | PM101XA-JW-98390.01-1 | CS | 2020-08-05 | 2020-08-28 | Other | TRUE | 5 | J06 | 272 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,160,XSx160,XS,XS,XS,XS |  | 36.576 | 9 | 9 | [5 empty] | 23
272-2 | PM101XA-JW-98390.01-2 | CS |  |  | Other |  | 5 | J06 | 272 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 5.152 | 4 | 4
272-3 | PM101XA-JW-98390.01-3 | CS | 2020-08-20 | 2020-08-25 | Other | TRUE | 5 | J06 | 272 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object] |  |  |  | 0 | 0 | 0 | [5 empty] | 5
273-1 | PM101XA-JW-98390.02-1 | CS |  |  | Other |  | 5 | J06 | 273 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,160,XS,XS | 6000 | 24.528 | 8 | 8
274-1 | PM101XA-JW-98416.01-1 | CS |  |  | Other |  | 5 | J07 | 274 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE,VALVES / IN-LINE ITEMS | 160160160160160 | 6000 | 41.92 | 20 | 20
274-2 | PM101XA-JW-98416.01-2 | CS |  |  | Other |  | 5 | J07 | 274 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 160160160160160 | 6000 | 14.176 | 8 | 8
274-3 | PM101XA-JW-98416.01-3 | CS |  |  | Other |  | 5 | J07 | 274 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 160160160160160 | 6000 | 14.176 | 8 | 8
274-4 | PM101XA-JW-98416.01-4 | CS |  |  | Other |  | 5 | J07 | 274 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 1.6016e+17 | 6000 | 0 | 0 | 0
275-1 | PM101XA-JW-98417.01-1 | CS |  |  | Other |  | 5 | J06 | 275 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160160 | 6000 | 37.984 | 18 | 18
275-2 | PM101XA-JW-98417.01-2 | CS |  |  | Other |  | 5 | J06 | 275 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | SUPPORTS,PIPE,PIPE | 160160160160160 | 6000 | 14.176 | 8 | 8
275-3 | PM101XA-JW-98417.01-3 | CS |  |  | Other |  | 5 | J06 | 275 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 160160160160160 | 6000 | 14.176 | 8 | 8
275-4 | PM101XA-JW-98417.01-4 | CS |  |  | Other |  | 5 | J06 | 275 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,VALVES / IN-LINE ITEMS,PIPE | 160160160160160 | 6000 | 0 | 0 | 0
276-1 | PM101XA-JW-98425.01-1 | CS |  |  | Other |  | 5 | J07 | 276 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS,PIPE,FITTINGS,FITTINGS,FITTINGS,FITTINGS | 160160 |  | 9.328 | 11 | 11
276-2 | PM101XA-JW-98425.01-2 | CS |  |  | Other |  | 5 | J07 | 276 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] | PIPE | 160160 |  | 1.024 | 1 | 1
276-3 | PM101XA-JW-98425.01-3 | CS |  |  | Other |  | 5 | J07 | 276 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE,FITTINGS | 160160160 |  | 2.544 | 3 | 3
276-4 | PM101XA-JW-98425.01-4 | CS |  |  | Other |  | 5 | J07 | 276 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | 160160160 |  | 7.616 | 4 | 4
277-1 | PM101XA-JW-98426.01-1 | CS |  |  | Other |  | 5 | J06 | 277 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE,PIPE,FITTINGS,PIPE,FITTINGS,FITTINGS,FITTINGS,FITTINGS | 160,160,STD,STD,160 |  | 9.328 | 11 | 11
277-2 | PM101XA-JW-98426.01-2 | CS |  |  | Other |  | 5 | J06 | 277 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] | PIPE | 160160 |  | 1.024 | 1 | 1
277-3 | PM101XA-JW-98426.01-3 | CS |  |  | Other |  | 5 | J06 | 277 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE,FITTINGS | 160160160 |  | 2.544 | 3 | 3
277-4 | PM101XA-JW-98426.01-4 | CS |  |  | Other |  | 5 | J06 | 277 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] | PIPE | 160160 |  | 7.232 | 4 | 4
278-1 | PM101XA-JW-100405.01-1 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 5 | J06 | 278 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 8.816 | 3 | 3 | 2020-08-13 |  |  |  |  | 1 |  | 7
278-2 | PM101XA-JW-100405.01-2 | CS |  |  | Other |  | 5 | J06 | 278 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | XS,XS,XS,160,160,XS,XS | 60006000 | 40.336 | 15 | 15
279-1 | PM101XA-JW-100405.02-1 | CS |  |  | Other | TRUE | 5 | J06 | 279 |  | UP |  |  | 1 | 7052 | CP CHEM | Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 160,XS,XS,XS,XS,XSx160,XS,XSx160,XS,XS |  | 55.376 | 15 | 15
280-1 | PM101XA-JW-100405.03-1 | CS |  |  | Other | TRUE | 5 | J06 | 280 |  | UP |  |  | 1 | 7052 | CP CHEM | Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 22.176 | 7 | 7
280-2 | PM101XA-JW-100405.03-2 | CS |  |  | Other |  | 5 | J06 | 280 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,XS,160,XS | 6000 | 31.904 | 10 | 10
281-1 | PM101XA-N-97767.01-1 | CS |  |  | Other |  | 5 | J07 | 281 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160,160,XS |  | 4.72 | 5 | 5
282-1 | PM101XA-N-98377.01-1 | CS |  |  | Other |  | 5 | J07 | 282 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS,PIPE,PIPE | 160160160160 |  | 34.224 | 29 | 29
282-2 | PM101XA-N-98377.01-2 | CS |  |  | Other |  | 5 | J07 | 282 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE,VALVES / IN-LINE ITEMS | 160160160 |  | 10.512 | 9 | 9
283-1 | PM101XA-N-98377.02-1 | CS |  |  | Other |  | 5 | J07 | 283 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 160160160160160 |  | 43.328 | 36 | 36
284-1 | PM101XA-N-98381.01-1 | CS |  |  | Other |  | 5 | J06 | 284 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 160160160160160 |  | 40.928 | 34 | 34
285-1 | PM101XA-N-98381.02-1 | CS |  |  | Other |  | 5 | J06 | 285 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE,VALVES / IN-LINE ITEMS | 160160160160 |  | 31.728 | 27 | 27
285-2 | PM101XA-N-98381.02-2 | CS |  |  | Other |  | 5 | J06 | 285 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE,VALVES / IN-LINE ITEMS | 160160160 |  | 10.512 | 9 | 9
286-1 | PM101XA-N-98383.01-1 | CS |  |  | Other |  | 5 | J06 | 286 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] |  | XS,XS |  | 2.832 | 3 | 3
287-1 | PM101XA-N-100389.01-1 | CS |  |  | Other |  | 5 | J06 | 287 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS |  | 8.496 | 9 | 9
288-1 | PM101XA-N-100390.01-1 | CS |  |  | Other |  | 5 | J07 | 288 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS | XS |  | 8.496 | 9 | 9
289-1 | PM101XA-N-100412.01-1 | CS |  |  | Other |  | 5 | J07 | 289 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 1.888 | 2 | 2
290-1 | PM101XA-N-100413.01-1 | CS |  |  | Other |  | 5 | J06 | 290 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 1.888 | 2 | 2
291-1 | PM101XA-N-100423.01-1 | CS |  |  | Other |  | 5 | J07 | 291 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE,VALVES / IN-LINE ITEMS | 160 |  | 3.6 | 3 | 3
292-1 | PM101XA-N-100424.01-1 | CS |  |  | Other |  | 5 | J06 | 292 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE,VALVES / IN-LINE ITEMS | 160 |  | 3.6 | 3 | 3
293-1 | PM101XA-N-100425.01-1 | CS |  |  | Other |  | 5 | J07 | 293 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] | PIPE | 160160 |  | 1.2 | 1 | 1
294-1 | PM101XA-N-100427.01-1 | CS |  |  | Other |  | 5 | J06 | 294 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] | PIPE | 160160 |  | 1.2 | 1 | 1
296-1 | PM101XA-S-97778.01-1 | CS |  |  | Other |  | 5 | J07 | 296 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 18.432 | 9 | 9
296-2 | PM101XA-S-97778.01-2 | CS |  |  | Other |  | 5 | J07 | 296 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 12.288 | 6 | 6
296-3 | PM101XA-S-97778.01-3 | CS |  |  | Other |  | 5 | J07 | 296 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,160,XS,XSx160,XS,XS,XS,160,XS,XS | 6000 | 38.496 | 17 | 17
297-1 | PM101XA-S-97778.02-1 | CS |  |  | Other |  | 5 | J07 | 297 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,160,XS,XS | 6000 | 11.12 | 6 | 6
297-2 | PM101XA-S-97778.02-2 | CS |  |  | Other |  | 5 | J07 | 297 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160,XS,XS,XS | 6000 | 11.12 | 6 | 6
298-1 | PM101XA-S-97778.03-1 | CS |  |  | Other |  | 5 | J07 | 298 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 160,XS,XS,XS,XS,XSx160,XS,160,160,XS,XS,XS |  | 30.896 | 14 | 14
298-2 | PM101XA-S-97778.03-2 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 5 | J07 | 298 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 10.672 | 5 | 5 | [5 empty] | 11
299-1 | PM101XA-S-98378.01-1 | CS |  |  | Other |  | 5 | J06 | 299 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,XSx160,XS,160,XS,XS,160 | 6000 | 32.352 | 14 | 14
300-1 | PM101XA-S-98378.02-1 | CS |  |  | Other |  | 5 | J06 | 300 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,160,XS,XS | 6000 | 11.12 | 6 | 6
300-2 | PM101XA-S-98378.02-2 | CS |  |  | Other |  | 5 | J06 | 300 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,160,XS | 6000 | 11.12 | 6 | 6
301-1 | PM101XA-S-98378.03-1 | CS |  |  | Other |  | 5 | J06 | 301 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | XS,160,160,XS,XSx160,XS,XS,XS,XS,XS,XS,160 |  | 30.896 | 14 | 14
301-2 | PM101XA-S-98378.03-2 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 5 | J06 | 301 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 10.672 | 5 | 5 | [5 empty] | 11
302-1 | PM101XA-V-97769.01-1 | CS |  |  | Other |  | 5 | J07 | 302 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1
303-1 | PM101XA-V-98386.01-1 | CS |  |  | Other |  | 5 | J06 | 303 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1
304-1 | PM101XA-V-100426.01-1 | CS |  |  | Other |  | 5 | J07 | 304 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS |  | 6.608 | 7 | 7
305-1 | PM101XA-V-100428.01-1 | CS |  |  | Other |  | 5 | J06 | 305 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS |  | 6.608 | 7 | 7
308-1 | PM102XA-C-97608.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 308 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,40Sx80S,40Sx80S,80S,80S,40S,80S,80S |  | 22.316 | 9 | 9
308-2 | PM102XA-C-97608.01-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 308 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
309-1 | PM102XA-C-97608.02-1 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 309 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 15.96 | 6 | 6 | [5 empty] | 5
309-2 | PM102XA-C-97608.02-2 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 309 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S |  | 5.32 | 2 | 2 | [5 empty] | 5
310-1 | PM102XA-C-97608.03-1 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 310 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 21.28 | 8 | 8 | [5 empty] | 5
310-2 | PM102XA-C-97608.03-2 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 310 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 21.28 | 8 | 8 | [5 empty] | 5
311-1 | PM102XA-C-97625.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 311 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40Sx80S,40S,40S,80S,80S | 3000 | 19.432 | 8 | 8
311-2 | PM102XA-C-97625.01-2 | 304/304L SS | 2020-08-13 | 2020-08-17 | Other | TRUE | 7 | J04 | 311 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  | 80S |  | 0 | 0 | 0 | 2020-08-17 |  |  |  |  | 4 |  | 0
311-3 | PM102XA-C-97625.01-3 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 7 | J04 | 311 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
312-1 | PM102XA-C-97625.02-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 312 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40Sx80S,40S,40S,40S,80S |  | 18.788 | 7 | 7
312-2 | PM102XA-C-97625.02-2 | 304/304L SS | 2020-08-11 |  | Other | TRUE | 7 | J04 | 312 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object] |  |  |  | 0 | 0 | 0
313-1 | PM102XA-C-97625.03-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 313 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S,40S,40S |  | 21.504 | 8 | 8 | [5 empty] | 1
313-2 | PM102XA-C-97625.03-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 313 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
313-3 | PM102XA-C-97625.03-3 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 313 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
313-4 | PM102XA-C-97625.03-4 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 313 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 13.44 | 5 | 5 | 2020-09-02 |  |  |  |  | 1 |  | 8
313-5 | PM102XA-C-97625.03-5 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 313 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S,40S |  | 18.816 | 7 | 7 | [5 empty] | 1
314-1 | PM102XA-C-97626.01-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 314 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S,40S |  | 18.816 | 7 | 7 | [5 empty] | 1
314-2 | PM102XA-C-97626.01-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 314 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 13.44 | 5 | 5 | 2020-09-02 |  |  |  |  | 1 |  | 8
314-3 | PM102XA-C-97626.01-3 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 314 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 16.128 | 6 | 6 | 2020-09-02 |  |  |  |  | 1 |  | 8
315-1 | PM102XA-C-97626.02-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 315 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40S,40S,40S,40S,40S,80S | 3000 | 30.548 | 12 | 12
315-2 | PM102XA-C-97626.02-2 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 315 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object] |  |  |  | 0 | 0 | 0
316-1 | PM102XA-C-97626.03-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 316 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,80S,40Sx80S,40S,40S,80S,80S | 30003000 | 24.976 | 10 | 10
316-2 | PM102XA-C-97626.03-2 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 7 | J04 | 316 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
316-3 | PM102XA-C-97626.03-3 | 304/304L SS | 2020-08-11 |  | Other | TRUE | 7 | J04 | 316 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object] |  |  |  | 0 | 0 | 0
317-1 | PM102XA-C-97626.04-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 317 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,40Sx80S,80S,80S,80S,80S,40S,80S,80S,80S,80S |  | 36.932 | 14 | 14
318-1 | PM102XA-C-97626.05-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 318 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 13.3 | 5 | 5
318-2 | PM102XA-C-97626.05-2 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 318 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 20.944 | 8 | 8
318-3 | PM102XA-C-97626.05-3 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 318 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object] |  |  |  | 0 | 0 | 0
319-1 | PM102XA-C-97626.06-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 319 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object] |  | 80S,80S |  | 2.324 | 1 | 1 | [5 empty] | 7
319-2 | PM102XA-C-97626.06-2 | 304/304L SS | 2020-08-13 | 2020-08-17 | Other | TRUE | 7 | J04 | 319 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  | 80S |  | 1.932 | 1 | 1 | 2020-08-17 |  |  |  |  | 4 |  | 0
320-1 | PM102XA-C-97629.01-1 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 320 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S |  | 10.64 | 4 | 4 | [5 empty] | 5
320-2 | PM102XA-C-97629.01-2 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 320 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 20.944 | 8 | 8 | [5 empty] | 5
320-3 | PM102XA-C-97629.01-3 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 7 | J04 | 320 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
321-1 | PM102XA-C-97630.01-1 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 321 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 15.96 | 6 | 6 | [5 empty] | 5
321-2 | PM102XA-C-97630.01-2 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 321 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 18.62 | 7 | 7 | [5 empty] | 5
321-3 | PM102XA-C-97630.01-3 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 321 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S |  | 5.32 | 2 | 2 | [5 empty] | 5
321-4 | PM102XA-C-97630.01-4 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 321 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S |  | 10.64 | 4 | 4 | [5 empty] | 5
322-1 | PM102XA-C-97631.01-1 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 322 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S |  | 10.64 | 4 | 4 | [5 empty] | 5
323-1 | PM102XA-C-97632.01-1 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 323 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 13.3 | 5 | 5 | [5 empty] | 5
323-2 | PM102XA-C-97632.01-2 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 323 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S |  | 10.64 | 4 | 4 | [5 empty] | 5
324-1 | PM102XA-C-97635.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 324 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40Sx80S,40Sx80S,80S,80S,80S,40S,40S,80S,80S |  | 37.38 | 14 | 14
325-1 | PM102XA-C-97635.02-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 325 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40S,40S,80S | 3000 | 14.42 | 6 | 6 | 2020-09-02 |  |  |  |  | 1 |  | 8
325-2 | PM102XA-C-97635.02-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 325 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-28 |  |  |  |  | 1 |  | 3
325-3 | PM102XA-C-97635.02-3 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 7 | J04 | 325 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
326-1 | PM102XA-C-97635.03-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 326 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40S,40S,80S | 3000 | 14.42 | 6 | 6 | 2020-09-02 |  |  |  |  | 1 |  | 8
326-2 | PM102XA-C-97635.03-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 326 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | [5 empty] | 1
326-3 | PM102XA-C-97635.03-3 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 7 | J04 | 326 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
327-1 | PM102XA-C-97636.01-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 327 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS | 40S,40S,40Sx80S,40S,40Sx80S,40Sx80S,80S,80S,80S |  | 26.992 | 8 | 8
328-1 | PM102XA-C-97636.02-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 328 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 15.624 | 6 | 6
328-2 | PM102XA-C-97636.02-2 | 304/304L SS |  |  | Other |  | 7 | J04 | 328 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  |  |  | 0 | 0 | 0
329-1 | PM102XA-C-97636.03-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 329 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,40Sx80S,80S,40S,80S |  | 13.328 | 5 | 5
330-1 | PM102XA-C-97637.01-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 330 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS | 40S,40S,40Sx80S,40S,40Sx80S,40Sx80S,80S,80S,80S |  | 26.992 | 8 | 8
331-1 | PM102XA-C-97637.02-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 331 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 12.964 | 5 | 5
331-2 | PM102XA-C-97637.02-2 | 304/304L SS |  |  | Other |  | 7 | J04 | 331 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  |  |  | 0 | 0 | 0
332-1 | PM102XA-C-97637.03-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 332 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,40Sx80S,80S,40S,80S |  | 13.328 | 5 | 5
333-1 | PM102XA-C-97638.01-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 333 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40S,40S,40S,40S,80S | 3000 | 22.484 | 9 | 9 | 2020-09-02 |  |  |  |  | 1 |  | 8
333-2 | PM102XA-C-97638.01-2 | 304/304L SS |  |  | Other |  | 7 | J04 | 333 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS | 40S,40S,40S,40S,40S |  | 13.44 | 5 | 5
334-1 | PM102XA-C-97638.02-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 334 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS | 40S,80S,40Sx80S,40S,40S,40S,80S,80S,40S,80S |  | 29.428 | 11 | 11
335-1 | PM102XA-C-97638.03-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 335 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40S,80S,80S | 30003000 | 16.604 | 7 | 7 | [5 empty] | 1
335-2 | PM102XA-C-97638.03-2 | 304/304L SS | 2020-08-13 | 2020-08-17 | Other | TRUE | 7 | J04 | 335 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  | 80S |  | 1.932 | 1 | 1 | 2020-08-17 |  |  |  |  | 4 |  | 0
335-3 | PM102XA-C-97638.03-3 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 7 | J04 | 335 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
336-1 | PM102XA-C-97641.01-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 336 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 13.16 | 4 | 4 | 2020-09-02 |  |  |  |  | 1 |  | 8
336-2 | PM102XA-C-97641.01-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 336 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 16.128 | 6 | 6 | [5 empty] | 1
337-1 | PM102XA-C-97642.01-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 337 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 13.16 | 4 | 4 | 2020-09-02 |  |  |  |  | 1 |  | 8
337-2 | PM102XA-C-97642.01-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 337 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 16.128 | 6 | 6 | 2020-09-02 |  |  |  |  | 1 |  | 8
338-1 | PM102XA-C-98412.01-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 338 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 23.24 | 10 | 10 | [5 empty] | 7
339-1 | PM102XA-C-98412.02-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 339 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S,80S |  | 20.916 | 9 | 9 | [5 empty] | 7
339-2 | PM102XA-C-98412.02-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 339 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 11.62 | 5 | 5 | [5 empty] | 7
340-1 | PM102XA-C-98424.01-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 340 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 19.656 | 6 | 6
341-1 | PM102XA-C-100210.01-1 | 304/304L SS | 2020-08-11 | 2020-08-11 | Other | TRUE | 7 | J04 | 341 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S |  | 13.44 | 5 | 5 | 2020-08-18 |  |  |  |  | 0 |  | 7
342-1 | PM102XA-C-100409.01-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 342 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40S,40S,40S,40S,40S,40S,40S,40S,40S,40S,80S,80S,80S,80S | 3000300030003000 | 82.628 | 30 | 30
343-1 | PM102XA-C-100409.03-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 343 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 13.944 | 6 | 6 | [5 empty] | 7
343-2 | PM102XA-C-100409.03-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 343 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | 80S,80S,80S |  | 0 | 0 | 0 | [5 empty] | 7
343-3 | PM102XA-C-100409.03-3 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 7 | J04 | 343 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
343-4 | PM102XA-C-100409.03-4 | 304/304L SS | 2020-08-04 | 2020-08-06 | Other | TRUE | 7 | J04 | 343 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 2 |  | 4
344-1 | PM102XA-C-100409.04-1 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 344 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 13.944 | 6 | 6 | [5 empty] | 7
344-2 | PM102XA-C-100409.04-2 | 304/304L SS | 2020-08-24 | 2020-08-31 | Other | TRUE | 7 | J04 | 344 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | 80S,80S,80S |  | 0 | 0 | 0 | [5 empty] | 7
344-3 | PM102XA-C-100409.04-3 | 304/304L SS | 2020-08-03 | 2020-08-06 | Other | TRUE | 7 | J04 | 344 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 3 |  | 4
344-4 | PM102XA-C-100409.04-4 | 304/304L SS | 2020-08-04 | 2020-08-06 | Other | TRUE | 7 | J04 | 344 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 2 |  | 4
345-1 | PM102XA-C-100411.02-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 345 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S,40S |  | 18.816 | 7 | 7 | 2020-09-02 |  |  |  |  | 1 |  | 8
346-1 | PM102XA-CCW-97620.01-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 346 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-13 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 2 | 7 | 4 | 11
346-2 | PM102XA-CCW-97620.01-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 346 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 15.92 | 8 | 8 | 2020-08-20 |  |  |  |  | 0 |  | 9
347-1 | PM102XA-CCW-97620.02-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 347 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 4.848 | 3 | 3 | 2020-08-20 |  |  |  |  | 0 |  | 9
347-2 | PM102XA-CCW-97620.02-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 347 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-20 |  |  |  |  | 0 |  | 9
348-1 | PM102XA-CCW-97620.03-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 348 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-20 |  |  |  |  | 0 |  | 9
348-2 | PM102XA-CCW-97620.03-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 348 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 4.848 | 3 | 3 | 2020-08-17 |  |  |  |  | 0 |  | 6
349-1 | PM102XA-CCW-97620.04-1 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 6 | J21 | 349 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS,XS | 3000 | 14.8 | 11 | 11 | 2020-08-24 |  |  |  |  | 2 |  | 5
349-2 | PM102XA-CCW-97620.04-2 | CS | 2020-08-03 | 2020-08-03 | Other | TRUE | 6 | J21 | 349 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-05 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 2 | 15 | 4 | 19
350-1 | PM102XA-CCW-97621.01-1 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 6 | J21 | 350 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS | 3000 | 13.456 | 11 | 11 | 2020-08-24 |  |  |  |  | 2 |  | 5
350-2 | PM102XA-CCW-97621.01-2 | CS | 2020-08-03 | 2020-08-03 | Other | TRUE | 6 | J21 | 350 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-05 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 2 | 15 | 4 | 19
351-1 | PM102XA-CCW-97621.02-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 351 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 4.848 | 3 | 3 | 2020-08-17 |  |  |  |  | 0 |  | 6
351-2 | PM102XA-CCW-97621.02-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 351 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
352-1 | PM102XA-CCW-97621.03-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 352 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
352-2 | PM102XA-CCW-97621.03-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 352 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 4.848 | 3 | 3 | 2020-08-19 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 8 | 1 | 4 | 5
353-1 | PM102XA-CCW-97621.04-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 353 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 15.92 | 8 | 8 | 2020-08-24 |  |  |  |  | 0 |  | 13
353-2 | PM102XA-CCW-97621.04-2 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 6 | J21 | 353 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-17 |  | 2020-08-20 | 2020-08-24 |  | 0 |  | 6 | 3 | 4 | 7
354-1 | PM102XA-CW-97784.01-1 | CS |  |  | Other |  | 6 | J20 | 354 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS,XS |  | 2.832 | 3 | 3
354-2 | PM102XA-CW-97784.01-2 | CS | 2020-08-11 | 2020-08-13 | Other |  | 6 | J20 | 354 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 7.408 | 7 | 7 | [5 empty] | 2
354-3 | PM102XA-CW-97784.01-3 | CS | 2020-08-26 | 2020-08-28 | Other | TRUE | 6 | J20 | 354 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 9.936 | 9 | 9 | [5 empty] | 2
355-1 | PM102XA-CW-97785.01-1 | CS |  |  | Other |  | 6 | J20 | 355 |  | X |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 9.936 | 9 | 9
355-2 | PM102XA-CW-97785.01-2 | CS | 2020-08-05 | 2020-08-10 | Other | TRUE | 6 | J20 | 355 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 2.912 | 2 | 2 | 2020-08-12 |  | 2020-08-20 | 2020-08-24 |  | 5 |  | 2 | 8 | 4 | 12
355-3 | PM102XA-CW-97785.01-3 | CS | 2020-08-11 | 2020-08-13 | Other | TRUE | 6 | J20 | 355 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 6.464 | 6 | 6 | 2020-08-20 |  |  |  |  | 2 |  | 7
355-4 | PM102XA-CW-97785.01-4 | CS |  |  | Other |  | 6 | J20 | 355 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS,XS |  | 2.832 | 3 | 3
356-1 | PM102XA-N-102360.01-1 | CS |  |  | Other |  | 7 | J04 | 356 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS,XS |  | 17.776 | 11 | 11
356-2 | PM102XA-N-102360.01-2 | CS |  |  | Other |  | 7 | J04 | 356 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2
356-3 | PM102XA-N-102360.01-3 | CS |  |  | Other |  | 7 | J04 | 356 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 11.312 | 7 | 7
356-4 | PM102XA-N-102360.01-4 | CS |  |  | Other |  | 7 | J04 | 356 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 14.032 | 9 | 9
357-1 | PM102XA-P-3023.01-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 357 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | FITTINGS | 40S,40Sx80S,40Sx80S,40S,40S,40S,80S,80S |  | 21.448 | 8 | 8
358-1 | PM102XA-P-3023.02-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 7 | J04 | 358 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S |  | 10.752 | 4 | 4 | 2020-09-02 |  |  |  |  | 1 |  | 8
359-1 | PM102XA-T-97611.01-1 | A333 | 2020-08-05 | 2020-08-10 | Other | TRUE | 6 | J20 | 359 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 5.2 | 5 | 5 | 2020-08-11 |  | 2020-08-20 | 2020-08-24 |  | 5 |  | 1 | 9 | 4 | 13
360-1 | PM102XA-T-97612.01-1 | A333 | 2020-08-11 | 2020-08-13 | Other | TRUE | 6 | J20 | 360 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 160160160 |  | 3.968 | 3 | 3 | 2020-08-17 |  |  |  |  | 2 |  | 4
361-1 | PM102XA-T-97613.01-1 | A333 | 2020-08-11 | 2020-08-13 | Other | TRUE | 6 | J20 | 361 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XXS,160,XXSx160,XXS,160 |  | 18.848 | 13 | 13 | 2020-08-24 |  |  |  |  | 2 |  | 11
362-1 | PM102XA-T-97617.01-1 | A333 |  |  | Other |  | 6 | J21 | 362 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS,VALVES / IN-LINE ITEMS | XS,XS,XS,XS,XS,XS |  | 15.472 | 15 | 15 | [6 empty] | TRUE
363-1 | PM102XA-T-97617.02-1 | A333 | 2020-08-05 | 2020-08-10 | Other | TRUE | 6 | J21 | 363 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 4.256 | 4 | 4 | 2020-08-11 |  |  |  |  | 5 |  | 1
364-1 | PM102XA-T-97618.01-1 | A333 |  |  | Other |  | 6 | J21 | 364 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS | XS,XS,XS,XS,XS,XS,XS,XS,XS |  | 20.176 | 15 | 15 | [6 empty] | TRUE
365-1 | PM102XA-T-97618.02-1 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J21 | 365 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-20 |  |  |  |  | 4 |  | 3
365-2 | PM102XA-T-97618.02-2 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J21 | 365 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 11.312 | 7 | 7 | 2020-08-20 |  |  |  |  | 4 |  | 3
366-1 | PM102XA-T-97618.03-1 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J21 | 366 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 8.08 | 5 | 5 | 2020-08-20 |  |  |  |  | 4 |  | 3
366-2 | PM102XA-T-97618.03-2 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J21 | 366 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-20 |  |  |  |  | 4 |  | 3
367-1 | PM102XA-T-97618.04-1 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J21 | 367 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS | 3000 | 7.92 | 5 | 5 | 2020-08-20 |  |  |  |  | 4 |  | 3
368-1 | PM102XA-T-97618.05-1 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J21 | 368 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 4.848 | 3 | 3 | 2020-08-19 |  |  |  |  | 4 |  | 2
368-2 | PM102XA-T-97618.05-2 | A333 |  |  | Other |  | 6 | J21 | 368 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS | XS,XS,XS,XS,XS,XS,XS,XS | 30003000 | 16.592 | 12 | 12 | [6 empty] | TRUE
369-1 | PM102XA-T-97619.01-1 | A333 |  |  | Other |  | 6 | J21 | 369 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS | XS,XS,XS,XS,XS,XS | 3000 | 10.464 | 8 | 8 | [6 empty] | TRUE
369-2 | PM102XA-T-97619.01-2 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J21 | 369 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 8.08 | 5 | 5 | 2020-08-20 |  |  |  |  | 4 |  | 3
370-1 | PM102XA-T-97619.02-1 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J20 | 370 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS | 3000 | 7.92 | 5 | 5 | 2020-08-19 |  |  |  |  | 4 |  | 2
370-2 | PM102XA-T-97619.02-2 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J20 | 370 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-19 |  |  |  |  | 4 |  | 2
371-1 | PM102XA-T-97619.03-1 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J20 | 371 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 8.08 | 5 | 5 | 2020-08-20 |  |  |  |  | 4 |  | 3
371-2 | PM102XA-T-97619.03-2 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J20 | 371 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 11.312 | 7 | 7 | 2020-08-19 |  |  |  |  | 4 |  | 2
372-1 | PM102XA-T-97619.04-1 | A333 | 2020-08-13 | 2020-08-17 | Other | TRUE | 6 | J20 | 372 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 12.768 | 8 | 8 | 2020-08-19 |  |  |  |  | 4 |  | 2
373-1 | PM102XA-T-97619.05-1 | A333 |  |  | Other |  | 6 | J20 | 373 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS | XS,XS,XS,XS,XS,XS | 3000 | 11.568 | 9 | 9 | [6 empty] | TRUE
374-1 | PM102XA-T-100422.01-1 | A333 |  |  | Other |  | 6 | J20 | 374 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS | XS,XS,XS,XS,XS |  | 18.448 | 17 | 17 | [6 empty] | TRUE
375-1 | PM102XA-TR-F140E.02-1 | 304/304L SS |  |  | Other |  | 7 | J04 | 375 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | 80S,80S,80S |  | 4.704 | 2 | 2
375-2 | PM102XA-TR-F140E.02-2 | 304/304L SS |  |  | Other |  | 7 | J04 | 375 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 13.552 | 6 | 6
375-3 | PM102XA-TR-F140E.02-3 | 304/304L SS |  |  | Other |  | 7 | J04 | 375 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] |  |  |  | 0 | 0 | 0
376-1 | PM102XA-V-97622.01-1 | 304/304L SS CRYO |  |  | Other |  | 6 | J21 | 376 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS | 40S,80S,40S,40S | 3000 | 12.376 | 6 | 6 | [6 empty] | TRUE
376-2 | PM102XA-V-97622.01-2 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 6 | J21 | 376 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,80S,40S,40S,40S,80S | 3000 | 17.052 | 7 | 7 | [5 empty] | 5
377-1 | PM102XA-V-97622.02-1 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 6 | J21 | 377 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | [5 empty] | 5
377-2 | PM102XA-V-97622.02-2 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 6 | J21 | 377 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | [5 empty] | 5
378-1 | PM102XA-V-97622.03-1 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 6 | J21 | 378 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S |  | 8.064 | 3 | 3 | [5 empty] | 5
378-2 | PM102XA-V-97622.03-2 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 6 | J21 | 378 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 13.44 | 5 | 5 | [5 empty] | 5
379-1 | PM102XA-V-97622.04-1 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 6 | J21 | 379 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | [5 empty] | 5
379-2 | PM102XA-V-97622.04-2 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 6 | J21 | 379 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | [5 empty] | 5
379-3 | PM102XA-V-97622.04-3 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 6 | J21 | 379 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S,40S,40S |  | 21.504 | 8 | 8 | [5 empty] | 5
380-1 | PM102XA-V-97622.05-1 | 304/304L SS CRYO | 2020-08-26 | 2020-08-31 | Other | TRUE | 6 | J21 | 380 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S |  | 19.824 | 12 | 12 | [5 empty] | 5
381-1 | PM103XA-CS-97420.01-1 | CS |  |  | Other |  | 8 | J10 | 381 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.168 | 2 | 2
382-1 | PM103XA-CS-97781.01-1 | CS |  |  | Other |  | 8 | J10 | 382 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,XS,STD,STD,STD,STD,STD,STD,XS | 3000 | 37.104 | 17 | 17
382-2 | PM103XA-CS-97781.01-2 | CS |  |  | Other |  | 8 | J10 | 382 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold |  |  |  |  | 15.024 | 3 | 3
382-3 | PM103XA-CS-97781.01-3 | CS |  |  | Other |  | 8 | J10 | 382 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold |  |  |  |  | 0 | 0 | 0
383-1 | PM103XA-CS-97781.02-1 | CS | 2020-08-05 |  | Other |  | 8 | J10 | 383 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object] |  | STD,STD,XS |  | 4.288 | 2 | 2
384-1 | PM103XA-CS-97782.01-1 | CS |  |  | Other |  | 8 | J10 | 384 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE,PIPE | 1.6016e+23 |  | 23.68 | 14 | 14
385-1 | PM103XA-CS-97782.02-1 | CS |  |  | Other |  | 8 | J10 | 385 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 1.6016e+17 | 6000 | 18.112 | 10 | 10
386-1 | PM103XA-CS-97782.03-1 | CS |  |  | Other |  | 8 | J10 | 386 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160160 |  | 3.936 | 2 | 2
386-2 | PM103XA-CS-97782.03-2 | CS |  |  | Other |  | 8 | J10 | 386 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160 |  | 7.872 | 4 | 4
387-1 | PM103XA-CS-97783.01-1 | CS |  |  | Other |  | 8 | J10 | 387 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 8.08 | 5 | 5
388-1 | PM104XA-CNV-97730.01-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 388 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | FITTINGS,FLANGES,FLANGES |  |  | 101.088 | 10 | 10
388-2 | PM104XA-CNV-97730.01-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 388 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 86.016 | 7 | 7
389-1 | PM104XA-CNV-97730.02-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 389 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 73.728 | 6 | 6
389-2 | PM104XA-CNV-97730.02-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 389 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
389-3 | PM104XA-CNV-97730.02-3 | ALUMINUM |  |  | Other |  | 8 | J25 | 389 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
390-1 | PM104XA-CNV-97730.03-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 390 |  | UP |  | Hold | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
390-2 | PM104XA-CNV-97730.03-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 390 |  | UP |  | Hold | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
390-3 | PM104XA-CNV-97730.03-3 | ALUMINUM |  |  | Other |  | 8 | J25 | 390 |  | UP |  | Hold | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
390-4 | PM104XA-CNV-97730.03-4 | ALUMINUM |  |  | Other |  | 8 | J25 | 390 |  | UP |  | Hold | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | FITTINGS,FLANGES,FLANGES | STD |  | 61.44 | 5 | 5
391-1 | PM104XA-CNV-97730.04-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 391 |  | UP |  | Hold | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 86.016 | 7 | 7
391-2 | PM104XA-CNV-97730.04-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 391 |  | UP |  | Hold | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | STD |  | 110.592 | 9 | 9
392-1 | PM104XA-CNV-97730.05-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 392 |  | UP |  | Hold | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE,FLANGES,FLANGES | STD |  | 61.44 | 5 | 5
392-2 | PM104XA-CNV-97730.05-2 | ALUMINUM |  |  | Other |  | 8 | J25 | 392 |  | UP |  | Hold | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 49.152 | 4 | 4
392-3 | PM104XA-CNV-97730.05-3 | ALUMINUM |  |  | Other |  | 8 | J25 | 392 |  | UP |  | Hold | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | FLANGES,FLANGES |  |  | 73.728 | 6 | 6
393-1 | PM104XA-CNV-98368.01-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 393 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | PIPE | 40 |  | 0 | 0 | 0
394-1 | PM104XA-CNV-98369.01-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 394 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | PIPE | 40 |  | 0 | 0 | 0
395-1 | PM104XA-CNV-98370.01-1 | ALUMINUM |  |  | Other |  | 8 | J25 | 395 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | PIPE | 40 |  | 0 | 0 | 0
396-1 | PM104XA-CW-97720.01-1 | CS | 2020-08-20 |  | Other | TRUE | 8 | J25 | 396 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD,STD | 3000 | 18.208 | 10 | 10
397-1 | PM104XA-CW-97720.02-1 | CS |  |  | Other |  | 8 | J25 | 397 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,XS,STD,STD,STD | 3000 | 11.488 | 8 | 8
398-1 | PM104XA-CW-97721.01-1 | CS |  |  | Other |  | 8 | J25 | 398 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,XS,STD,STD,STD,STD,STD,STD,STD,STD,XS | 3000 | 41.072 | 18 | 18
399-1 | PM104XA-CW-97721.02-1 | CS | 2020-08-24 |  | Other | TRUE | 8 | J25 | 399 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | STD,STD,STD,STD,STD,STD | 3000 | 18.208 | 10 | 10
400-1 | PM110XA-C-97625.01-1 | 304/304L SS |  |  | Other |  | 4 | J32 | 400 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 13.44 | 5 | 5
400-2 | PM110XA-C-97625.01-2 | 304/304L SS |  |  | Other |  | 4 | J32 | 400 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S | 3000 | 7.756 | 3 | 3
400-3 | PM110XA-C-97625.01-3 | 304/304L SS |  |  | Other |  | 4 | J32 | 400 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2
400-4 | PM110XA-C-97625.01-4 | 304/304L SS |  |  | Other |  | 4 | J32 | 400 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 10.752 | 4 | 4
400-5 | PM110XA-C-97625.01-5 | 304/304L SS |  |  | Other |  | 4 | J32 | 400 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2
401-1 | PM110XA-C-97625.02-1 | 304/304L SS | 2020-08-11 | 2020-08-11 | Other | TRUE | 4 | J32 | 401 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-13 |  |  |  |  | 0 |  | 2
401-2 | PM110XA-C-97625.02-2 | 304/304L SS | 2020-08-11 | 2020-08-11 | Other | TRUE | 4 | J32 | 401 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-12 |  |  |  |  | 0 |  | 1
401-3 | PM110XA-C-97625.02-3 | 304/304L SS | 2020-08-11 | 2020-08-11 | Other | TRUE | 4 | J32 | 401 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-12 |  |  |  |  | 0 |  | 1
401-4 | PM110XA-C-97625.02-4 | 304/304L SS | 2020-08-11 | 2020-08-11 | Other | TRUE | 4 | J32 | 401 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-08-13 |  |  |  |  | 0 |  | 2
401-5 | PM110XA-C-97625.02-5 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 401 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
401-6 | PM110XA-C-97625.02-6 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 401 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 16.128 | 6 | 6 | 2020-09-02 |  |  |  |  | 1 |  | 8
402-1 | PM110XA-C-97625.03-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 402 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S | 3000 | 18.508 | 7 | 7 | 2020-09-02 |  |  |  |  | 1 |  | 8
402-2 | PM110XA-C-97625.03-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 402 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | [5 empty] | 1
402-3 | PM110XA-C-97625.03-3 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 402 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
402-4 | PM110XA-C-97625.03-4 | 304/304L SS |  |  | Other |  | 4 | J32 | 402 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2
403-1 | PM110XA-C-97625.04-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 403 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
403-2 | PM110XA-C-97625.04-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 403 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
403-3 | PM110XA-C-97625.04-3 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 403 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-02 |  |  |  |  | 1 |  | 8
403-4 | PM110XA-C-97625.04-4 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 403 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-02 |  |  |  |  | 1 |  | 8
403-5 | PM110XA-C-97625.04-5 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 403 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 13.44 | 5 | 5 | [5 empty] | 1
404-1 | PM110XA-C-97626.01-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 404 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 16.128 | 6 | 6 | 2020-09-02 |  |  |  |  | 1 |  | 8
404-2 | PM110XA-C-97626.01-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 404 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
404-3 | PM110XA-C-97626.01-3 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 404 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
404-4 | PM110XA-C-97626.01-4 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 404 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-02 |  |  |  |  | 1 |  | 8
404-5 | PM110XA-C-97626.01-5 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 404 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
405-1 | PM110XA-C-97626.02-1 | 304/304L SS | 2020-08-24 | ISO NO. | Other | TRUE | 4 | J32 | 405 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01
405-2 | PM110XA-C-97626.02-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 405 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
405-3 | PM110XA-C-97626.02-3 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 405 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
405-4 | PM110XA-C-97626.02-4 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 405 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
406-1 | PM110XA-C-97626.03-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 406 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
406-2 | PM110XA-C-97626.03-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 406 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
406-3 | PM110XA-C-97626.03-3 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 406 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-02 |  |  |  |  | 1 |  | 8
406-4 | PM110XA-C-97626.03-4 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 406 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
407-1 | PM110XA-C-97626.04-1 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 407 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
407-2 | PM110XA-C-97626.04-2 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 407 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 13.44 | 5 | 5 | 2020-09-02 |  |  |  |  | 1 |  | 8
407-3 | PM110XA-C-97626.04-3 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 407 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S |  | 5.376 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 7
407-4 | PM110XA-C-97626.04-4 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 407 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S | 3000 | 7.756 | 3 | 3 | 2020-09-01 |  |  |  |  | 1 |  | 7
407-5 | PM110XA-C-97626.04-5 | 304/304L SS | 2020-08-24 | 2020-08-25 | Other | TRUE | 4 | J32 | 407 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 40S,40S,40S,40S,40S |  | 13.44 | 5 | 5 | [5 empty] | 1
408-1 | PM110XA-CCW-97620.01-1 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 4 | J32 | 408 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS | 3000 | 11.152 | 7 | 7 | 2020-08-12 |  |  |  |  | 1 |  | 6
408-2 | PM110XA-CCW-97620.01-2 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 4 | J32 | 408 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-13 |  |  |  |  | 1 |  | 7
409-1 | PM110XA-CCW-97620.02-1 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 4 | J32 | 409 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 4.848 | 3 | 3 | 2020-08-20 |  |  |  |  | 1 |  | 14
409-2 | PM110XA-CCW-97620.02-2 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 4 | J32 | 409 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 14.544 | 9 | 9 | 2020-08-13 |  |  |  |  | 1 |  | 7
410-1 | PM110XA-CCW-97620.03-1 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 4 | J32 | 410 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS | 3000 | 10.464 | 8 | 8 | 2020-08-25 |  |  |  |  | 2 |  | 6
410-2 | PM110XA-CCW-97620.03-2 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 4 | J32 | 410 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-11 |  |  |  |  | 1 |  | 5
411-1 | PM110XA-CCW-97620.04-1 | CS | 2020-08-05 | 2020-08-10 | Other | TRUE | 4 | J32 | 411 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS | 3000 | 6.304 | 4 | 4 | 2020-08-20 |  |  |  |  | 5 |  | 10
411-2 | PM110XA-CCW-97620.04-2 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 4 | J32 | 411 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 11.312 | 7 | 7 | 2020-08-12 |  |  |  |  | 1 |  | 6
412-1 | PM110XA-CCW-97621.01-1 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 4 | J32 | 412 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 11.312 | 7 | 7 | 2020-08-12 |  |  |  |  | 1 |  | 6
412-2 | PM110XA-CCW-97621.01-2 | CS | 2020-08-05 | 2020-08-10 | Other | TRUE | 4 | J32 | 412 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS | 3000 | 6.304 | 4 | 4 | 2020-08-12 |  |  |  |  | 5 |  | 2
413-1 | PM110XA-CCW-97621.02-1 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 4 | J32 | 413 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-12 |  | 2020-08-20 | 2020-08-24 |  | 1 |  | 6 | 8 | 4 | 12
413-2 | PM110XA-CCW-97621.02-2 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 4 | J32 | 413 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS | 3000 | 8.848 | 7 | 7 | 2020-08-25 |  |  |  |  | 2 |  | 6
414-1 | PM110XA-CCW-97621.03-1 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 4 | J32 | 414 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 14.544 | 9 | 9 | 2020-08-13 |  |  |  |  | 1 |  | 7
414-2 | PM110XA-CCW-97621.03-2 | CS | 2020-08-05 | 2020-08-06 | Other | TRUE | 4 | J32 | 414 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Shipped to Coating | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-08-13 |  | 2020-08-20 | 2020-08-24 |  | 1 |  | 7 | 7 | 4 | 11
415-1 | PM110XA-CCW-97621.04-1 | CS | 2020-08-05 | 2020-08-13 | Other | TRUE | 4 | J32 | 415 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 6.464 | 4 | 4 | [5 empty] | 8
415-2 | PM110XA-CCW-97621.04-2 | CS | 2020-08-05 | 2020-08-10 | Other | TRUE | 4 | J32 | 415 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS | 3000 | 11.152 | 7 | 7 | 2020-08-12 |  |  |  |  | 5 |  | 2
416-1 | PM110XA-CS-97779.01-1 | CS |  |  | Other |  | 4 | J32 | 416 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1
416-2 | PM110XA-CS-97779.01-2 | CS |  |  | Other |  | 4 | J32 | 416 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
416-3 | PM110XA-CS-97779.01-3 | CS |  |  | Other |  | 4 | J32 | 416 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1
417-1 | PM110XA-CS-97779.02-1 | CS |  |  | Other |  | 4 | J32 | 417 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS,XS |  | 16.16 | 10 | 10
418-1 | PM110XA-CS-97779.03-1 | CS | 2020-09-01 |  | Other | TRUE | 4 | J32 | 418 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2
418-2 | PM110XA-CS-97779.03-2 | CS | 2020-09-01 |  | Other | TRUE | 4 | J32 | 418 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2
418-3 | PM110XA-CS-97779.03-3 | CS | 2020-09-01 |  | Other | TRUE | 4 | J32 | 418 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS | 3000 | 11.232 | 8 | 8
419-1 | PM110XA-CS-97779.04-1 | CS |  |  | Other |  | 4 | J32 | 419 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 9.696 | 6 | 6
419-2 | PM110XA-CS-97779.04-2 | CS |  |  | Other |  | 4 | J32 | 419 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2
419-3 | PM110XA-CS-97779.04-3 | CS |  |  | Other |  | 4 | J32 | 419 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2
419-4 | PM110XA-CS-97779.04-4 | CS |  |  | Other |  | 4 | J32 | 419 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 12.928 | 8 | 8
420-1 | PM110XA-CS-97779.05-1 | CS | 2020-08-11 | 2020-08-11 | Other | TRUE | 4 | J32 | 420 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS | 3000 | 11.152 | 7 | 7 | [5 empty] | 0
420-2 | PM110XA-CS-97779.05-2 | CS | 2020-08-11 | 2020-09-01 | Other | TRUE | 4 | J32 | 420 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS,XS |  | 17.776 | 11 | 11 | [5 empty] | 21
421-1 | PM110XA-CS-97779.06-1 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 421 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-28 |  |  |  |  | 1 |  | 16
421-2 | PM110XA-CS-97779.06-2 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 421 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-26 |  |  |  |  | 1 |  | 14
421-3 | PM110XA-CS-97779.06-3 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 421 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 6.464 | 4 | 4 | 2020-09-01 |  |  |  |  | 1 |  | 20
422-1 | PM110XA-CS-97779.07-1 | CS | 2020-09-01 |  | Other | TRUE | 4 | J32 | 422 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 9.696 | 6 | 6
422-2 | PM110XA-CS-97779.07-2 | CS | 2020-09-01 |  | Other | TRUE | 4 | J32 | 422 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS | 3000 | 11.232 | 8 | 8
423-1 | PM110XA-CS-97779.08-1 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 423 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-09-01 |  |  |  |  | 1 |  | 20
423-2 | PM110XA-CS-97779.08-2 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 423 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-28 |  |  |  |  | 1 |  | 16
423-3 | PM110XA-CS-97779.08-3 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 423 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-26 |  |  |  |  | 1 |  | 14
424-1 | PM110XA-CS-97779.09-1 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 424 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS,XS,XS |  | 19.392 | 12 | 12 | [5 empty] | 1
424-2 | PM110XA-CS-97779.09-2 | CS |  |  | Other |  | 4 | J32 | 424 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 14.544 | 9 | 9
424-3 | PM110XA-CS-97779.09-3 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 424 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS | 3000 | 14.384 | 9 | 9 | [5 empty] | 1
425-1 | PM110XA-CS-97782.01-1 | CS |  |  | Other |  | 4 | J32 | 425 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160160 |  | 11.808 | 6 | 6
425-2 | PM110XA-CS-97782.01-2 | CS |  |  | Other |  | 4 | J32 | 425 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160160 |  | 9.84 | 5 | 5
425-3 | PM110XA-CS-97782.01-3 | CS |  |  | Other |  | 4 | J32 | 425 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 1.6016e+20 | 6000 | 21.984 | 10 | 10
426-1 | PM110XA-CS-97782.02-1 | CS |  |  | Other |  | 4 | J32 | 426 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
426-2 | PM110XA-CS-97782.02-2 | CS |  |  | Other |  | 4 | J32 | 426 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 1.6016e+20 | 6000 | 18.976 | 10 | 10
426-3 | PM110XA-CS-97782.02-3 | CS |  |  | Other |  | 4 | J32 | 426 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
427-1 | PM110XA-CS-97782.03-1 | CS |  |  | Other |  | 4 | J32 | 427 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160 |  | 5.904 | 3 | 3
427-2 | PM110XA-CS-97782.03-2 | CS |  |  | Other |  | 4 | J32 | 427 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 1.6016e+20 | 6000 | 22.672 | 11 | 11
428-1 | PM110XA-CS-97782.04-1 | CS |  |  | Other |  | 4 | J32 | 428 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160160 |  | 9.84 | 5 | 5
428-2 | PM110XA-CS-97782.04-2 | CS |  |  | Other |  | 4 | J32 | 428 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
428-3 | PM110XA-CS-97782.04-3 | CS |  |  | Other |  | 4 | J32 | 428 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
429-1 | PM110XA-CS-97782.05-1 | CS |  |  | Other |  | 4 | J32 | 429 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160160 |  | 9.84 | 5 | 5
429-2 | PM110XA-CS-97782.05-2 | CS |  |  | Other |  | 4 | J32 | 429 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 1.6016e+20 | 6000 | 18.976 | 10 | 10
429-3 | PM110XA-CS-97782.05-3 | CS |  |  | Other |  | 4 | J32 | 429 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160 |  | 5.904 | 3 | 3
430-1 | PM110XA-CS-97782.06-1 | CS |  |  | Other |  | 4 | J32 | 430 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
430-2 | PM110XA-CS-97782.06-2 | CS |  |  | Other |  | 4 | J32 | 430 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
430-3 | PM110XA-CS-97782.06-3 | CS |  |  | Other |  | 4 | J32 | 430 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 1.6016e+17 |  | 15.744 | 8 | 8
431-1 | PM110XA-CS-97782.07-1 | CS |  |  | Other |  | 4 | J32 | 431 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160160 |  | 11.808 | 6 | 6
431-2 | PM110XA-CS-97782.07-2 | CS |  |  | Other |  | 4 | J32 | 431 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
431-3 | PM110XA-CS-97782.07-3 | CS |  |  | Other |  | 4 | J32 | 431 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160160 |  | 11.808 | 6 | 6
432-1 | PM110XA-CS-97782.08-1 | CS |  |  | Other |  | 4 | J32 | 432 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160160160 |  | 9.84 | 5 | 5
432-2 | PM110XA-CS-97782.08-2 | CS |  |  | Other |  | 4 | J32 | 432 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
433-1 | PM110XA-CS-97782.09-1 | CS |  |  | Other |  | 4 | J32 | 433 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
433-2 | PM110XA-CS-97782.09-2 | CS |  |  | Other |  | 4 | J32 | 433 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 1.6016e+26 | 6000 | 24.88 | 13 | 13
434-1 | PM110XA-CS-97782.10-1 | CS |  |  | Other |  | 4 | J32 | 434 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE | 160160 |  | 1.968 | 1 | 1
434-2 | PM110XA-CS-97782.10-2 | CS |  |  | Other |  | 4 | J32 | 434 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
434-3 | PM110XA-CS-97782.10-3 | CS |  |  | Other |  | 4 | J32 | 434 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE | 160160 |  | 1.968 | 1 | 1
435-1 | PM110XA-CS-98376.01-1 | CS |  |  | Other |  | 4 | J32 | 435 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
435-2 | PM110XA-CS-98376.01-2 | CS |  |  | Other |  | 4 | J32 | 435 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
435-3 | PM110XA-CS-98376.01-3 | CS |  |  | Other |  | 4 | J32 | 435 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 7.872 | 4 | 4
435-4 | PM110XA-CS-98376.01-4 | CS |  |  | Other |  | 4 | J32 | 435 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 |  | 3.936 | 2 | 2
436-1 | PM110XA-CS-98376.02-1 | CS |  |  | Other |  | 4 | J32 | 436 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
436-2 | PM110XA-CS-98376.02-2 | CS |  |  | Other |  | 4 | J32 | 436 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
436-3 | PM110XA-CS-98376.02-3 | CS |  |  | Other |  | 4 | J32 | 436 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
436-4 | PM110XA-CS-98376.02-4 | CS |  |  | Other |  | 4 | J32 | 436 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
437-1 | PM110XA-CS-98376.03-1 | CS |  |  | Other |  | 4 | J32 | 437 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
437-2 | PM110XA-CS-98376.03-2 | CS |  |  | Other |  | 4 | J32 | 437 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
437-3 | PM110XA-CS-98376.03-3 | CS |  |  | Other |  | 4 | J32 | 437 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
437-4 | PM110XA-CS-98376.03-4 | CS |  |  | Other |  | 4 | J32 | 437 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160160 |  | 1.968 | 1 | 1
437-5 | PM110XA-CS-98376.03-5 | CS |  |  | Other |  | 4 | J32 | 437 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 160160160 | 6000 | 7.168 | 4 | 4
438-1 | PM110XA-CS-98376.04-1 | CS |  |  | Other |  | 4 | J32 | 438 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object] | PIPE | 160 |  | 0 | 0 | 0
438-2 | PM110XA-CS-98376.04-2 | CS |  |  | Other |  | 4 | J32 | 438 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160160160 | 6000 | 8.896 | 4 | 4
438-3 | PM110XA-CS-98376.04-3 | CS |  |  | Other |  | 4 | J32 | 438 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,PIPE | 160160160160160 | 6000 | 15.04 | 8 | 8
439-1 | PM110XA-CS-98413.01-1 | CS |  |  | Other |  | 4 | J32 | 439 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,XS,160 |  | 8.08 | 5 | 5
439-2 | PM110XA-CS-98413.01-2 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 439 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS | 3000 | 6.304 | 4 | 4 | [5 empty] | 1
439-3 | PM110XA-CS-98413.01-3 | CS | 2020-08-11 | 2020-08-13 | Other | TRUE | 4 | J32 | 439 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-28 |  |  |  |  | 2 |  | 15
440-1 | PM110XA-CS-98413.02-1 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 440 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1 | 2020-08-28 |  |  |  |  | 1 |  | 16
440-2 | PM110XA-CS-98413.02-2 | CS | 2020-08-11 | 2020-08-13 | Other | TRUE | 4 | J32 | 440 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1 | 2020-09-01 |  |  |  |  | 2 |  | 19
440-3 | PM110XA-CS-98413.02-3 | CS | 2020-08-11 | 2020-08-25 | Other | TRUE | 4 | J32 | 440 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-25 |  |  |  |  | 14 |  | 0
440-4 | PM110XA-CS-98413.02-4 | CS | 2020-08-11 | 2020-08-13 | Other | TRUE | 4 | J32 | 440 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-26 |  |  |  |  | 2 |  | 13
440-5 | PM110XA-CS-98413.02-5 | CS |  |  | Other |  | 4 | J32 | 440 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS | 3000 | 8 | 6 | 6
441-1 | PM110XA-CS-98413.03-1 | CS | 2020-08-11 | 2020-09-01 | Other | TRUE | 4 | J32 | 441 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS | 3000 | 7.92 | 5 | 5 | [5 empty] | 21
441-2 | PM110XA-CS-98413.03-2 | CS | 2020-08-11 | 2020-09-01 | Other | TRUE | 4 | J32 | 441 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 4.848 | 3 | 3 | [5 empty] | 21
441-3 | PM110XA-CS-98413.03-3 | CS | 2020-08-11 | 2020-08-13 | Other | TRUE | 4 | J32 | 441 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-26 |  |  |  |  | 2 |  | 13
441-4 | PM110XA-CS-98413.03-4 | CS | 2020-08-11 | 2020-08-13 | Other | TRUE | 4 | J32 | 441 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-26 |  |  |  |  | 2 |  | 13
442-1 | PM110XA-CS-98413.04-1 | CS |  |  | Other |  | 4 | J32 | 442 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS | 3000 | 3.152 | 3 | 3
442-2 | PM110XA-CS-98413.04-2 | CS | 2020-08-11 | 2020-09-01 | Other | TRUE | 4 | J32 | 442 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 6.464 | 4 | 4 | [5 empty] | 21
442-3 | PM110XA-CS-98413.04-3 | CS | 2020-08-11 | 2020-08-31 | Other | TRUE | 4 | J32 | 442 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1 | 2020-08-31 |  |  |  |  | 20 |  | 0
442-4 | PM110XA-CS-98413.04-4 | CS | 2020-08-11 | 2020-08-13 | Other | TRUE | 4 | J32 | 442 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-26 |  |  |  |  | 2 |  | 13
442-5 | PM110XA-CS-98413.04-5 | CS | 2020-08-11 | 2020-08-13 | Other | TRUE | 4 | J32 | 442 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-28 |  |  |  |  | 2 |  | 15
443-1 | PM110XA-CS-99999.01-1 | CS |  |  | Other |  | 4 | J32 | 443 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160 |  | 12 | 10 | 10
444-1 | PM110XA-CS-99999.02-1 | CS |  |  | Other |  | 4 | J32 | 444 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,VALVES / IN-LINE ITEMS,PIPE,VALVES / IN-LINE ITEMS | 160160 |  | 10.896 | 9 | 9
444-2 | PM110XA-CS-99999.02-2 | CS |  |  | Other |  | 4 | J32 | 444 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] | PIPE | 160 |  | 2.4 | 2 | 2
444-3 | PM110XA-CS-99999.02-3 | CS |  |  | Other |  | 4 | J32 | 444 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160 |  | 2.4 | 2 | 2
445-1 | PM110XA-CS-99999.03-1 | CS |  |  | Other |  | 4 | J32 | 445 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160 |  | 9.6 | 8 | 8
446-1 | PM110XA-CS-99999.04-1 | CS |  |  | Other |  | 4 | J32 | 446 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,VALVES / IN-LINE ITEMS,PIPE,VALVES / IN-LINE ITEMS | 160160160 |  | 12.096 | 10 | 10
446-2 | PM110XA-CS-99999.04-2 | CS |  |  | Other |  | 4 | J32 | 446 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] | PIPE | 160 |  | 0 | 0 | 0
446-3 | PM110XA-CS-99999.04-3 | CS |  |  | Other |  | 4 | J32 | 446 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE | 160160 |  | 3.6 | 3 | 3
447-1 | PM110XA-CS-99999.05-1 | CS |  |  | Other |  | 4 | J32 | 447 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160 |  | 16.8 | 14 | 14
448-1 | PM110XA-CS-99999.06-1 | CS |  |  | Other |  | 4 | J32 | 448 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,VALVES / IN-LINE ITEMS,VALVES / IN-LINE ITEMS,PIPE | 160160160 |  | 12.096 | 10 | 10
448-2 | PM110XA-CS-99999.06-2 | CS |  |  | Other |  | 4 | J32 | 448 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] | PIPE | 160 |  | 0 | 0 | 0
448-3 | PM110XA-CS-99999.06-3 | CS |  |  | Other |  | 4 | J32 | 448 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] | PIPE | 160160 |  | 3.6 | 3 | 3
449-1 | PM110XA-CS-99999.07-1 | CS |  |  | Other |  | 4 | J32 | 449 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,VALVES / IN-LINE ITEMS,PIPE,VALVES / IN-LINE ITEMS | 160160160 |  | 14.496 | 12 | 12
449-2 | PM110XA-CS-99999.07-2 | CS |  |  | Other |  | 4 | J32 | 449 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] | PIPE | 160 |  | 0 | 0 | 0
449-3 | PM110XA-CS-99999.07-3 | CS |  |  | Other |  | 4 | J32 | 449 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160160 |  | 3.6 | 3 | 3
450-1 | PM110XA-CS-99999.08-1 | CS |  |  | Other |  | 4 | J32 | 450 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | VALVES / IN-LINE ITEMS,VALVES / IN-LINE ITEMS,PIPE,PIPE | 160160160 |  | 14.496 | 12 | 12
450-2 | PM110XA-CS-99999.08-2 | CS |  |  | Other |  | 4 | J32 | 450 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] | PIPE | 160 |  | 0 | 0 | 0
450-3 | PM110XA-CS-99999.08-3 | CS |  |  | Other |  | 4 | J32 | 450 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160160 |  | 3.6 | 3 | 3
451-1 | PM110XA-CS-99999.09-1 | CS |  |  | Other |  | 4 | J32 | 451 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,VALVES / IN-LINE ITEMS,VALVES / IN-LINE ITEMS,PIPE | 160160160 |  | 14.496 | 12 | 12
451-2 | PM110XA-CS-99999.09-2 | CS |  |  | Other |  | 4 | J32 | 451 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] | PIPE | 160 |  | 0 | 0 | 0
451-3 | PM110XA-CS-99999.09-3 | CS |  |  | Other |  | 4 | J32 | 451 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] | PIPE | 160160 | 6000 | 0 | 0 | 0
451-4 | PM110XA-CS-99999.09-4 | CS |  |  | Other |  | 4 | J32 | 451 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] | PIPE | 160 |  | 3.6 | 3 | 3
452-1 | PM110XA-N-100388.01-1 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 452 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS,XS,XS,XS |  | 22.624 | 14 | 14 | [5 empty] | 1
452-2 | PM110XA-N-100388.01-2 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 452 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 8.08 | 5 | 5 | [5 empty] | 1
453-1 | PM110XA-N-100388.02-1 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 453 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS | 3000 | 6.304 | 4 | 4 | 2020-09-02 |  |  |  |  | 1 |  | 21
453-2 | PM110XA-N-100388.02-2 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 453 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-08-31 |  |  |  |  | 1 |  | 19
453-3 | PM110XA-N-100388.02-3 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 4 | J32 | 453 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS | 3000 | 15.312 | 11 | 11 | [5 empty] | 2
453-4 | PM110XA-N-100388.02-4 | CS | 2020-08-11 | 2020-08-12 | Other | TRUE | 4 | J32 | 453 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 4.848 | 3 | 3 | 2020-09-01 |  |  |  |  | 1 |  | 20
454-1 | PM110XA-N-100388.03-1 | CS | 2020-08-11 | 2020-08-31 | Other | TRUE | 4 | J32 | 454 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2 | 2020-09-01 |  |  |  |  | 20 |  | 1
454-2 | PM110XA-N-100388.03-2 | CS | 2020-08-11 | 2020-08-25 | Other | TRUE | 4 | J32 | 454 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-28 |  |  |  |  | 14 |  | 3
454-3 | PM110XA-N-100388.03-3 | CS | 2020-08-11 | 2020-08-19 | Other | TRUE | 4 | J32 | 454 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS | 3000 | 1.712 | 1 | 1 | 2020-08-20 |  |  |  |  | 8 |  | 1
454-4 | PM110XA-N-100388.03-4 | CS | 2020-08-11 | 2020-08-18 | Other | TRUE | 4 | J32 | 454 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-19 |  |  |  |  | 7 |  | 1
454-5 | PM110XA-N-100388.03-5 | CS | 2020-08-11 | 2020-08-31 | Other | TRUE | 4 | J32 | 454 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1 | 2020-09-01 |  |  |  |  | 20 |  | 1
454-6 | PM110XA-N-100388.03-6 | CS | 2020-08-11 | 2020-08-31 | Other | TRUE | 4 | J32 | 454 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1 | 2020-09-01 |  |  |  |  | 20 |  | 1
455-1 | PM110XA-N-100388.04-1 | CS | 2020-08-11 | 2020-08-18 | Other | TRUE | 4 | J32 | 455 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-19 |  |  |  |  | 7 |  | 1
455-2 | PM110XA-N-100388.04-2 | CS | 2020-08-11 | 2020-08-18 | Other | TRUE | 4 | J32 | 455 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-18 |  |  |  |  | 7 |  | 0
455-3 | PM110XA-N-100388.04-3 | CS | 2020-08-11 | 2020-08-18 | Other | TRUE | 4 | J32 | 455 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-18 |  |  |  |  | 7 |  | 0
455-4 | PM110XA-N-100388.04-4 | CS | 2020-08-11 | 2020-08-18 | Other | TRUE | 4 | J32 | 455 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-18 |  |  |  |  | 7 |  | 0
455-5 | PM110XA-N-100388.04-5 | CS | 2020-08-11 | 2020-08-17 | Other | TRUE | 4 | J32 | 455 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-18 |  |  |  |  | 6 |  | 1
455-6 | PM110XA-N-100388.04-6 | CS | 2020-08-11 | 2020-08-17 | Other | TRUE | 4 | J32 | 455 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-19 |  |  |  |  | 6 |  | 2
455-7 | PM110XA-N-100388.04-7 | CS | 2020-08-11 | 2020-08-17 | Other | TRUE | 4 | J32 | 455 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-18 |  |  |  |  | 6 |  | 1
455-8 | PM110XA-N-100388.04-8 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 4 | J32 | 455 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS | 3000 | 7.232 | 6 | 6 | 2020-09-01 |  |  |  |  | 2 |  | 13
456-1 | PM110XA-N-100388.05-1 | CS | 2020-08-11 | 2020-09-01 | Other | TRUE | 4 | J32 | 456 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1 | [5 empty] | 21
456-2 | PM110XA-N-100388.05-2 | CS | 2020-08-11 | 2020-09-01 | Other | TRUE | 4 | J32 | 456 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS | 3000 | 6.304 | 4 | 4 | [5 empty] | 21
456-3 | PM110XA-N-100388.05-3 | CS | 2020-08-17 | 2020-08-19 | Other | TRUE | 4 | J32 | 456 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS | 30003000 | 10.56 | 8 | 8 | [5 empty] | 2
457-1 | PM110XA-PW-100395.01-1 | CS |  |  | Other |  | 4 | J32 | 457 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS |  | 14.416 | 9 | 9
457-2 | PM110XA-PW-100395.01-2 | CS |  |  | Other |  | 4 | J32 | 457 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 3.232 | 2 | 2
457-3 | PM110XA-PW-100395.01-3 | CS |  |  | Other |  | 4 | J32 | 457 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
457-4 | PM110XA-PW-100395.01-4 | CS |  |  | Other |  | 4 | J32 | 457 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS | 3000 | 1.712 | 1 | 1
458-1 | PM110XA-PW-100395.02-1 | CS |  |  | Other |  | 4 | J32 | 458 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
458-2 | PM110XA-PW-100395.02-2 | CS |  |  | Other |  | 4 | J32 | 458 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1
458-3 | PM110XA-PW-100395.02-3 | CS |  |  | Other |  | 4 | J32 | 458 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 8.08 | 5 | 5
459-1 | PM110XA-PW-100395.03-1 | CS |  |  | Other |  | 4 | J32 | 459 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
459-2 | PM110XA-PW-100395.03-2 | CS |  |  | Other |  | 4 | J32 | 459 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
459-3 | PM110XA-PW-100395.03-3 | CS |  |  | Other |  | 4 | J32 | 459 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
460-1 | PM110XA-PW-100395.04-1 | CS |  |  | Other |  | 4 | J32 | 460 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
460-2 | PM110XA-PW-100395.04-2 | CS |  |  | Other |  | 4 | J32 | 460 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
460-3 | PM110XA-PW-100395.04-3 | CS |  |  | Other |  | 4 | J32 | 460 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
461-1 | PM110XA-PW-100395.05-1 | CS |  |  | Other |  | 4 | J32 | 461 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
461-2 | PM110XA-PW-100395.05-2 | CS |  |  | Other |  | 4 | J32 | 461 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS | 3000 | 7.232 | 6 | 6
461-3 | PM110XA-PW-100395.05-3 | CS |  |  | Other |  | 4 | J32 | 461 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object] |  | XS,XS |  | 1.616 | 1 | 1
462-1 | PM110XA-PW-100395.06-1 | CS |  |  | Other |  | 4 | J32 | 462 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS | 3000 | 6.304 | 4 | 4
462-2 | PM110XA-PW-100395.06-2 | CS |  |  | Other |  | 4 | J32 | 462 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS | 30003000 | 10.56 | 8 | 8
463-1 | PM110XA-S-97778.01-1 | CS | 2020-08-05 | 2020-09-01 | Other | TRUE | 4 | J32 | 463 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS | 6000 | 21.296 | 9 | 9 | [5 empty] | 27
463-2 | PM110XA-S-97778.01-2 | CS | 2020-08-05 | 2020-08-31 | Other | TRUE | 4 | J32 | 463 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 22.32 | 9 | 9 | [5 empty] | 26
463-3 | PM110XA-S-97778.01-3 | CS | 2020-08-05 | 2020-08-25 | Other | TRUE | 4 | J32 | 463 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 4.96 | 2 | 2 | 2020-08-26 |  |  |  |  | 20 |  | 1
463-4 | PM110XA-S-97778.01-4 | CS | 2020-08-20 | 2020-09-01 | Other | TRUE | 4 | J32 | 463 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 4.96 | 2 | 2 | 2020-09-01 |  |  |  |  | 12 |  | 0
464-1 | PM110XA-S-97778.02-1 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 4 | J32 | 464 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 4.96 | 2 | 2 | [5 empty] | 11
464-2 | PM110XA-S-97778.02-2 | CS |  |  | Other |  | 4 | J32 | 464 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 12.4 | 5 | 5
464-3 | PM110XA-S-97778.02-3 | CS |  |  | Other |  | 4 | J32 | 464 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,XS,XS,XS,XS,XS,XS,160 | 6000 | 33.84 | 14 | 14
465-1 | PM110XA-S-97778.03-1 | CS | 2020-08-05 | 2020-08-28 | Other | TRUE | 4 | J32 | 465 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS |  | 9.92 | 4 | 4 | 2020-08-31 |  |  |  |  | 23 |  | 3
465-2 | PM110XA-S-97778.03-2 | CS | 2020-08-20 | 2020-09-01 | Other | TRUE | 4 | J32 | 465 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 4.96 | 2 | 2 | [5 empty] | 12
465-3 | PM110XA-S-97778.03-3 | CS | 2020-08-20 | 2020-09-01 | Other | TRUE | 4 | J32 | 465 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 4.96 | 2 | 2 | [5 empty] | 12
465-4 | PM110XA-S-97778.03-4 | CS |  |  | Other |  | 4 | J32 | 465 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,XS,XS,XS,XS,XS,XS,XS,160,XS,XS | 6000 | 44.08 | 18 | 18
466-1 | PM110XA-S-97778.04-1 | CS | 2020-08-20 | 2020-09-01 | Other | TRUE | 4 | J32 | 466 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS | 6000 | 16.336 | 7 | 7 | [5 empty] | 12
466-2 | PM110XA-S-97778.04-2 | CS |  |  | Other |  | 4 | J32 | 466 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 22.32 | 9 | 9
466-3 | PM110XA-S-97778.04-3 | CS |  |  | Other |  | 4 | J32 | 466 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 4.96 | 2 | 2
467-1 | PM110XA-S-97778.05-1 | CS |  |  | Other |  | 4 | J32 | 467 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 4.96 | 2 | 2
467-2 | PM110XA-S-97778.05-2 | CS | 2020-08-20 | 2020-09-01 | Other | TRUE | 4 | J32 | 467 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 22.32 | 9 | 9 | [5 empty] | 12
467-3 | PM110XA-S-97778.05-3 | CS |  |  | Other |  | 4 | J32 | 467 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 4.96 | 2 | 2
468-1 | PM110XA-S-97778.06-1 | CS |  |  | Other |  | 4 | J32 | 468 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 7.44 | 3 | 3
468-2 | PM110XA-S-97778.06-2 | CS |  |  | Other |  | 4 | J32 | 468 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,XS,XS,XS,XS,XS,XS,160,XS,XS | 6000 | 39.12 | 16 | 16
469-1 | PM110XA-S-97778.07-1 | CS |  |  | Other |  | 4 | J32 | 469 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS |  | 2.48 | 1 | 1
469-2 | PM110XA-S-97778.07-2 | CS | 2020-08-20 |  | Other |  | 4 | J32 | 469 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0
469-3 | PM110XA-S-97778.07-3 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 4 | J32 | 469 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 7.952 | 2 | 2 | [5 empty] | 11
470-1 | PM110XA-S-98378.01-1 | CS | 2020-08-04 | 2020-08-05 | Other | TRUE | 4 | J32 | 470 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 1 |  | 5
470-2 | PM110XA-S-98378.01-2 | CS | 2020-08-04 | 2020-08-05 | Other | TRUE | 4 | J32 | 470 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 1 |  | 5
470-3 | PM110XA-S-98378.01-3 | CS | 2020-08-04 | 2020-08-05 | Other | TRUE | 4 | J32 | 470 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object] |  | XS,XS |  | 4.096 | 2 | 2 | 2020-08-11 |  |  |  |  | 1 |  | 6
470-4 | PM110XA-S-98378.01-4 | CS | 2020-08-04 | 2020-08-05 | Other | TRUE | 4 | J32 | 470 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 8.192 | 4 | 4 | 2020-08-11 |  |  |  |  | 1 |  | 6
471-1 | PM110XA-S-98378.02-1 | CS |  |  | Other |  | 4 | J32 | 471 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,XS,XS,160,XS | 6000 | 15.856 | 8 | 8
471-2 | PM110XA-S-98378.02-2 | CS | 2020-08-04 | 2020-08-05 | Other | TRUE | 4 | J32 | 471 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-08-10 |  |  |  |  | 1 |  | 5
471-3 | PM110XA-S-98378.02-3 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 4 | J32 | 471 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | [5 empty] | 11
472-1 | PM110XA-S-98378.03-1 | CS |  |  | Other |  | 4 | J32 | 472 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160,XS,XS,XS,XS,XS,XS | 6000 | 22 | 11 | 11
472-2 | PM110XA-S-98378.03-2 | CS | 2020-08-04 | 2020-08-05 | Other | TRUE | 4 | J32 | 472 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS | 6000 | 9.648 | 5 | 5 | 2020-08-12 |  |  |  |  | 1 |  | 7
472-3 | PM110XA-S-98378.03-3 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 4 | J32 | 472 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 6.144 | 3 | 3 | [5 empty] | 11
473-1 | PM110XA-S-98378.04-1 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 4 | J32 | 473 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | [5 empty] | 11
473-2 | PM110XA-S-98378.04-2 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 4 | J32 | 473 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | XS |  | 0 | 0 | 0 | [5 empty] | 11
473-3 | PM110XA-S-98378.04-3 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 4 | J32 | 473 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object] |  | XS,XS |  | 2.048 | 1 | 1 | [5 empty] | 11
473-4 | PM110XA-S-98378.04-4 | CS |  |  | Other |  | 4 | J32 | 473 |  | UP |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | 160,XS,XS,XS,XS,XS | 6000 | 17.904 | 9 | 9
474-1 | PM110XA-S-98378.05-1 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 4 | J32 | 474 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object],[object Object] |  | XS |  | 0 | 0 | 0 | 2020-09-02 |  |  |  |  | 11 |  | 2
474-2 | PM110XA-S-98378.05-2 | CS | 2020-08-20 |  | Other |  | 4 | J32 | 474 | ISS | ISS | PA | HOLD | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS | 6000 | 5.552 | 3 | 3
474-3 | PM110XA-S-98378.05-3 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 4 | J32 | 474 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  | XS |  | 0 | 0 | 0 | 2020-09-01 |  |  |  |  | 11 |  | 1
474-4 | PM110XA-S-98378.05-4 | CS | 2020-08-20 | 2020-08-31 | Other | TRUE | 4 | J32 | 474 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS |  | 8.192 | 4 | 4 | [5 empty] | 11
475-1 | PK102XA-CW-100027.01-1 | CS |  |  | Other |  | 6 | J20 | 475 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE | XS,160,XS | 300030003000 | 0 | 0 | 0
475-2 | PK102XA-CW-100027.01-2 | CS |  |  | Other |  | 6 | J20 | 475 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object] | PIPE | XS,160,XS |  | 0 | 0 | 0
476-1 | PK102XA-CW-100028.01-1 | CS |  |  | Other |  | 6 | J20 | 476 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object] | PIPE | 160,XS |  | 0 | 0 | 0
476-2 | PK102XA-CW-100028.01-2 | CS |  |  | Other |  | 6 | J20 | 476 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] | PIPE,VALVES / IN-LINE ITEMS | XS,160,XS | 30003000 | 0 | 0 | 0
477-1 | PM101XA-CCW-97620.01-1 | CS | 2020-09-01 |  | Other | TRUE | 6 | J21 | 477 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 0 | 0 | 0
477-2 | PM101XA-CCW-97620.01-2 | CS | 2020-09-01 |  | Other | TRUE | 6 | J21 | 477 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 0 | 0 | 0
478-1 | PM101XA-CCW-97621.01-1 | CS | 2020-09-01 |  | Other | TRUE | 6 | J21 | 478 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS |  | 0 | 0 | 0
478-2 | PM101XA-CCW-97621.01-2 | CS | 2020-09-01 |  | Other | TRUE | 6 | J21 | 478 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | XS,XS,XS,XS,XS,XS,XS |  | 0 | 0 | 0
479-1 | PM102XA-SO-97623.01-1 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 479 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S |  | 0 | 0 | 0
479-2 | PM102XA-SO-97623.01-2 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 479 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S |  | 0 | 0 | 0
479-3 | PM102XA-SO-97623.01-3 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 479 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S |  | 0 | 0 | 0
479-4 | PM102XA-SO-97623.01-4 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 479 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S |  | 0 | 0 | 0 | [5 empty] | 5
479-5 | PM102XA-SO-97623.01-5 | 304/304L SS | 2020-09-01 |  | Other | TRUE | 7 | J04 | 479 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Issued | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S |  | 0 | 0 | 0
479-6 | PM102XA-SO-97623.01-6 | 304/304L SS | 2020-08-26 | 2020-08-31 | Other | TRUE | 7 | J04 | 479 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Pulled | [object Object],[object Object],[object Object],[object Object],[object Object],[object Object] |  | 80S,80S,80S,80S,80S,80S |  | 0 | 0 | 0 | [5 empty] | 5
479-7 | PM102XA-SO-97623.01-7 | 304/304L SS | 2020-08-13 | 2020-08-18 | Other | TRUE | 7 | J04 | 479 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-18 |  |  |  |  | 5 |  | 0
2000-1 | PK101XA-CCW-1513.02-1 | CS | 2020-08-11 | 2020-08-17 | Other | TRUE | 11 | J18 | 2000 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  |  |  |  | 6 |  | 0
2001-1 | PK101XA-CCW-1514.02-1 | CS | 2020-08-11 | 2020-08-17 | Other | TRUE | 11 | J18 | 2001 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  |  |  |  | 6 |  | 0
2002-1 | PK101XA-CCW-1611.01-1 | CS | 2020-08-11 | 2020-08-17 | Other | TRUE | 11 | J13 | 2002 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  | STD |  | 0 | 0 | 0 | 2020-08-17 |  |  |  |  | 6 |  | 0
2002-2 | PK101XA-CCW-1611.01-2 | CS | 2020-08-17 | 2020-08-24 | Other | TRUE | 11 | J13 | 2002 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-24 |  |  |  |  | 7 |  | 0
2003-1 | PK101XA-CCW-1612.01-2 | CS | 2020-08-11 | 2020-08-24 | Other | TRUE | 11 | J13 | 2003 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  | STD |  | 0 | 0 | 0 | 2020-08-24 |  |  |  |  | 13 |  | 0
2003-2 | PK101XA-CCW-1612.01-1 | CS | 2020-08-17 | 2020-08-17 | Other | TRUE | 11 | J13 | 2003 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  |  |  |  | 0 |  | 0
2031-1 | PK104XA-CNV-107.03-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2031 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2032-1 | PK104XA-CNV-301.04-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2032 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2033-1 | PK104XA-CNV-301.05-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2033 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2034-1 | PK104XA-CNV-315.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2034 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2035-1 | PK104XA-CNV-315.03-1 | ALUMINUM |  |  | Other |  | 12 | J01 | 2035 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2036-1 | PK104XA-CNV-315.04-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2036 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2037-1 | PK104XA-CNV-315.05-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2037 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2038-1 | PK104XA-CNV-315.06-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2038 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2039-1 | PK104XA-CNV-315.07-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2039 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2040-1 | PK104XA-CNV-315.08-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2040 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2041-1 | PK104XA-CNV-315.09-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2041 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2042-1 | PK104XA-CNV-315.10-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2042 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2043-1 | PK104XA-CNV-325.06-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2043 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2044-1 | PK104XA-CNV-325.08-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2044 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2045-1 | PK104XA-CNV-325.09-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2045 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2046-1 | PK104XA-CNV-325.10-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2046 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2047-1 | PK104XA-CNV-325.11-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2047 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2048-1 | PK104XA-CNV-325.12-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2048 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2049-1 | PK104XA-CNV-325.16-1 | ALUMINUM |  |  | Other |  | 12 | J01 | 2049 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2050-1 | PK104XA-CNV-325.17-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2050 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2051-1 | PK104XA-CNV-325.19-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2051 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2052-1 | PK104XA-CNV-402.01-1 |  |  |  | Other |  | 2 | J14 | 2052 |  | X |  | HOLD | 1 | 7052 | CP CHEM | On Hold | [object Object] | FLANGES |  |  | 0 | 0 | 0
2053-1 | PK104XA-CNV-1603.03-1 | ALUMINUM |  |  | Other |  | 12 | J01 | 2053 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2054-1 | PK104XA-CNV-1603.04-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2054 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2055-1 | PK104XA-CNV-3003.01-1 | ALUMINUM |  |  | Other |  | 12 | J01 | 2055 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2056-1 | PK104XA-CNV-3003.02-1 | ALUMINUM |  |  | Other |  | 2 | J14 | 2056 |  | UP |  |  | 1 | 7052 | CP CHEM | Not Workable | [object Object] | FLANGES |  |  | 0 | 0 | 0
2136-1 | PM101XA-TR-V1550D.01-1 | CS | 2020-08-20 | 2020-08-25 | Other | TRUE | 5 | J07 | 2136 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object] |  |  |  | 0 | 0 | 0 | [5 empty] | 5
2137-1 | PM101XA-TR-V1550J.01-1 | CS | 2020-08-11 | 2020-08-17 | Other | TRUE | 5 | J07 | 2137 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  |  |  |  | 6 |  | 0
2141-1 | PM101XA-TR-V1650D.01-1 | CS | 2020-08-20 | 2020-08-25 | Other | TRUE | 5 | J06 | 2141 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Pulled | [object Object] |  |  |  | 0 | 0 | 0 | [5 empty] | 5
2142-1 | PM101XA-TR-V1650J.01-1 | CS | 2020-08-11 | 2020-08-17 | Other | TRUE | 5 | J06 | 2142 | ISS | ISS | PA |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  |  |  |  | 6 |  | 0
2149-1 | PM102XA-TR-F140EN4.01-1 | 304/304L SS | 2020-08-11 | 2020-08-17 | Other | TRUE | 7 | J04 | 2149 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  |  |  |  | 6 |  | 0
2150-1 | PM102XA-TR-F140EN5.01-1 | 304/304L SS | 2020-08-11 | 2020-08-17 | Other | TRUE | 7 | J04 | 2150 | ISS | ISS | BR |  | 1 | 7052 | CP CHEM | Welded Out | [object Object] |  |  |  | 0 | 0 | 0 | 2020-08-17 |  |  |  |  | 6 |  | 0