## PRINTOUT
CP CHEM: 7052 |  | 1295 Spools |  | 931 Workable |  | 1107 Issued
SPOOLS BY SCOPE | [5 empty] | Workable Man Hours (By Material)
SPOOLS | Performance | Client | Other | TOTAL |  |  |  | Carbon | Stainless | TOTAL
Valves | [5 empty] | Workable Man Hours
Flanges
Fittings | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
Pipe | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Supports | [5 empty] | Valves
Issued | [5 empty] | Flanges
Workable (Not Issued) | [5 empty] | Fittings
Issued (Missing Items) | [5 empty] | Supports
On Hold (No Shorts) | [5 empty] | TOTAL
Discrepancies
TOTAL | [5 empty] | Pipe
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Supports | [5 empty] | Supports
TOTAL | [5 empty] | TOTAL
Pipe | [5 empty] | Pipe
Not on Line List | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Purchased
7052 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
Nozzle |  | 153 | 0 | 0 | 153 | 79 | 74 | 0 | 23 | 130 | 0% | 51.6% | 15.0%
J30 | 1 | 9 | 0 | 3 | 6 | 3 | 6 | 3 | 0 | 9 | 33.3% | 33.3% | 0.0%
J14 | 2 | 123 | 2 | 121 | 2 | 120 | 3 | 0 | 108 | 15 | 98.4% | 97.6% | 87.8%
J23 | 3 | 45 | 0 | 45 | 0 | 44 | 1 | 43 | 9 | 36 | 100% | 97.8% | 20.0%
J32 | 4 | 237 | 0 | 217 | 20 | 222 | 15 | 113 | 128 | 109 | 91.6% | 93.7% | 54.0%
J06 | 5 | 151 | 5 | 74 | 77 | 71 | 80 | 60 | 28 | 123 | 49.0% | 47.0% | 18.5%
J07 | 5 | 150 | 5 | 80 | 70 | 67 | 83 | 54 | 34 | 116 | 53.3% | 44.7% | 22.7%
J21 | 6 | 42 | 0 | 41 | 1 | 41 | 1 | 31 | 12 | 30 | 97.6% | 97.6% | 28.6%
J20 | 6 | 21 | 1 | 20 | 1 | 21 | 0 | 21 | 0 | 21 | 95.2% | 100% | 0.0%
J04 | 7 | 158 | 4 | 147 | 11 | 146 | 12 | 12 | 122 | 36 | 93.0% | 92.4% | 77.2%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 40 | 2 | 40 | 100% | 100% | 4.8%
J25 | 8 | 39 | 13 | 25 | 14 | 19 | 20 | 1 | 12 | 27 | 64.1% | 48.7% | 30.8%
J10 | 8 | 10 | 1 | 7 | 3 | 5 | 5 | 5 | 0 | 10 | 70.0% | 50.0% | 0.0%
J19 | 9 | 3 | 0 | 3 | 0 | 1 | 2 | 0 | 1 | 2 | 100% | 33.3% | 33.3%
J03 | 10 | 9 | 0 | 9 | 0 | 9 | 0 | 9 | 5 | 4 | 100% | 100% | 55.6%
J13 | 11 | 22 | 0 | 22 | 0 | 22 | 0 | 10 | 14 | 8 | 100% | 100% | 63.6%
J18 | 11 | 25 | 0 | 25 | 0 | 25 | 0 | 12 | 15 | 10 | 100% | 100% | 60.0%
J01 | 12 | 53 | 6 | 47 | 6 | 46 | 7 | 31 | 14 | 39 | 88.7% | 86.8% | 26.4%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
TOTALS |  | 1295 | 37 | 931 | 364 | 986 | 309 | 448 | 527 | 768 | 72% | 76% | 41%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
Nozzle |  | 153 | 0 | 0 | 153 | 79 | 74 | 0 | 23 | 130 | 0% | 51.6% | 15.0%
J30 | 1 | 9 | 0 | 3 | 6 | 3 | 6 | 3 | 0 | 9 | 33.3% | 33.3% | 0.0%
J14 | 2 | 123 | 2 | 121 | 2 | 120 | 3 | 0 | 108 | 15 | 98.4% | 97.6% | 87.8%
J23 | 3 | 45 | 0 | 45 | 0 | 44 | 1 | 43 | 9 | 36 | 100% | 97.8% | 20.0%
J32 | 4 | 237 | 0 | 217 | 20 | 222 | 15 | 113 | 128 | 109 | 91.6% | 93.7% | 54.0%
J06 | 5 | 151 | 5 | 74 | 77 | 71 | 80 | 60 | 28 | 123 | 49.0% | 47.0% | 18.5%
J07 | 5 | 150 | 5 | 80 | 70 | 67 | 83 | 54 | 34 | 116 | 53.3% | 44.7% | 22.7%
J21 | 6 | 42 | 0 | 41 | 1 | 41 | 1 | 31 | 12 | 30 | 97.6% | 97.6% | 28.6%
J20 | 6 | 21 | 1 | 20 | 1 | 21 | 0 | 21 | 0 | 21 | 95.2% | 100% | 0.0%
J04 | 7 | 158 | 4 | 147 | 11 | 146 | 12 | 12 | 122 | 36 | 93.0% | 92.4% | 77.2%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 40 | 2 | 40 | 100% | 100% | 4.8%
J25 | 8 | 39 | 13 | 25 | 14 | 19 | 20 | 1 | 12 | 27 | 64.1% | 48.7% | 30.8%
J10 | 8 | 10 | 1 | 7 | 3 | 5 | 5 | 5 | 0 | 10 | 70.0% | 50.0% | 0.0%
J19 | 9 | 3 | 0 | 3 | 0 | 1 | 2 | 0 | 1 | 2 | 100% | 33.3% | 33.3%
J03 | 10 | 9 | 0 | 9 | 0 | 9 | 0 | 9 | 5 | 4 | 100% | 100% | 55.6%
J13 | 11 | 22 | 0 | 22 | 0 | 22 | 0 | 10 | 14 | 8 | 100% | 100% | 63.6%
J18 | 11 | 25 | 0 | 25 | 0 | 25 | 0 | 12 | 15 | 10 | 100% | 100% | 60.0%
J01 | 12 | 53 | 6 | 47 | 6 | 46 | 7 | 31 | 14 | 39 | 88.7% | 86.8% | 26.4%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
TOTALS |  | 1295 | 37 | 931 | 364 | 986 | 309 | 448 | 527 | 768 | 72% | 76% | 41%

## Areas Summary (By Material)
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J04 | 7 | 154 | 4 | 143 | 11 | 142 | 12 | 12 | 122 | 32 | 92.9% | 92.2% | 79.2%
J05 | 7 | 42 | 0 | 42 | 0 | 42 | 0 | 40 | 2 | 40 | 100% | 100% | 4.8%
J18 | 11 | 13 | 0 | 13 | 0 | 13 | 0 | 0 | 12 | 1 | 100% | 100% | 92.3%
J13 | 11 | 12 | 0 | 12 | 0 | 12 | 0 | 0 | 9 | 3 | 100% | 100% | 75.0%
J32 | 4 | 38 | 0 | 38 | 0 | 38 | 0 | 0 | 36 | 2 | 100% | 100% | 94.7%
Nozzle |  | 31 | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 31 | 0% | 0.0% | 0.0%
TOTALS |  | 290 | 4 | 248 | 42 | 247 | 43 | 52 | 181 | 109 | 86% | 85% | 62%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J13 | 11 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 5 | 5 | 100% | 100% | 50.0%
J18 | 11 | 12 | 0 | 12 | 0 | 12 | 0 | 12 | 3 | 9 | 100% | 100% | 25.0%
J01 | 12 | 28 | 0 | 28 | 0 | 28 | 0 | 27 | 5 | 23 | 100% | 100% | 17.9%
J30 | 1 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J03 | 10 | 9 | 0 | 9 | 0 | 9 | 0 | 9 | 5 | 4 | 100% | 100% | 55.6%
J23 | 3 | 45 | 0 | 45 | 0 | 44 | 1 | 43 | 9 | 36 | 100% | 97.8% | 20.0%
- | #N/A | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 3 | 100% | 100% | 0.0%
J32 | 4 | 199 | 0 | 179 | 20 | 184 | 15 | 113 | 92 | 107 | 89.9% | 92.5% | 46.2%
J07 | 5 | 121 | 5 | 54 | 67 | 41 | 80 | 37 | 8 | 113 | 44.6% | 33.9% | 6.6%
J06 | 5 | 122 | 5 | 51 | 71 | 45 | 77 | 39 | 6 | 116 | 41.8% | 36.9% | 4.9%
J21 | 6 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 2 | 18 | 100% | 100% | 10.0%
J20 | 6 | 11 | 1 | 10 | 1 | 11 | 0 | 11 | 0 | 11 | 90.9% | 100% | 0.0%
J04 | 7 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 100% | 100% | 0.0%
J10 | 8 | 10 | 1 | 7 | 3 | 5 | 5 | 5 | 0 | 10 | 70.0% | 50.0% | 0.0%
J25 | 8 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 4 | 50.0% | 50.0% | 0.0%
TOTALS |  | 601 | 14 | 437 | 164 | 421 | 180 | 333 | 135 | 466 | 73% | 70% | 22%
A333 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 100% | 100% | 0.0%
J20 | 6 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 100% | 100% | 0.0%
J21 | 6 | 12 | 0 | 11 | 1 | 11 | 1 | 11 | 0 | 12 | 91.7% | 91.7% | 0.0%
TOTALS |  | 26 | 0 | 25 | 1 | 25 | 1 | 25 | 0 | 26 | 96% | 96% | 0%
ALUMINUM Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 122 | 2 | 120 | 2 | 119 | 3 | 0 | 107 | 15 | 98.4% | 97.5% | 87.7%
J01 | 12 | 17 | 6 | 11 | 6 | 10 | 7 | 0 | 6 | 11 | 64.7% | 58.8% | 35.3%
J19 | 9 | 3 | 0 | 3 | 0 | 1 | 2 | 0 | 1 | 2 | 100% | 33.3% | 33.3%
J25 | 8 | 35 | 11 | 23 | 12 | 17 | 18 | 0 | 12 | 23 | 65.7% | 48.6% | 34.3%
Nozzle |  | 122 | 0 | 0 | 122 | 79 | 43 | 0 | 23 | 99 | 0% | 64.8% | 18.9%
TOTALS |  | 299 | 19 | 157 | 142 | 226 | 73 | 0 | 149 | 150 | 53% | 76% | 50%
304/304L SS CRYO Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J01 | 12 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 3 | 1 | 100% | 100% | 75.0%
J21 | 6 | 10 | 0 | 10 | 0 | 10 | 0 | 0 | 10 | 0 | 100% | 100% | 100%
TOTALS |  | 14 | 0 | 14 | 0 | 14 | 0 | 0 | 13 | 1 | 100% | 100% | 93%
Galv. Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J06 | 5 | 29 | 0 | 23 | 6 | 26 | 3 | 21 | 22 | 7 | 79.3% | 89.7% | 75.9%
J07 | 5 | 29 | 0 | 26 | 3 | 26 | 3 | 17 | 26 | 3 | 89.7% | 89.7% | 89.7%
TOTALS |  | 58 | 0 | 49 | 9 | 52 | 6 | 38 | 48 | 10 | 84% | 90% | 83%
A105 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J14 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 100% | 100% | 100%
TOTALS |  | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 100% | 100% | 100%
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
J30 | 1 | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 0% | 0.0% | 0.0%
TOTALS |  | 6 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 6 | 0% | 0% | 0%

## Spool Location
Not Workable | 327
Workable | 4
Issued | 29
Pulled | 11
Welded Out | 81
Shipped to Coating | 305
Ready To Deliver | 0
Delivered | 501
On Hold | 37

## Shorts by Scope
| 1295 Spools | 931 Workable | 1107 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 9 | 0
Flanges | 17 | 0 | 0
Fittings | 34 | 0 | 0
Supports | 30 | 0 | 0
TOTAL
Pipe | 117.7 | 0 | 0
Not on Line List

## Purchased by Scope
| 1295 Spools | 931 Workable | 1107 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 1 | 0
Flanges | 2 | 0 | 0
Fittings | 4 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 98.7 | 0 | 0

## No Material by Scope
| 1295 Spools | 931 Workable | 1107 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 8 | 0
Flanges | 15 | 0 | 0
Fittings | 30 | 0 | 0
Supports | 30 | 0 | 0
TOTAL
Pipe | 19 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 7

## Spools by Scope
| 1295 Spools | 931 Workable | 1107 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 9 | 0
Flanges | 32 | 0 | 0
Fittings | 11 | 0 | 0
Pipe | 7 | 0 | 0
Supports | 3 | 0 | 0
Issued |  |  |  | 1107
Workable (Not Issued) |  |  |  | 4
Issued (Missing Items) |  |  |  | 6
On Hold (No Shorts) |  |  |  | 3
Discrepancies |  |  |  | 21
TOTAL |  |  |  | 1295

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)
216-1 |  |  | 7052-CCW-VALVE-564-1
241-2 |  |  | 7052-CCW-VALVE-565-1
296-3 |  |  | 7052-CCW-VALVE-568-1
328-2 |  |  | 7052-CCW-VALVE-573-1
331-1 |  |  | 7052-CCW-VALVE-574-1
388-1 |  |  | 7052-CCW-VALVE-575-1
7052-CCW-VALVE-576-1
7052-CS-VALVE-569-1
7052-CS-VALVE-570-1
7052-CW-VALVE-566-1
7052-CW-VALVE-567-1
7052-GN-VALVE-563-1
7052-GN-VALVE-571-1
7052-GN-VALVE-572-1
PM110XA-CS-99999.09-4