## PRINTOUT
DUPONT: 7114 |  | 2935 Spools |  | 1959 Workable |  | 1823 Issued
SPOOLS BY SCOPE | [5 empty] | Workable Man Hours (By Material)
SPOOLS | Performance | Client | Other | TOTAL |  |  |  | Carbon | Stainless | TOTAL
Valves | 0 | 0 | 0 | 0 |  | Workable Man Hours
Flanges | 187 | 0 | 0 | 187
Fittings | 331 | 0 | 0 | 331 |  | TOTAL PURCHASED (ITEM QUANTITIES)
Pipe | 208 | 0 | 0 | 208 |  | ITEMS | Performance | Client | Other | TOTAL
Supports | 0 | 0 | 0 | 0 |  | Valves | 0 | 0 | 0 | 0
Issued |  |  |  | 1823 |  | Flanges | 203 | 0 | 0 | 203
Workable (Not Issued) |  |  |  | 193 |  | Fittings | 300 | 0 | 0 | 300
Issued (Missing Items) |  |  |  | 0 |  | Supports | 0 | 0 | 0 | 0
On Hold (No Shorts) |  |  |  | 51 |  | TOTAL | 503 | 0 | 0 | 503
Discrepancies |  |  |  | 6
TOTAL | 726 | 0 | 0 | 2935 |  | Pipe | 162.6 | 0 | 0 | 162.6
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0 | 0 |  | Valves | 0 | 0 | 0 | 0
Flanges | 682 | 0 | 0 | 682 |  | Flanges | 479 | 0 | 0 | 479
Fittings | 1230 | 0 | 0 | 1230 |  | Fittings | 930 | 0 | 0 | 930
Supports | 0 | 0 | 0 | 0 |  | Supports | 0 | 0 | 0 | 0
TOTAL | 1912 | 0 | 0 | 1912 |  | TOTAL | 1409 | 0 | 0 | 1409
Pipe | 2467 | 0 | 0 | 2467 |  | Pipe | 2304.4 | 0 | 0 | 2304.4
Not on Line List |  |  |  | 0 |  | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
[6 empty] | Purchased | 0 | 0 | 0 | 0
7114 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
6 | 1 | 1848 | 79 | 1334 | 514 | 947 | 901 | 149 | 0 | 1848 | 72.2% | 51.2% | 0.0%
0 | 2 | 530 | 6 | 415 | 115 | 17 | 513 | 0 | 0 | 530 | 78.3% | 3.2% | 0.0%
7 | 3 | 218 | 11 | 84 | 134 | 3 | 215 | 0 | 0 | 218 | 38.5% | 1.4% | 0.0%
8 | 4 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0% | 0.0% | 0.0%
3 | 5 | 78 | 2 | 32 | 46 | 2 | 76 | 0 | 0 | 78 | 41.0% | 2.6% | 0.0%
4 | 6 | 86 | 6 | 22 | 64 | 0 | 86 | 0 | 0 | 86 | 25.6% | 0.0% | 0.0%
1 | 7 | 41 | 1 | 14 | 27 | 0 | 41 | 0 | 0 | 41 | 34.1% | 0.0% | 0.0%
2 | 8 | 132 | 5 | 58 | 74 | 4 | 128 | 0 | 0 | 132 | 43.9% | 3.0% | 0.0%
TOTALS |  | 2935 | 110 | 1959 | 976 | 973 | 1962 | 149 | 0 | 2935 | 67% | 33% | 0%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
6 | 1-1 | 1848 | 79 | 1334 | 514 | 947 | 901 | 149 | 0 | 1848 | 72.2% | 51.2% | 0.0%
0 | 2 | 530 | 6 | 415 | 115 | 17 | 513 | 0 | 0 | 530 | 78.3% | 3.2% | 0.0%
7 | 3 | 218 | 11 | 84 | 134 | 3 | 215 | 0 | 0 | 218 | 38.5% | 1.4% | 0.0%
8 | 4 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0% | 0.0% | 0.0%
3 | 5 | 78 | 2 | 32 | 46 | 2 | 76 | 0 | 0 | 78 | 41.0% | 2.6% | 0.0%
4 | 6 | 86 | 6 | 22 | 64 | 0 | 86 | 0 | 0 | 86 | 25.6% | 0.0% | 0.0%
1 | 7 | 41 | 1 | 14 | 27 | 0 | 41 | 0 | 0 | 41 | 34.1% | 0.0% | 0.0%
2 | 8 | 132 | 5 | 58 | 74 | 4 | 128 | 0 | 0 | 132 | 43.9% | 3.0% | 0.0%
TOTALS |  | 2935 | 110 | 1959 | 976 | 973 | 1962 | 149 | 0 | 2935 | 67% | 33% | 0%

## Areas Summary (By Material)
316/316L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
6 | 1-1 | 541 | 13 | 440 | 101 | 344 | 197 | 0 | 0 | 541 | 81.3% | 63.6% | 0.0%
0 | 2 | 145 | 4 | 111 | 34 | 0 | 145 | 0 | 0 | 145 | 76.6% | 0.0% | 0.0%
7 | 3 | 25 | 0 | 16 | 9 | 0 | 25 | 0 | 0 | 25 | 64.0% | 0.0% | 0.0%
3 | 5 | 42 | 0 | 15 | 27 | 0 | 42 | 0 | 0 | 42 | 35.7% | 0.0% | 0.0%
4 | 6 | 48 | 3 | 11 | 37 | 0 | 48 | 0 | 0 | 48 | 22.9% | 0.0% | 0.0%
TOTALS |  | 801 | 20 | 593 | 208 | 344 | 457 | 0 | 0 | 801 | 74% | 43% | 0%
304/304L SS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
6 | 1-1 | 585 | 44 | 409 | 176 | 264 | 321 | 0 | 0 | 585 | 69.9% | 45.1% | 0.0%
0 | 2 | 133 | 2 | 109 | 24 | 0 | 133 | 0 | 0 | 133 | 82.0% | 0.0% | 0.0%
7 | 3 | 20 | 4 | 7 | 13 | 0 | 20 | 0 | 0 | 20 | 35.0% | 0.0% | 0.0%
3 | 5 | 5 | 1 | 0 | 5 | 0 | 5 | 0 | 0 | 5 | 0% | 0.0% | 0.0%
2 | 8 | 22 | 0 | 12 | 10 | 0 | 22 | 0 | 0 | 22 | 54.5% | 0.0% | 0.0%
4 | 6 | 13 | 0 | 7 | 6 | 0 | 13 | 0 | 0 | 13 | 53.8% | 0.0% | 0.0%
TOTALS |  | 778 | 51 | 544 | 234 | 264 | 514 | 0 | 0 | 778 | 70% | 34% | 0%
CS-GALV Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
6 | 1-1 | 327 | 9 | 219 | 108 | 165 | 162 | 79 | 0 | 327 | 67.0% | 50.5% | 0.0%
7 | 3 | 114 | 1 | 45 | 69 | 0 | 114 | 0 | 0 | 114 | 39.5% | 0.0% | 0.0%
0 | 2 | 124 | 0 | 106 | 18 | 17 | 107 | 0 | 0 | 124 | 85.5% | 13.7% | 0.0%
3 | 5 | 24 | 1 | 13 | 11 | 2 | 22 | 0 | 0 | 24 | 54.2% | 8.3% | 0.0%
2 | 8 | 59 | 3 | 27 | 32 | 2 | 57 | 0 | 0 | 59 | 45.8% | 3.4% | 0.0%
8 | 4 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0% | 0.0% | 0.0%
4 | 6 | 19 | 0 | 3 | 16 | 0 | 19 | 0 | 0 | 19 | 15.8% | 0.0% | 0.0%
1 | 7 | 15 | 1 | 4 | 11 | 0 | 15 | 0 | 0 | 15 | 26.7% | 0.0% | 0.0%
TOTALS |  | 684 | 15 | 417 | 267 | 186 | 498 | 79 | 0 | 684 | 61% | 27% | 0%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
6 | 1-2 | 395 | 13 | 266 | 129 | 174 | 221 | 70 | 0 | 395 | 67.3% | 44.1% | 0.0%
0 | 2 | 127 | 0 | 88 | 39 | 0 | 127 | 0 | 0 | 127 | 69.3% | 0.0% | 0.0%
7 | 3 | 59 | 6 | 16 | 43 | 3 | 56 | 0 | 0 | 59 | 27.1% | 5.1% | 0.0%
2 | 8 | 51 | 2 | 19 | 32 | 2 | 49 | 0 | 0 | 51 | 37.3% | 3.9% | 0.0%
3 | 5 | 7 | 0 | 4 | 3 | 0 | 7 | 0 | 0 | 7 | 57.1% | 0.0% | 0.0%
4 | 6 | 6 | 3 | 1 | 5 | 0 | 6 | 0 | 0 | 6 | 16.7% | 0.0% | 0.0%
1 | 7 | 26 | 0 | 10 | 16 | 0 | 26 | 0 | 0 | 26 | 38.5% | 0.0% | 0.0%
TOTALS |  | 671 | 24 | 404 | 267 | 179 | 492 | 70 | 0 | 671 | 60% | 27% | 0%
CS Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
0 | 2 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 100% | 0.0% | 0.0%
TOTALS |  | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 100% | 0% | 0%

## Spool Location
Not Workable | 866
Workable | 193
Issued | 687
Pulled | 142
Welded Out | 806
Shipped to Coating | 131
Ready To Deliver | 0
Delivered | 0
On Hold | 110

## Shorts by Scope
| 2935 Spools | 1959 Workable | 1823 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0 | 0
Flanges | 682 | 0 | 0 | 682
Fittings | 1230 | 0 | 0 | 1230
Supports | 0 | 0 | 0 | 0
TOTAL | 1912 | 0 | 0 | 1912
Pipe | 2467 | 0 | 0 | 2467
Not on Line List

## Purchased by Scope
| 2935 Spools | 1959 Workable | 1823 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0 | 0
Flanges | 203 | 0 | 0 | 203
Fittings | 300 | 0 | 0 | 300
Supports | 0 | 0 | 0 | 0
TOTAL | 503 | 0 | 0 | 503
Pipe | 162.6 | 0 | 0 | 162.6

## No Material by Scope
| 2935 Spools | 1959 Workable | 1823 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0 | 0
Flanges | 479 | 0 | 0 | 479
Fittings | 930 | 0 | 0 | 930
Supports | 0 | 0 | 0 | 0
TOTAL | 1409 | 0 | 0 | 1409
Pipe | 2304.4 | 0 | 0 | 2304.4

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 0 | 0

## Spools by Scope
| 2935 Spools | 1959 Workable | 1823 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0 | 0
Flanges | 187 | 0 | 0 | 187
Fittings | 331 | 0 | 0 | 331
Pipe | 208 | 0 | 0 | 208
Supports | 0 | 0 | 0 | 0
Issued |  |  |  | 1823
Workable (Not Issued) |  |  |  | 193
Issued (Missing Items) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 51
Discrepancies |  |  |  | 6
TOTAL | 726 | 0 | 0 | 2935

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)
6-7114-831-1
0-7114-842-1A
0-7114-864-1A
2-7114-1064-2
6-7114-1240-1A
6-7114-1260-1A