## PRINTOUT
AIR PRODUCTS: 7116 |  | 628 Spools |  | 628 Workable |  | 0 Issued
SPOOLS BY SCOPE | [5 empty] | Workable Man Hours (By Material)
SPOOLS | Performance | Client | Other | TOTAL |  |  |  | Carbon | Stainless | TOTAL
Valves | [5 empty] | Workable Man Hours
Flanges
Fittings | [5 empty] | TOTAL PURCHASED (ITEM QUANTITIES)
Pipe | [5 empty] | ITEMS | Performance | Client | Other | TOTAL
Supports | [5 empty] | Valves
Issued | [5 empty] | Flanges
Workable (Not Issued) | [5 empty] | Fittings
Issued (Missing Items) | [5 empty] | Supports
On Hold (No Shorts) | [5 empty] | TOTAL
Discrepancies
TOTAL | [5 empty] | Pipe
TOTAL SHORTS (ITEM QUANTITIES) | [5 empty] | TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL |  | ITEMS | Performance | Client | Other | TOTAL
Valves | [5 empty] | Valves
Flanges | [5 empty] | Flanges
Fittings | [5 empty] | Fittings
Supports | [5 empty] | Supports
TOTAL | [5 empty] | TOTAL
Pipe | [5 empty] | Pipe
Not on Line List | [5 empty] | SPOOLS MISSING VALVE ONLY
[6 empty] | ITEMS | Performance | Client | Other | TOTAL
Purchased
7116 Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
U010 |  | 502 | 0 | 502 | 0 | 0 | 502 | 0 | 0 | 502 | 100% | 0.0% | 0.0%
U030 |  | 126 | 0 | 126 | 0 | 0 | 126 | 0 | 0 | 126 | 100% | 0.0% | 0.0%
TOTALS |  | 628 | 0 | 628 | 0 | 0 | 628 | 0 | 0 | 628 | 100% | 0% | 0%

## Areas Summary
Areas Summary
Area | Priority | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
U010 |  | 502 | 0 | 502 | 0 | 0 | 502 | 0 | 0 | 502 | 100% | 0.0% | 0.0%
U030 |  | 126 | 0 | 126 | 0 | 0 | 126 | 0 | 0 | 126 | 100% | 0.0% | 0.0%
TOTALS |  | 628 | 0 | 628 | 0 | 0 | 628 | 0 | 0 | 628 | 100% | 0% | 0%

## Areas Summary (By Material)
Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
U010 |  | 244 | 0 | 244 | 0 | 0 | 244 | 0 | 0 | 244 | 100% | 0.0% | 0.0%
U030 |  | 126 | 0 | 126 | 0 | 0 | 126 | 0 | 0 | 126 | 100% | 0.0% | 0.0%
TOTALS |  | 370 | 0 | 370 | 0 | 0 | 370 | 0 | 0 | 370 | 100% | 0% | 0%
A234 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
U010 |  | 95 | 0 | 95 | 0 | 0 | 95 | 0 | 0 | 95 | 100% | 0.0% | 0.0%
TOTALS |  | 95 | 0 | 95 | 0 | 0 | 95 | 0 | 0 | 95 | 100% | 0% | 0%
304 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
U010 |  | 90 | 0 | 90 | 0 | 0 | 90 | 0 | 0 | 90 | 100% | 0.0% | 0.0%
TOTALS |  | 90 | 0 | 90 | 0 | 0 | 90 | 0 | 0 | 90 | 100% | 0% | 0%
A105 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
U010 |  | 41 | 0 | 41 | 0 | 0 | 41 | 0 | 0 | 41 | 100% | 0.0% | 0.0%
TOTALS |  | 41 | 0 | 41 | 0 | 0 | 41 | 0 | 0 | 41 | 100% | 0% | 0%
A106 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
U010 |  | 15 | 0 | 15 | 0 | 0 | 15 | 0 | 0 | 15 | 100% | 0.0% | 0.0%
TOTALS |  | 15 | 0 | 15 | 0 | 0 | 15 | 0 | 0 | 15 | 100% | 0% | 0%
316 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
U010 |  | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 100% | 0.0% | 0.0%
TOTALS |  | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 100% | 0% | 0%
A53 Summary
Area | Priority # | Total Spools | On Hold | Workable | Not Workable | Welded Out | Remaining to Weld Out | Shipped To Paint | Delivered | Remaining to Deliver | Workable % | Weld Out % | Delivered %
U010 |  | 16 | 0 | 16 | 0 | 0 | 16 | 0 | 0 | 16 | 100% | 0.0% | 0.0%
TOTALS |  | 16 | 0 | 16 | 0 | 0 | 16 | 0 | 0 | 16 | 100% | 0% | 0%

## Spool Location
Not Workable | 0
Workable | 628
Issued | 0
Pulled | 0
Welded Out | 0
Shipped to Coating | 0
Ready To Deliver | 0
Delivered | 0
On Hold | 0

## Shorts by Scope
| 628 Spools | 628 Workable | 0 Issued
TOTAL SHORTS (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0
Not on Line List

## Purchased by Scope
| 628 Spools | 628 Workable | 0 Issued
TOTAL PURCHASED (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0

## No Material by Scope
| 628 Spools | 628 Workable | 0 Issued
TOTAL NO MATERIAL (ITEM QUANTITIES)
ITEMS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Supports | 0 | 0 | 0
TOTAL
Pipe | 0 | 0 | 0

## Spool Missing Valve Only
SPOOLS MISSING VALVE ONLY
ITEMS | Performance | Client | Other | TOTAL
Purchased | 0 | 0 | 0

## Spools by Scope
| 628 Spools | 628 Workable | 0 Issued
* What item is holding up the spool and who is responsible for it?
SPOOLS | Performance | Client | Other | TOTAL
Valves | 0 | 0 | 0
Flanges | 0 | 0 | 0
Fittings | 0 | 0 | 0
Pipe | 0 | 0 | 0
Supports | 0 | 0 | 0
Issued |  |  |  | 0
Workable (Not Issued) |  |  |  | 628
Issued (Missing Items) |  |  |  | 0
On Hold (No Shorts) |  |  |  | 0
Discrepancies |  |  |  | 0
TOTAL |  |  |  | 628

## Discrepancies
In Forecast (Issued) | Not In Forecast (Not-Issued) | In Forecast (Not in Line List) | PM In Status Report (Not in Line List)